## Activity Plan
IMPROVEMENT DOZER CAM — PROJECT DEVELOPMENT PLAN | [15 empty] | PROJECT START |  | BULAN |  | TAHUN |  | DURASI (D)
[18 empty] | JUNI |  | 2026 |  | 90 |  |  |  |  | COMPLETE |  |  |  | STILL PROGRESS | [77 empty] | UNDER TARGET (Actual < Plan) | [5 empty] | DELAY / GAP / KETERLAMBATAN | [6 empty] | PROGRESS ON SCHEDULE | [5 empty] | COMPLETED ON PLAN |  |  |  |  | AHEAD OF SCHEDULE | [7 empty] | < 80% |  |  | > 80% & < 90% |  |  |  | > 90% & < 95% |  |  |  | > 95% & < 100% |  |  |  | > 100%
4617400%
TEMA : MENINGKATKAN PHYSICAL AVAILABILITY (PA) LIGHT VEHICLE (LV)
JUDUL : MENURUNKAN BREAKDOWN UNSCHEDULE LV | [15 empty] | PLAN | [90 empty] | ACTUAL | [90 empty] | ACHIVE
[6 empty] | PLAN |  |  | ACTUAL | [6 empty] | Jun 2026 | [29 empty] | Jul 2026 | [30 empty] | Aug 2026 | [29 empty] | Jun 2026 | [29 empty] | Jul 2026 | [30 empty] | Aug 2026 | [29 empty] | Jun 2026 | [29 empty] | Jul 2026 | [30 empty] | Aug 2026
NO | 5 FACTOR | BRAINSTORMING (PROBLEM) | CATEGORY | ACTION PLAN | PIC | PLAN START | DUE DATA | PLAN DURATION | ACTUAL START | ACTUAL FINISH | ACTUAL DURATION | STATUS | DUE STATUS | COMPLETION | COMPLETION_FLAG | [91 empty] | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | time axis 2026-06-01 to 2026-08-30
1 | MAN | User tetap mengoperasikan LV dengan gejala abnormal karena belum memahami batas aman, tidak ada konsekuensi, dan temuan P2H tidak mendapat feedback. | Quick Action | Lakukan refreshment care unit dan sosialisasi kriteria STOP/GO kepada seluruh user LV. | GS-PLANT-SHE | 2026-06-08 | 2026-06-19 | 12 |  |  | No Progress | OPEN | < 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | MAN | Kepedulian rendah karena tidak ada ownership unit dan kinerja pemeliharaan user tidak diukur. | Long Term / Development | Tetapkan user/PIC tetap per LV, KPI compliance P2H, serta evaluasi bulanan per departemen. | GS-HC-USER | 2026-06-15 | 2026-07-17 | 33 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | MAN | PIC LV belum konsisten menindaklanjuti temuan karena tidak ada daily control board dan forum eskalasi. | Quick Action | Buat daily control board: status unit, temuan P2H, aging repair, kebutuhan part, dan PIC follow-up. | GS-PIC LV | 2026-06-08 | 2026-06-15 | 8 |  |  | No Progress | OPEN | < 7 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | MAN | Kualitas troubleshooting mekanik bervariasi dan repeat job belum menjadi bahan evaluasi. | Quick Action | Review mingguan mekanik berdasarkan diagnosis time, repair time, repeat job, dan kualitas closing WO. | PLANT-GS | 2026-06-10 | 2026-07-03 | 24 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | MAN | Kompetensi electrical, engine, brake, dan AC belum merata karena belum ada skill matrix LV. | Long Term / Development | Susun skill matrix; lakukan coaching, pairing mekanik, dan evaluasi kompetensi per sistem. | PLANT-SLD | 2026-06-22 | 2026-08-14 | 54 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | METHOD | P2H menjadi formalitas karena checklist terlalu umum dan tidak memberi panduan gejala abnormal. | Quick Action | Revisi checklist P2H dengan foto standar, item kritikal, klasifikasi temuan, dan bukti pemeriksaan. | GS-PLANT-SHE | 2026-06-08 | 2026-06-26 | 19 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | METHOD | Temuan P2H tidak tertutup karena tidak ada SLA, prioritas risiko, dan verifikasi closing. | Quick Action | Buat register temuan P2H dengan klasifikasi A/B/C, SLA, PIC, evidence, dan verifikasi closing. | GS-PLANT | 2026-06-15 | 2026-07-03 | 19 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | METHOD | PM check tidak efektif karena hanya fokus penggantian periodik, belum berbasis kondisi unit. | Long Term / Development | Tambahkan condition-based inspection saat PM: leak, brake, steering, suspension, electrical, tire, dan abnormal noise. | PLANT | 2026-06-22 | 2026-07-24 | 33 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | METHOD | Tidak ada inspeksi menyeluruh sehingga kerusakan laten baru diketahui saat breakdown. | Quick Action | Laksanakan baseline comprehensive inspection seluruh LV dan keluarkan health score serta repair recommendation. | GS-PLANT-SHE | 2026-06-10 | 2026-07-10 | 31 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | METHOD | Lead time repair panjang karena tidak ada jalur eskalasi berdasarkan aging. | Long Term / Development | Terapkan SOP eskalasi repair >24 jam, >3 hari, >7 hari dengan kebutuhan keputusan yang jelas. | GS-PLANT-LOG | 2026-07-01 | 2026-07-31 | 31 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | METHOD | Jadwal PM bentrok dengan kebutuhan operasi sehingga PM tertunda. | Quick Action | Susun weekly maintenance window dan koordinasi unit replacement dengan user. | GS-PLANT-USER | 2026-06-15 | 2026-06-26 | 12 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | MACHINE | Sebagian LV memiliki health score rendah akibat usia pakai dan backlog repair. | Quick Action | Mapping health condition: fit, monitor, restricted, stop use; buat recovery plan per unit. | GS-PLANT | 2026-06-08 | 2026-07-03 | 26 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | MACHINE | Unit breakdown menekan PA karena tidak tersedia pool/standby sesuai kebutuhan kritikal. | Long Term / Development | Hitung kebutuhan minimum unit dan usulkan standby/replacement berdasarkan utilization serta service level. | GS-HO-OPS | 2026-07-01 | 2026-08-14 | 45 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | MACHINE | Diagnosis dan repair lambat karena tools/scanner belum lengkap atau tidak terkalibrasi. | Quick Action | Inventarisasi dan lengkapi scanner, battery tester, pressure gauge, torque wrench, dan special tools. | PLANT-GS | 2026-06-15 | 2026-07-17 | 33 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | MACHINE | Kerusakan ban/suspensi berulang akibat unit tidak sesuai medan/rute. | Long Term / Development | Review kesesuaian spesifikasi LV, tire type, payload, dan rute penggunaan per unit. | GS-PLANT-OPS | 2026-07-13 | 2026-08-21 | 40 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | MATERIAL | Fast moving part sering kosong karena min-max tidak berbasis konsumsi dan lead time. | Quick Action | Analisis histori 12 bulan dan tetapkan min-max fast moving part LV per model. | LOG-PLANT | 2026-06-08 | 2026-07-03 | 26 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
17 | MATERIAL | Critical part belum tersedia karena belum ada klasifikasi dampak terhadap PA. | Quick Action | Susun critical spare list dan buffer stock untuk part berdampak tinggi terhadap PA. | LOG-GS-PLANT | 2026-06-22 | 2026-07-24 | 33 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | MATERIAL | Part urgent menunggu approval panjang karena alur non-budget tidak memiliki fast track. | Long Term / Development | Usulkan batas otorisasi dan fast-track approval part urgent disertai kontrol penggunaan. | GS-LOG-HO | 2026-07-01 | 2026-08-07 | 38 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
19 | MATERIAL | Part datang tidak sesuai karena identifikasi part number dan data unit tidak akurat. | Quick Action | Validasi master unit, serial number, part book, serta proses double-check sebelum PR/PO. | LOG-PLANT | 2026-06-29 | 2026-07-17 | 19 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | MEASUREMENT | PA LV hanya dilihat sebagai angka akhir sehingga penyebab loss availability tidak terlihat. | Quick Action | Buat dashboard PA per unit dan loss tree: unscheduled, PM, waiting part, waiting mechanic, repeat repair. | GS-PLANT | 2026-06-08 | 2026-06-26 | 19 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
21 | MEASUREMENT | Data P2H, PM, WO, downtime, dan part tersebar sehingga sulit dianalisis. | Long Term / Development | Bangun database per LV yang menghubungkan P2H, PM, WO, downtime, part, biaya, dan closing. | GS-PLANT-LOG | 2026-07-01 | 2026-08-28 | 59 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
22 | ENVIRONMENT | Jalan rusak, genangan, dan debu mempercepat kerusakan ban, suspensi, filter, serta underbody. | Long Term / Development | Mapping hotspot kerusakan; koordinasikan road maintenance, dust control, dan inspeksi rute. | GS-OPS-SHE | 2026-07-01 | 2026-08-14 | 45 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
23 | ENVIRONMENT | Area parkir tidak tertata sehingga inspeksi dan kontrol status unit tidak konsisten. | Quick Action | Bangun inspection point sederhana dengan penerangan, papan status, dan area karantina unit. | GS-SHE | 2026-06-29 | 2026-07-31 | 33 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
24 | ENVIRONMENT | Budaya kejar operasional menyebabkan unit dengan temuan tetap digunakan. | Long Term / Development | Masukkan kepatuhan STOP/GO dan care unit dalam safety accountability meeting. | GS-SHE-OPS | 2026-07-13 | 2026-08-28 | 47 |  |  | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[16 empty] | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | DAILY ACHIVEMENT | [13 empty] | 2026-06-01: 16; 2026-06-02: 16; 2026-06-03: 16; 2026-06-04: 16; 2026-06-05: 16; 2026-06-06: 16; 2026-06-07: 16; 2026-06-08: 16; 2026-06-09: 16; 2026-06-10: 16; 2026-06-11: 16; 2026-06-12: 16; 2026-06-13: 16; 2026-06-14: 16; 2026-06-15: 16; 2026-06-16: 16; 2026-06-17: 16; 2026-06-18: 16; 2026-06-19: 16; 2026-06-20: 16; 2026-06-21: 16; 2026-06-22: 16; 2026-06-23: 16; 2026-06-24: 16; 2026-06-25: 16; 2026-06-26: 16; 2026-06-27: 16; 2026-06-28: 16; 2026-06-29: 16; 2026-06-30: 16; 2026-07-01: 16
|  | DOZER READINESS | PLAN | [12 empty] | 2026-06-01: 15; 2026-06-02: 13; 2026-06-03: 14; 2026-06-04: 11; 2026-06-05: 16; 2026-06-06: 14; 2026-06-07: 16; 2026-06-08: 15; 2026-06-09: 13; 2026-06-10: 14; 2026-06-11: 11; 2026-06-12: 16; 2026-06-13: 14; 2026-06-14: 16; 2026-06-15: 15; 2026-06-16: 13; 2026-06-17: 14; 2026-06-18: 11; 2026-06-19: 16; 2026-06-20: 14; 2026-06-21: 16; 2026-06-22: 15; 2026-06-23: 13; 2026-06-24: 14; 2026-06-25: 11; 2026-06-26: 16; 2026-06-27: 14; 2026-06-28: 16; 2026-06-29: 12; 2026-06-30: 11; 2026-07-01: 15
|  |  | ACTUAL | [12 empty] | 2026-06-01: 93.75%; 2026-06-02: 81.25%; 2026-06-03: 87.5%; 2026-06-04: 68.75%; 2026-06-05: 100%; 2026-06-06: 87.5%; 2026-06-07: 100%; 2026-06-08: 93.75%; 2026-06-09: 81.25%; 2026-06-10: 87.5%; 2026-06-11: 68.75%; 2026-06-12: 100%; 2026-06-13: 87.5%; 2026-06-14: 100%; 2026-06-15: 93.75%; 2026-06-16: 81.25%; 2026-06-17: 87.5%; 2026-06-18: 68.75%; 2026-06-19: 100%; 2026-06-20: 87.5%; 2026-06-21: 100%; 2026-06-22: 93.75%; 2026-06-23: 81.25%; 2026-06-24: 87.5%; 2026-06-25: 68.75%; 2026-06-26: 100%; 2026-06-27: 87.5%; 2026-06-28: 100%; 2026-06-29: 75%; 2026-06-30: 68.75%; 2026-07-01: 93.75%
|  |  | ACHIVE | [12 empty] | 2026-06-01: 90%; 2026-06-02: 90%; 2026-06-03: 90%; 2026-06-04: 90%; 2026-06-05: 90%; 2026-06-06: 90%; 2026-06-07: 90%; 2026-06-08: 90%; 2026-06-09: 90%; 2026-06-10: 90%; 2026-06-11: 90%; 2026-06-12: 90%; 2026-06-13: 90%; 2026-06-14: 90%; 2026-06-15: 90%; 2026-06-16: 90%; 2026-06-17: 90%; 2026-06-18: 90%; 2026-06-19: 90%; 2026-06-20: 90%; 2026-06-21: 90%; 2026-06-22: 90%; 2026-06-23: 90%; 2026-06-24: 90%; 2026-06-25: 90%; 2026-06-26: 90%; 2026-06-27: 90%; 2026-06-28: 90%; 2026-06-29: 90%; 2026-06-30: 90%; 2026-07-01: 90%
|  | PA ALL DOZER | PLAN | [12 empty] | 2026-06-01: 87%; 2026-06-02: 80%; 2026-06-03: 83%; 2026-06-04: 72%; 2026-06-05: 100%; 2026-06-06: 90%; 2026-06-07: 98%; 2026-06-08: 93%; 2026-06-09: 87%; 2026-06-10: 80%; 2026-06-11: 83%; 2026-06-12: 72%; 2026-06-13: 100%; 2026-06-14: 90%; 2026-06-15: 98%; 2026-06-16: 93%; 2026-06-17: 87%; 2026-06-18: 80%; 2026-06-19: 83%; 2026-06-20: 72%; 2026-06-21: 100%; 2026-06-22: 90%; 2026-06-23: 98%; 2026-06-24: 93%; 2026-06-25: 87%; 2026-06-26: 80%; 2026-06-27: 83%; 2026-06-28: 72%; 2026-06-29: 100%; 2026-06-30: 90%; 2026-07-01: 98%
|  |  | ACTUAL | [12 empty] | 2026-06-01: 96.67%; 2026-06-02: 88.89%; 2026-06-03: 92.22%; 2026-06-04: 80%; 2026-06-05: 111.1%; 2026-06-06: 100%; 2026-06-07: 108.9%; 2026-06-08: 103.3%; 2026-06-09: 96.67%; 2026-06-10: 88.89%; 2026-06-11: 92.22%; 2026-06-12: 80%; 2026-06-13: 111.1%; 2026-06-14: 100%; 2026-06-15: 108.9%; 2026-06-16: 103.3%; 2026-06-17: 96.67%; 2026-06-18: 88.89%; 2026-06-19: 92.22%; 2026-06-20: 80%; 2026-06-21: 111.1%; 2026-06-22: 100%; 2026-06-23: 108.9%; 2026-06-24: 103.3%; 2026-06-25: 96.67%; 2026-06-26: 88.89%; 2026-06-27: 92.22%; 2026-06-28: 80%; 2026-06-29: 111.1%; 2026-06-30: 100%; 2026-07-01: 108.9%
|  |  | ACHIVE | [12 empty] | 2026-06-01: 70; 2026-06-02: 70; 2026-06-03: 70; 2026-06-04: 70; 2026-06-05: 70; 2026-06-06: 70; 2026-06-07: 70; 2026-06-08: 70; 2026-06-09: 70; 2026-06-10: 70; 2026-06-11: 70; 2026-06-12: 70; 2026-06-13: 70; 2026-06-14: 70; 2026-06-15: 70; 2026-06-16: 70; 2026-06-17: 70; 2026-06-18: 70; 2026-06-19: 70; 2026-06-20: 70; 2026-06-21: 70; 2026-06-22: 70; 2026-06-23: 70; 2026-06-24: 70; 2026-06-25: 70; 2026-06-26: 70; 2026-06-27: 70; 2026-06-28: 70; 2026-06-29: 70; 2026-06-30: 70; 2026-07-01: 70
|  | MTBF | PLAN | [12 empty] | 2026-06-01: 80; 2026-06-02: 60; 2026-06-03: 50; 2026-06-04: 75; 2026-06-05: 83; 2026-06-06: 65; 2026-06-07: 73; 2026-06-08: 80; 2026-06-09: 60; 2026-06-10: 50; 2026-06-11: 75; 2026-06-12: 83; 2026-06-13: 65; 2026-06-14: 73; 2026-06-15: 80; 2026-06-16: 60; 2026-06-17: 50; 2026-06-18: 75; 2026-06-19: 83; 2026-06-20: 65; 2026-06-21: 73; 2026-06-22: 80; 2026-06-23: 60; 2026-06-24: 50; 2026-06-25: 75; 2026-06-26: 83; 2026-06-27: 65; 2026-06-28: 73; 2026-06-29: 75; 2026-06-30: 83; 2026-07-01: 65
|  |  | ACTUAL | [12 empty] | 2026-06-01: 114.3%; 2026-06-02: 85.71%; 2026-06-03: 71.43%; 2026-06-04: 107.1%; 2026-06-05: 118.6%; 2026-06-06: 92.86%; 2026-06-07: 104.3%; 2026-06-08: 114.3%; 2026-06-09: 85.71%; 2026-06-10: 71.43%; 2026-06-11: 107.1%; 2026-06-12: 118.6%; 2026-06-13: 92.86%; 2026-06-14: 104.3%; 2026-06-15: 114.3%; 2026-06-16: 85.71%; 2026-06-17: 71.43%; 2026-06-18: 107.1%; 2026-06-19: 118.6%; 2026-06-20: 92.86%; 2026-06-21: 104.3%; 2026-06-22: 114.3%; 2026-06-23: 85.71%; 2026-06-24: 71.43%; 2026-06-25: 107.1%; 2026-06-26: 118.6%; 2026-06-27: 92.86%; 2026-06-28: 104.3%; 2026-06-29: 107.1%; 2026-06-30: 118.6%; 2026-07-01: 92.86%
|  |  | ACHIVE | [12 empty] | 2026-06-01: 80; 2026-06-02: 80; 2026-06-03: 80; 2026-06-04: 80; 2026-06-05: 80; 2026-06-06: 80; 2026-06-07: 80; 2026-06-08: 80; 2026-06-09: 80; 2026-06-10: 80; 2026-06-11: 80; 2026-06-12: 80; 2026-06-13: 80; 2026-06-14: 80; 2026-06-15: 80; 2026-06-16: 80; 2026-06-17: 80; 2026-06-18: 80; 2026-06-19: 80; 2026-06-20: 80; 2026-06-21: 80; 2026-06-22: 80; 2026-06-23: 80; 2026-06-24: 80; 2026-06-25: 80; 2026-06-26: 80; 2026-06-27: 80; 2026-06-28: 80; 2026-06-29: 80; 2026-06-30: 80; 2026-07-01: 80
|  | MTTR | PLAN | [12 empty] | 2026-06-01: 80; 2026-06-02: 60; 2026-06-03: 50; 2026-06-04: 75; 2026-06-05: 83; 2026-06-06: 65; 2026-06-07: 73; 2026-06-08: 80; 2026-06-09: 60; 2026-06-10: 50; 2026-06-11: 75; 2026-06-12: 83; 2026-06-13: 65; 2026-06-14: 73; 2026-06-15: 80; 2026-06-16: 60; 2026-06-17: 50; 2026-06-18: 75; 2026-06-19: 83; 2026-06-20: 65; 2026-06-21: 73; 2026-06-22: 80; 2026-06-23: 60; 2026-06-24: 50; 2026-06-25: 75; 2026-06-26: 83; 2026-06-27: 65; 2026-06-28: 73; 2026-06-29: 75; 2026-06-30: 83; 2026-07-01: 65
|  |  | ACTUAL | [12 empty] | 2026-06-01: 100%; 2026-06-02: 75%; 2026-06-03: 62.5%; 2026-06-04: 93.75%; 2026-06-05: 103.8%; 2026-06-06: 81.25%; 2026-06-07: 91.25%; 2026-06-08: 100%; 2026-06-09: 75%; 2026-06-10: 62.5%; 2026-06-11: 93.75%; 2026-06-12: 103.8%; 2026-06-13: 81.25%; 2026-06-14: 91.25%; 2026-06-15: 100%; 2026-06-16: 75%; 2026-06-17: 62.5%; 2026-06-18: 93.75%; 2026-06-19: 103.8%; 2026-06-20: 81.25%; 2026-06-21: 91.25%; 2026-06-22: 100%; 2026-06-23: 75%; 2026-06-24: 62.5%; 2026-06-25: 93.75%; 2026-06-26: 103.8%; 2026-06-27: 81.25%; 2026-06-28: 91.25%; 2026-06-29: 93.75%; 2026-06-30: 103.8%; 2026-07-01: 81.25%
ACHIVE
[6 empty] | klo perlu MTBF | klo perlu MTBF

## DATA
TBL_DOZER_READINESS |  |  |  | TBL_PA ALL DOZER |  |  |  | TBL_MTBF |  |  |  | TBL_MTTR |  |  |  | ACHIVEMENT | [7 empty] | Tbl_Summary | [13 empty] | Tbl_ACH | [33 empty] | Tbl_Daily | [14 empty] | SUM_ACT
PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | NO | 5 FACTOR | CATEGORY | PIC | PLAN START | DUE DATA | PLAN DURATION | ACTUAL START | ACTUAL FINISH | ACTUAL DURATION | STATUS | DUE STATUS | COMPLETION | COMPLETION_FLAG | ACHIVEMENT | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 |  |  | NO | 5 FACTOR | CATEGORY | Attribute | Value | SS | PARAMETER | CATEGORY | DATE | VALUE | BULAN |  | DAY | TYPE | ACHIEVEMENT | DATE | DAILY_PLAN | DAILY_ACTUAL | DOZER_READINESS | PA_DOZER | MTBF | MTTR
DOZER READINESS | PLAN | 1 | 16 | PA ALL DOZER | PLAN | 1 | 90% | MTBF | PLAN | 1 | 70 | MTTR | PLAN | 1 | 80 | DOZER READINESS | ACHIVE | 1 | 93.75% | DAILY ACHIVEMENT | PLAN | 1 | 5% | 1 | MAN | Quick Action | GS-PLANT-SHE | 2026-06-08 | 2026-06-19 | 12 | 0 | N/A | No Progress | OPEN | < 14 HARI | 52.67% | 0 | PLAN | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% |  |  | 1 | MAN | Quick Action | 1 | 0% | FACTOR | DOZER READINESS | PLAN | 1 | 16 | 1 | JANUARI | 46174 | PLAN | 5% | 1 | 5% | 53.5% | 15 | 87% | 80 | 80
DOZER READINESS | ACTUAL | 1 | 15 | PA ALL DOZER | ACTUAL | 1 | 87% | MTBF | ACTUAL | 1 | 80 | MTTR | ACTUAL | 1 | 80 | DOZER READINESS | ACHIVE | 2 | 81.25% | DAILY ACHIVEMENT | PLAN | 2 | 8% | 2 | MAN | Long Term / Development | GS-HC-USER | 2026-06-15 | 2026-07-17 | 33 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | ACTUAL | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A |  |  | 1 | MAN | Quick Action | 2 | 0% | FACTOR | DOZER READINESS | ACTUAL | 1 | 15 | 2 | FEBRUARI | 46174 | ACTUAL | 53.5% | 2 | 8% | 54.33% | 15 | 87% | 80 | 80
DOZER READINESS | PLAN | 2 | 16 | PA ALL DOZER | PLAN | 2 | 90% | MTBF | PLAN | 2 | 70 | MTTR | PLAN | 2 | 80 | DOZER READINESS | ACHIVE | 3 | 87.5% | DAILY ACHIVEMENT | PLAN | 3 | 10% | 3 | MAN | Quick Action | GS-PIC LV | 2026-06-08 | 2026-06-15 | 8 | 0 | N/A | No Progress | OPEN | < 7 HARI | 52.67% | 0 | [34 empty] | 1 | MAN | Quick Action | 3 | 0% | FACTOR | DOZER READINESS | PLAN | 2 | 16 | 3 | MARET | 46175 | PLAN | 8% | 3 | 10% | 55.17% | 13 | 80% | 60 | 60
DOZER READINESS | ACTUAL | 2 | 13 | PA ALL DOZER | ACTUAL | 2 | 80% | MTBF | ACTUAL | 2 | 60 | MTTR | ACTUAL | 2 | 60 | DOZER READINESS | ACHIVE | 4 | 68.75% | DAILY ACHIVEMENT | PLAN | 4 | 12.67% | 4 | MAN | Quick Action | PLANT-GS | 2026-06-10 | 2026-07-03 | 24 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | Tbl_Daily ACH | [33 empty] | 1 | MAN | Quick Action | 4 | 0% | FACTOR | DOZER READINESS | ACTUAL | 2 | 13 | 4 | APRIL | 46175 | ACTUAL | 54.33% | 4 | 12.67% | 56% | 13 | 80% | 60 | 60
DOZER READINESS | PLAN | 3 | 16 | PA ALL DOZER | PLAN | 3 | 90% | MTBF | PLAN | 3 | 70 | MTTR | PLAN | 3 | 80 | DOZER READINESS | ACHIVE | 5 | 100% | DAILY ACHIVEMENT | PLAN | 5 | 15.17% | 5 | MAN | Long Term / Development | PLANT-SLD | 2026-06-22 | 2026-08-14 | 54 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | NO | 5 FACTOR | CATEGORY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | MAN | Quick Action | 5 | 0% | FACTOR | DOZER READINESS | PLAN | 3 | 16 | 5 | MEI | 46176 | PLAN | 10% | 5 | 15.17% | 56.83% | 14 | 83% | 50 | 50
DOZER READINESS | ACTUAL | 3 | 14 | PA ALL DOZER | ACTUAL | 3 | 83% | MTBF | ACTUAL | 3 | 50 | MTTR | ACTUAL | 3 | 50 | DOZER READINESS | ACHIVE | 6 | 87.5% | DAILY ACHIVEMENT | PLAN | 6 | 17.67% | 6 | METHOD | Quick Action | GS-PLANT-SHE | 2026-06-08 | 2026-06-26 | 19 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 1 | MAN | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 6 | 0% | FACTOR | DOZER READINESS | ACTUAL | 3 | 14 | 6 | JUNI | 46176 | ACTUAL | 55.17% | 6 | 17.67% | 60% | 14 | 83% | 50 | 50
DOZER READINESS | PLAN | 4 | 16 | PA ALL DOZER | PLAN | 4 | 90% | MTBF | PLAN | 4 | 70 | MTTR | PLAN | 4 | 80 | DOZER READINESS | ACHIVE | 7 | 100% | DAILY ACHIVEMENT | PLAN | 7 | 20.17% | 7 | METHOD | Quick Action | GS-PLANT | 2026-06-15 | 2026-07-03 | 19 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 2 | MAN | Long Term / Development | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 7 | 100% | FACTOR | DOZER READINESS | PLAN | 4 | 16 | 7 | JULI | 46177 | PLAN | 12.67% | 7 | 20.17% | 63% | 11 | 72% | 75 | 75
DOZER READINESS | ACTUAL | 4 | 11 | PA ALL DOZER | ACTUAL | 4 | 72% | MTBF | ACTUAL | 4 | 75 | MTTR | ACTUAL | 4 | 75 | DOZER READINESS | ACHIVE | 8 | 93.75% | DAILY ACHIVEMENT | PLAN | 8 | 22.67% | 8 | METHOD | Long Term / Development | PLANT | 2026-06-22 | 2026-07-24 | 33 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 3 | MAN | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 8 | 100% | FACTOR | DOZER READINESS | ACTUAL | 4 | 11 | 8 | AGUSTUS | 46177 | ACTUAL | 56% | 8 | 22.67% | 66% | 11 | 72% | 75 | 75
DOZER READINESS | PLAN | 5 | 16 | PA ALL DOZER | PLAN | 5 | 90% | MTBF | PLAN | 5 | 70 | MTTR | PLAN | 5 | 80 | DOZER READINESS | ACHIVE | 9 | 81.25% | DAILY ACHIVEMENT | PLAN | 9 | 25.17% | 9 | METHOD | Quick Action | GS-PLANT-SHE | 2026-06-10 | 2026-07-10 | 31 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 4 | MAN | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 9 | 100% | FACTOR | DOZER READINESS | PLAN | 5 | 16 | 9 | SEPTEMBER | 46178 | PLAN | 15.17% | 9 | 25.17% | 69% | 16 | 100% | 83 | 83
DOZER READINESS | ACTUAL | 5 | 16 | PA ALL DOZER | ACTUAL | 5 | 100% | MTBF | ACTUAL | 5 | 83 | MTTR | ACTUAL | 5 | 83 | DOZER READINESS | ACHIVE | 10 | 87.5% | DAILY ACHIVEMENT | PLAN | 10 | 27.67% | 10 | METHOD | Long Term / Development | GS-PLANT-LOG | 2026-07-01 | 2026-07-31 | 31 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 5 | MAN | Long Term / Development | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 10 | 100% | FACTOR | DOZER READINESS | ACTUAL | 5 | 16 | 10 | OKTOBER | 46178 | ACTUAL | 56.83% | 10 | 27.67% | 72% | 16 | 100% | 83 | 83
DOZER READINESS | PLAN | 6 | 16 | PA ALL DOZER | PLAN | 6 | 90% | MTBF | PLAN | 6 | 70 | MTTR | PLAN | 6 | 80 | DOZER READINESS | ACHIVE | 11 | 68.75% | DAILY ACHIVEMENT | PLAN | 11 | 30.17% | 11 | METHOD | Quick Action | GS-PLANT-USER | 2026-06-15 | 2026-06-26 | 12 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 6 | METHOD | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 11 | 100% | FACTOR | DOZER READINESS | PLAN | 6 | 16 | 11 | NOVEMBER | 46179 | PLAN | 17.67% | 11 | 30.17% | 75% | 14 | 90% | 65 | 65
DOZER READINESS | ACTUAL | 6 | 14 | PA ALL DOZER | ACTUAL | 6 | 90% | MTBF | ACTUAL | 6 | 65 | MTTR | ACTUAL | 6 | 65 | DOZER READINESS | ACHIVE | 12 | 100% | DAILY ACHIVEMENT | PLAN | 12 | 32.67% | 12 | MACHINE | Quick Action | GS-PLANT | 2026-06-08 | 2026-07-03 | 26 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 7 | METHOD | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 12 | 100% | FACTOR | DOZER READINESS | ACTUAL | 6 | 14 | 12 | DESEMBER | 46179 | ACTUAL | 60% | 12 | 32.67% | 78% | 14 | 90% | 65 | 65
DOZER READINESS | PLAN | 7 | 16 | PA ALL DOZER | PLAN | 7 | 90% | MTBF | PLAN | 7 | 70 | MTTR | PLAN | 7 | 80 | DOZER READINESS | ACHIVE | 13 | 87.5% | DAILY ACHIVEMENT | PLAN | 13 | 35.17% | 13 | MACHINE | Long Term / Development | GS-HO-OPS | 2026-07-01 | 2026-08-14 | 45 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 8 | METHOD | Long Term / Development | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 13 | 100% | FACTOR | DOZER READINESS | PLAN | 7 | 16 |  |  | 46180 | PLAN | 20.17% | 13 | 35.17% | 81% | 16 | 98% | 73 | 73
DOZER READINESS | ACTUAL | 7 | 16 | PA ALL DOZER | ACTUAL | 7 | 98% | MTBF | ACTUAL | 7 | 73 | MTTR | ACTUAL | 7 | 73 | DOZER READINESS | ACHIVE | 14 | 100% | DAILY ACHIVEMENT | PLAN | 14 | 37.67% | 14 | MACHINE | Quick Action | PLANT-GS | 2026-06-15 | 2026-07-17 | 33 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 9 | METHOD | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 14 | 100% | FACTOR | DOZER READINESS | ACTUAL | 7 | 16 |  | 5 FACTOR | 46180 | ACTUAL | 63% | 14 | 37.67% | 84% | 16 | 98% | 73 | 73
DOZER READINESS | PLAN | 8 | 16 | PA ALL DOZER | PLAN | 8 | 90% | MTBF | PLAN | 8 | 70 | MTTR | PLAN | 8 | 80 | DOZER READINESS | ACHIVE | 15 | 93.75% | DAILY ACHIVEMENT | PLAN | 15 | 40.17% | 15 | MACHINE | Long Term / Development | GS-PLANT-OPS | 2026-07-13 | 2026-08-21 | 40 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 10 | METHOD | Long Term / Development | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 15 | 100% | FACTOR | DOZER READINESS | PLAN | 8 | 16 |  | MAN | 46181 | PLAN | 22.67% | 15 | 40.17% | 87% | 15 | 93% | 80 | 80
DOZER READINESS | ACTUAL | 8 | 15 | PA ALL DOZER | ACTUAL | 8 | 93% | MTBF | ACTUAL | 8 | 80 | MTTR | ACTUAL | 8 | 80 | DOZER READINESS | ACHIVE | 16 | 81.25% | DAILY ACHIVEMENT | PLAN | 16 | 42.67% | 16 | MATERIAL | Quick Action | LOG-PLANT | 2026-06-08 | 2026-07-03 | 26 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 11 | METHOD | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 16 | 100% | FACTOR | DOZER READINESS | ACTUAL | 8 | 15 |  | METHOD | 46181 | ACTUAL | 66% | 16 | 42.67% | 90% | 15 | 93% | 80 | 80
DOZER READINESS | PLAN | 9 | 16 | PA ALL DOZER | PLAN | 9 | 90% | MTBF | PLAN | 9 | 70 | MTTR | PLAN | 9 | 80 | DOZER READINESS | ACHIVE | 17 | 87.5% | DAILY ACHIVEMENT | PLAN | 17 | 45.17% | 17 | MATERIAL | Quick Action | LOG-GS-PLANT | 2026-06-22 | 2026-07-24 | 33 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 12 | MACHINE | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 17 | 100% | FACTOR | DOZER READINESS | PLAN | 9 | 16 |  | MACHINE | 46182 | PLAN | 25.17% | 17 | 45.17% | 93% | 13 | 87% | 60 | 60
DOZER READINESS | ACTUAL | 9 | 13 | PA ALL DOZER | ACTUAL | 9 | 87% | MTBF | ACTUAL | 9 | 60 | MTTR | ACTUAL | 9 | 60 | DOZER READINESS | ACHIVE | 18 | 68.75% | DAILY ACHIVEMENT | PLAN | 18 | 47.67% | 18 | MATERIAL | Long Term / Development | GS-LOG-HO | 2026-07-01 | 2026-08-07 | 38 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 13 | MACHINE | Long Term / Development | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 18 | 100% | FACTOR | DOZER READINESS | ACTUAL | 9 | 13 |  | MATERIAL | 46182 | ACTUAL | 69% | 18 | 47.67% | 96% | 13 | 87% | 60 | 60
DOZER READINESS | PLAN | 10 | 16 | PA ALL DOZER | PLAN | 10 | 90% | MTBF | PLAN | 10 | 70 | MTTR | PLAN | 10 | 80 | DOZER READINESS | ACHIVE | 19 | 100% | DAILY ACHIVEMENT | PLAN | 19 | 50.17% | 19 | MATERIAL | Quick Action | LOG-PLANT | 2026-06-29 | 2026-07-17 | 19 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 14 | MACHINE | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 19 | 100% | FACTOR | DOZER READINESS | PLAN | 10 | 16 |  | ENVIRONTMENT | 46183 | PLAN | 27.67% | 19 | 50.17% | 99% | 14 | 80% | 50 | 50
DOZER READINESS | ACTUAL | 10 | 14 | PA ALL DOZER | ACTUAL | 10 | 80% | MTBF | ACTUAL | 10 | 50 | MTTR | ACTUAL | 10 | 50 | DOZER READINESS | ACHIVE | 20 | 87.5% | DAILY ACHIVEMENT | PLAN | 20 | 50.17% | 20 | MEASUREMENT | Quick Action | GS-PLANT | 2026-06-08 | 2026-06-26 | 19 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 15 | MACHINE | Long Term / Development | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 20 | 100% | FACTOR | DOZER READINESS | ACTUAL | 10 | 14 |  |  | 46183 | ACTUAL | 72% | 20 | 50.17% | 100% | 14 | 80% | 50 | 50
DOZER READINESS | PLAN | 11 | 16 | PA ALL DOZER | PLAN | 11 | 90% | MTBF | PLAN | 11 | 70 | MTTR | PLAN | 11 | 80 | DOZER READINESS | ACHIVE | 21 | 100% | DAILY ACHIVEMENT | PLAN | 21 | 50.17% | 21 | MEASUREMENT | Long Term / Development | GS-PLANT-LOG | 2026-07-01 | 2026-08-28 | 59 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 16 | MATERIAL | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 21 | 100% | FACTOR | DOZER READINESS | PLAN | 11 | 16 |  |  | 46184 | PLAN | 30.17% | 21 | 50.17% | 100% | 11 | 83% | 75 | 75
DOZER READINESS | ACTUAL | 11 | 11 | PA ALL DOZER | ACTUAL | 11 | 83% | MTBF | ACTUAL | 11 | 75 | MTTR | ACTUAL | 11 | 75 | DOZER READINESS | ACHIVE | 22 | 93.75% | DAILY ACHIVEMENT | PLAN | 22 | 50.17% | 22 | ENVIRONMENT | Long Term / Development | GS-OPS-SHE | 2026-07-01 | 2026-08-14 | 45 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 17 | MATERIAL | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 22 | 100% | FACTOR | DOZER READINESS | ACTUAL | 11 | 11 |  |  | 46184 | ACTUAL | 75% | 22 | 50.17% | 100% | 11 | 83% | 75 | 75
DOZER READINESS | PLAN | 12 | 16 | PA ALL DOZER | PLAN | 12 | 90% | MTBF | PLAN | 12 | 70 | MTTR | PLAN | 12 | 80 | DOZER READINESS | ACHIVE | 23 | 81.25% | DAILY ACHIVEMENT | PLAN | 23 | 50.17% | 23 | ENVIRONMENT | Quick Action | GS-SHE | 2026-06-29 | 2026-07-31 | 33 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 18 | MATERIAL | Long Term / Development | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 23 | 100% | FACTOR | DOZER READINESS | PLAN | 12 | 16 |  |  | 46185 | PLAN | 32.67% | 23 | 50.17% | 100% | 16 | 72% | 83 | 83
DOZER READINESS | ACTUAL | 12 | 16 | PA ALL DOZER | ACTUAL | 12 | 72% | MTBF | ACTUAL | 12 | 83 | MTTR | ACTUAL | 12 | 83 | DOZER READINESS | ACHIVE | 24 | 87.5% | DAILY ACHIVEMENT | PLAN | 24 | 50.17% | 24 | ENVIRONMENT | Long Term / Development | GS-SHE-OPS | 2026-07-13 | 2026-08-28 | 47 | 0 | N/A | No Progress | OPEN | > 14 HARI | 52.67% | 0 | 19 | MATERIAL | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 24 | 100% | FACTOR | DOZER READINESS | ACTUAL | 12 | 16 |  |  | 46185 | ACTUAL | 78% | 24 | 50.17% | 100% | 16 | 72% | 83 | 83
DOZER READINESS | PLAN | 13 | 16 | PA ALL DOZER | PLAN | 13 | 90% | MTBF | PLAN | 13 | 70 | MTTR | PLAN | 13 | 80 | DOZER READINESS | ACHIVE | 25 | 68.75% | DAILY ACHIVEMENT | PLAN | 25 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | 20 | MEASUREMENT | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 25 | 100% | FACTOR | DOZER READINESS | PLAN | 13 | 16 |  |  | 46186 | PLAN | 35.17% | 25 | 50.17% | 100% | 14 | 100% | 65 | 65
DOZER READINESS | ACTUAL | 13 | 14 | PA ALL DOZER | ACTUAL | 13 | 100% | MTBF | ACTUAL | 13 | 65 | MTTR | ACTUAL | 13 | 65 | DOZER READINESS | ACHIVE | 26 | 100% | DAILY ACHIVEMENT | PLAN | 26 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | 21 | MEASUREMENT | Long Term / Development | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 26 | 100% | FACTOR | DOZER READINESS | ACTUAL | 13 | 14 |  |  | 46186 | ACTUAL | 81% | 26 | 50.17% | 100% | 14 | 100% | 65 | 65
DOZER READINESS | PLAN | 14 | 16 | PA ALL DOZER | PLAN | 14 | 90% | MTBF | PLAN | 14 | 70 | MTTR | PLAN | 14 | 80 | DOZER READINESS | ACHIVE | 27 | 87.5% | DAILY ACHIVEMENT | PLAN | 27 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | 22 | ENVIRONMENT | Long Term / Development | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 27 | 100% | FACTOR | DOZER READINESS | PLAN | 14 | 16 |  |  | 46187 | PLAN | 37.67% | 27 | 50.17% | 100% | 16 | 90% | 73 | 73
DOZER READINESS | ACTUAL | 14 | 16 | PA ALL DOZER | ACTUAL | 14 | 90% | MTBF | ACTUAL | 14 | 73 | MTTR | ACTUAL | 14 | 73 | DOZER READINESS | ACHIVE | 28 | 100% | DAILY ACHIVEMENT | PLAN | 28 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | 23 | ENVIRONMENT | Quick Action | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 28 | 100% | FACTOR | DOZER READINESS | ACTUAL | 14 | 16 |  |  | 46187 | ACTUAL | 84% | 28 | 50.17% | 100% | 16 | 90% | 73 | 73
DOZER READINESS | PLAN | 15 | 16 | PA ALL DOZER | PLAN | 15 | 90% | MTBF | PLAN | 15 | 70 | MTTR | PLAN | 15 | 80 | DOZER READINESS | ACHIVE | 29 | 75% | DAILY ACHIVEMENT | PLAN | 29 | 51% | N/A | [7 empty] | N/A | [5 empty] | 24 | ENVIRONMENT | Long Term / Development | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 29 | 100% | FACTOR | DOZER READINESS | PLAN | 15 | 16 |  |  | 46188 | PLAN | 40.17% | 29 | 51% | 100% | 15 | 98% | 80 | 80
DOZER READINESS | ACTUAL | 15 | 15 | PA ALL DOZER | ACTUAL | 15 | 98% | MTBF | ACTUAL | 15 | 80 | MTTR | ACTUAL | 15 | 80 | DOZER READINESS | ACHIVE | 30 | 68.75% | DAILY ACHIVEMENT | PLAN | 30 | 51.83% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 30 | 100% | FACTOR | DOZER READINESS | ACTUAL | 15 | 15 |  |  | 46188 | ACTUAL | 87% | 30 | 51.83% | 100% | 15 | 98% | 80 | 80
DOZER READINESS | PLAN | 16 | 16 | PA ALL DOZER | PLAN | 16 | 90% | MTBF | PLAN | 16 | 70 | MTTR | PLAN | 16 | 80 | DOZER READINESS | ACHIVE | 31 | #N/A | DAILY ACHIVEMENT | PLAN | 31 | 52.67% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 31 | 100% | FACTOR | DOZER READINESS | PLAN | 16 | 16 |  |  | 46189 | PLAN | 42.67% | 31 | 52.67% | 0% | 13 | 93% | 60 | 60
DOZER READINESS | ACTUAL | 16 | 13 | PA ALL DOZER | ACTUAL | 16 | 93% | MTBF | ACTUAL | 16 | 60 | MTTR | ACTUAL | 16 | 60 | PA ALL DOZER | ACHIVE | 1 | 96.67% | DAILY ACHIVEMENT | ACTUAL | 1 | 53.5% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2 | MAN | Quick Action | 3 | 0% | FACTOR | DOZER READINESS | ACTUAL | 16 | 13 |  |  | 46189 | ACTUAL | 90%
DOZER READINESS | PLAN | 17 | 16 | PA ALL DOZER | PLAN | 17 | 90% | MTBF | PLAN | 17 | 70 | MTTR | PLAN | 17 | 80 | PA ALL DOZER | ACHIVE | 2 | 88.89% | DAILY ACHIVEMENT | ACTUAL | 2 | 54.33% | N/A | [7 empty] | N/A | [39 empty] | 2 | MAN | Quick Action | 4 | 0% | FACTOR | DOZER READINESS | PLAN | 17 | 16 |  |  | 46190 | PLAN | 45.17%
DOZER READINESS | ACTUAL | 17 | 14 | PA ALL DOZER | ACTUAL | 17 | 87% | MTBF | ACTUAL | 17 | 50 | MTTR | ACTUAL | 17 | 50 | PA ALL DOZER | ACHIVE | 3 | 92.22% | DAILY ACHIVEMENT | ACTUAL | 3 | 55.17% | N/A | [7 empty] | N/A | [39 empty] | 2 | MAN | Quick Action | 5 | 100% | FACTOR | DOZER READINESS | ACTUAL | 17 | 14 |  |  | 46190 | ACTUAL | 93%
DOZER READINESS | PLAN | 18 | 16 | PA ALL DOZER | PLAN | 18 | 90% | MTBF | PLAN | 18 | 70 | MTTR | PLAN | 18 | 80 | PA ALL DOZER | ACHIVE | 4 | 80% | DAILY ACHIVEMENT | ACTUAL | 4 | 56% | [48 empty] | 2 | MAN | Quick Action | 6 | 0% | FACTOR | DOZER READINESS | PLAN | 18 | 16 |  |  | 46191 | PLAN | 47.67%
DOZER READINESS | ACTUAL | 18 | 11 | PA ALL DOZER | ACTUAL | 18 | 80% | MTBF | ACTUAL | 18 | 75 | MTTR | ACTUAL | 18 | 75 | PA ALL DOZER | ACHIVE | 5 | 111.1% | DAILY ACHIVEMENT | ACTUAL | 5 | 56.83% | [48 empty] | 2 | MAN | Quick Action | 7 | 100% | FACTOR | DOZER READINESS | ACTUAL | 18 | 11 |  |  | 46191 | ACTUAL | 96%
DOZER READINESS | PLAN | 19 | 16 | PA ALL DOZER | PLAN | 19 | 90% | MTBF | PLAN | 19 | 70 | MTTR | PLAN | 19 | 80 | PA ALL DOZER | ACHIVE | 6 | 100% | DAILY ACHIVEMENT | ACTUAL | 6 | 60% | [48 empty] | 2 | MAN | Quick Action | 8 | 100% | FACTOR | DOZER READINESS | PLAN | 19 | 16 |  |  | 46192 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 19 | 16 | PA ALL DOZER | ACTUAL | 19 | 83% | MTBF | ACTUAL | 19 | 83 | MTTR | ACTUAL | 19 | 83 | PA ALL DOZER | ACHIVE | 7 | 108.9% | DAILY ACHIVEMENT | ACTUAL | 7 | 63% | [48 empty] | 2 | MAN | Quick Action | 9 | 100% | FACTOR | DOZER READINESS | ACTUAL | 19 | 16 |  |  | 46192 | ACTUAL | 99%
DOZER READINESS | PLAN | 20 | 16 | PA ALL DOZER | PLAN | 20 | 90% | MTBF | PLAN | 20 | 70 | MTTR | PLAN | 20 | 80 | PA ALL DOZER | ACHIVE | 8 | 103.3% | DAILY ACHIVEMENT | ACTUAL | 8 | 66% | [48 empty] | 2 | MAN | Quick Action | 10 | 100% | FACTOR | DOZER READINESS | PLAN | 20 | 16 |  |  | 46193 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 20 | 14 | PA ALL DOZER | ACTUAL | 20 | 72% | MTBF | ACTUAL | 20 | 65 | MTTR | ACTUAL | 20 | 65 | PA ALL DOZER | ACHIVE | 9 | 96.67% | DAILY ACHIVEMENT | ACTUAL | 9 | 69% | [48 empty] | 2 | MAN | Quick Action | 11 | 100% | FACTOR | DOZER READINESS | ACTUAL | 20 | 14 |  |  | 46193 | ACTUAL | 100%
DOZER READINESS | PLAN | 21 | 16 | PA ALL DOZER | PLAN | 21 | 90% | MTBF | PLAN | 21 | 70 | MTTR | PLAN | 21 | 80 | PA ALL DOZER | ACHIVE | 10 | 88.89% | DAILY ACHIVEMENT | ACTUAL | 10 | 72% | [48 empty] | 2 | MAN | Quick Action | 12 | 100% | FACTOR | DOZER READINESS | PLAN | 21 | 16 |  |  | 46194 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 21 | 16 | PA ALL DOZER | ACTUAL | 21 | 100% | MTBF | ACTUAL | 21 | 73 | MTTR | ACTUAL | 21 | 73 | PA ALL DOZER | ACHIVE | 11 | 92.22% | DAILY ACHIVEMENT | ACTUAL | 11 | 75% | [48 empty] | 2 | MAN | Quick Action | 13 | 100% | FACTOR | DOZER READINESS | ACTUAL | 21 | 16 |  |  | 46194 | ACTUAL | 100%
DOZER READINESS | PLAN | 22 | 16 | PA ALL DOZER | PLAN | 22 | 90% | MTBF | PLAN | 22 | 70 | MTTR | PLAN | 22 | 80 | PA ALL DOZER | ACHIVE | 12 | 80% | DAILY ACHIVEMENT | ACTUAL | 12 | 78% | [48 empty] | 2 | MAN | Quick Action | 14 | 100% | FACTOR | DOZER READINESS | PLAN | 22 | 16 |  |  | 46195 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 22 | 15 | PA ALL DOZER | ACTUAL | 22 | 90% | MTBF | ACTUAL | 22 | 80 | MTTR | ACTUAL | 22 | 80 | PA ALL DOZER | ACHIVE | 13 | 111.1% | DAILY ACHIVEMENT | ACTUAL | 13 | 81% | [48 empty] | 2 | MAN | Quick Action | 15 | 100% | FACTOR | DOZER READINESS | ACTUAL | 22 | 15 |  |  | 46195 | ACTUAL | 100%
DOZER READINESS | PLAN | 23 | 16 | PA ALL DOZER | PLAN | 23 | 90% | MTBF | PLAN | 23 | 70 | MTTR | PLAN | 23 | 80 | PA ALL DOZER | ACHIVE | 14 | 100% | DAILY ACHIVEMENT | ACTUAL | 14 | 84% | [48 empty] | 2 | MAN | Quick Action | 16 | 100% | FACTOR | DOZER READINESS | PLAN | 23 | 16 |  |  | 46196 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 23 | 13 | PA ALL DOZER | ACTUAL | 23 | 98% | MTBF | ACTUAL | 23 | 60 | MTTR | ACTUAL | 23 | 60 | PA ALL DOZER | ACHIVE | 15 | 108.9% | DAILY ACHIVEMENT | ACTUAL | 15 | 87% | [48 empty] | 2 | MAN | Quick Action | 17 | 100% | FACTOR | DOZER READINESS | ACTUAL | 23 | 13 |  |  | 46196 | ACTUAL | 100%
DOZER READINESS | PLAN | 24 | 16 | PA ALL DOZER | PLAN | 24 | 90% | MTBF | PLAN | 24 | 70 | MTTR | PLAN | 24 | 80 | PA ALL DOZER | ACHIVE | 16 | 103.3% | DAILY ACHIVEMENT | ACTUAL | 16 | 90% | [48 empty] | 2 | MAN | Quick Action | 18 | 100% | FACTOR | DOZER READINESS | PLAN | 24 | 16 |  |  | 46197 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 24 | 14 | PA ALL DOZER | ACTUAL | 24 | 93% | MTBF | ACTUAL | 24 | 50 | MTTR | ACTUAL | 24 | 50 | PA ALL DOZER | ACHIVE | 17 | 96.67% | DAILY ACHIVEMENT | ACTUAL | 17 | 93% | [48 empty] | 2 | MAN | Quick Action | 19 | 100% | FACTOR | DOZER READINESS | ACTUAL | 24 | 14 |  |  | 46197 | ACTUAL | 100%
DOZER READINESS | PLAN | 25 | 16 | PA ALL DOZER | PLAN | 25 | 90% | MTBF | PLAN | 25 | 70 | MTTR | PLAN | 25 | 80 | PA ALL DOZER | ACHIVE | 18 | 88.89% | DAILY ACHIVEMENT | ACTUAL | 18 | 96% | [48 empty] | 2 | MAN | Quick Action | 20 | 100% | FACTOR | DOZER READINESS | PLAN | 25 | 16 |  |  | 46198 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 25 | 11 | PA ALL DOZER | ACTUAL | 25 | 87% | MTBF | ACTUAL | 25 | 75 | MTTR | ACTUAL | 25 | 75 | PA ALL DOZER | ACHIVE | 19 | 92.22% | DAILY ACHIVEMENT | ACTUAL | 19 | 99% | [48 empty] | 2 | MAN | Quick Action | 21 | 100% | FACTOR | DOZER READINESS | ACTUAL | 25 | 11 |  |  | 46198 | ACTUAL | 100%
DOZER READINESS | PLAN | 26 | 16 | PA ALL DOZER | PLAN | 26 | 90% | MTBF | PLAN | 26 | 70 | MTTR | PLAN | 26 | 80 | PA ALL DOZER | ACHIVE | 20 | 80% | DAILY ACHIVEMENT | ACTUAL | 20 | 100% | [48 empty] | 2 | MAN | Quick Action | 22 | 100% | FACTOR | DOZER READINESS | PLAN | 26 | 16 |  |  | 46199 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 26 | 16 | PA ALL DOZER | ACTUAL | 26 | 80% | MTBF | ACTUAL | 26 | 83 | MTTR | ACTUAL | 26 | 83 | PA ALL DOZER | ACHIVE | 21 | 111.1% | DAILY ACHIVEMENT | ACTUAL | 21 | 100% | [48 empty] | 2 | MAN | Quick Action | 23 | 100% | FACTOR | DOZER READINESS | ACTUAL | 26 | 16 |  |  | 46199 | ACTUAL | 100%
DOZER READINESS | PLAN | 27 | 16 | PA ALL DOZER | PLAN | 27 | 90% | MTBF | PLAN | 27 | 70 | MTTR | PLAN | 27 | 80 | PA ALL DOZER | ACHIVE | 22 | 100% | DAILY ACHIVEMENT | ACTUAL | 22 | 100% | [48 empty] | 2 | MAN | Quick Action | 24 | 100% | FACTOR | DOZER READINESS | PLAN | 27 | 16 |  |  | 46200 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 27 | 14 | PA ALL DOZER | ACTUAL | 27 | 83% | MTBF | ACTUAL | 27 | 65 | MTTR | ACTUAL | 27 | 65 | PA ALL DOZER | ACHIVE | 23 | 108.9% | DAILY ACHIVEMENT | ACTUAL | 23 | 100% | [48 empty] | 2 | MAN | Quick Action | 25 | 100% | FACTOR | DOZER READINESS | ACTUAL | 27 | 14 |  |  | 46200 | ACTUAL | 100%
DOZER READINESS | PLAN | 28 | 16 | PA ALL DOZER | PLAN | 28 | 90% | MTBF | PLAN | 28 | 70 | MTTR | PLAN | 28 | 80 | PA ALL DOZER | ACHIVE | 24 | 103.3% | DAILY ACHIVEMENT | ACTUAL | 24 | 100% | [48 empty] | 2 | MAN | Quick Action | 26 | 100% | FACTOR | DOZER READINESS | PLAN | 28 | 16 |  |  | 46201 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 28 | 16 | PA ALL DOZER | ACTUAL | 28 | 72% | MTBF | ACTUAL | 28 | 73 | MTTR | ACTUAL | 28 | 73 | PA ALL DOZER | ACHIVE | 25 | 96.67% | DAILY ACHIVEMENT | ACTUAL | 25 | 100% | [48 empty] | 2 | MAN | Quick Action | 27 | 100% | FACTOR | DOZER READINESS | ACTUAL | 28 | 16 |  |  | 46201 | ACTUAL | 100%
DOZER READINESS | PLAN | 29 | 16 | PA ALL DOZER | PLAN | 29 | 90% | MTBF | PLAN | 29 | 70 | MTTR | PLAN | 29 | 80 | PA ALL DOZER | ACHIVE | 26 | 88.89% | DAILY ACHIVEMENT | ACTUAL | 26 | 100% | [48 empty] | 2 | MAN | Quick Action | 28 | 100% | FACTOR | DOZER READINESS | PLAN | 29 | 16 |  |  | 46202 | PLAN | 51%
DOZER READINESS | ACTUAL | 29 | 12 | PA ALL DOZER | ACTUAL | 29 | 100% | MTBF | ACTUAL | 29 | 75 | MTTR | ACTUAL | 29 | 75 | PA ALL DOZER | ACHIVE | 27 | 92.22% | DAILY ACHIVEMENT | ACTUAL | 27 | 100% | [48 empty] | 2 | MAN | Quick Action | 29 | 100% | FACTOR | DOZER READINESS | ACTUAL | 29 | 12 |  |  | 46202 | ACTUAL | 100%
DOZER READINESS | PLAN | 30 | 16 | PA ALL DOZER | PLAN | 30 | 90% | MTBF | PLAN | 30 | 70 | MTTR | PLAN | 30 | 80 | PA ALL DOZER | ACHIVE | 28 | 80% | DAILY ACHIVEMENT | ACTUAL | 28 | 100% | [48 empty] | 2 | MAN | Quick Action | 30 | 100% | FACTOR | DOZER READINESS | PLAN | 30 | 16 |  |  | 46203 | PLAN | 51.83%
DOZER READINESS | ACTUAL | 30 | 11 | PA ALL DOZER | ACTUAL | 30 | 90% | MTBF | ACTUAL | 30 | 83 | MTTR | ACTUAL | 30 | 83 | PA ALL DOZER | ACHIVE | 29 | 111.1% | DAILY ACHIVEMENT | ACTUAL | 29 | 100% | [48 empty] | 2 | MAN | Quick Action | 31 | 100% | FACTOR | DOZER READINESS | ACTUAL | 30 | 11 |  |  | 46203 | ACTUAL | 100%
DOZER READINESS | PLAN | 31 | #N/A | PA ALL DOZER | PLAN | 31 | #N/A | MTBF | PLAN | 31 | #N/A | MTTR | PLAN | 31 | #N/A | PA ALL DOZER | ACHIVE | 30 | 100% | DAILY ACHIVEMENT | ACTUAL | 30 | 100% | [48 empty] | 3 | MAN | Quick Action | 5 | 0% | FACTOR | DOZER READINESS | PLAN | 31 | #N/A |  |  | 46204 | PLAN | 52.67%
DOZER READINESS | ACTUAL | 31 | #N/A | PA ALL DOZER | ACTUAL | 31 | #N/A | MTBF | ACTUAL | 31 | #N/A | MTTR | ACTUAL | 31 | #N/A | PA ALL DOZER | ACHIVE | 31 | #N/A | DAILY ACHIVEMENT | ACTUAL | 31 | 0% | [48 empty] | 3 | MAN | Quick Action | 6 | 0% | FACTOR | DOZER READINESS | ACTUAL | 31 | #N/A |  |  | 46204 | ACTUAL | N/A
[16 empty] | MTBF | ACHIVE | 1 | 114.3% | [52 empty] | 3 | MAN | Quick Action | 7 | 100% | FACTOR | PA ALL DOZER | PLAN | 1 | 90%
[16 empty] | MTBF | ACHIVE | 2 | 85.71% | [52 empty] | 3 | MAN | Quick Action | 8 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 1 | 87%
[16 empty] | MTBF | ACHIVE | 3 | 71.43% | [52 empty] | 3 | MAN | Quick Action | 9 | 100% | FACTOR | PA ALL DOZER | PLAN | 2 | 90%
[16 empty] | MTBF | ACHIVE | 4 | 107.1% | [52 empty] | 3 | MAN | Quick Action | 10 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 2 | 80%
[16 empty] | MTBF | ACHIVE | 5 | 118.6% | [52 empty] | 3 | MAN | Quick Action | 11 | 100% | FACTOR | PA ALL DOZER | PLAN | 3 | 90%
[16 empty] | MTBF | ACHIVE | 6 | 92.86% | [52 empty] | 3 | MAN | Quick Action | 12 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 3 | 83%
[16 empty] | MTBF | ACHIVE | 7 | 104.3% | [52 empty] | 3 | MAN | Quick Action | 13 | 100% | FACTOR | PA ALL DOZER | PLAN | 4 | 90%
[16 empty] | MTBF | ACHIVE | 8 | 114.3% | [52 empty] | 3 | MAN | Quick Action | 14 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 4 | 72%
[16 empty] | MTBF | ACHIVE | 9 | 85.71% | [52 empty] | 3 | MAN | Quick Action | 15 | 100% | FACTOR | PA ALL DOZER | PLAN | 5 | 90%
[16 empty] | MTBF | ACHIVE | 10 | 71.43% | [52 empty] | 3 | MAN | Quick Action | 16 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 5 | 100%
[16 empty] | MTBF | ACHIVE | 11 | 107.1% | [52 empty] | 3 | MAN | Quick Action | 17 | 100% | FACTOR | PA ALL DOZER | PLAN | 6 | 90%
[16 empty] | MTBF | ACHIVE | 12 | 118.6% | [52 empty] | 3 | MAN | Quick Action | 18 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 6 | 90%
[16 empty] | MTBF | ACHIVE | 13 | 92.86% | [52 empty] | 3 | MAN | Quick Action | 19 | 100% | FACTOR | PA ALL DOZER | PLAN | 7 | 90%
[16 empty] | MTBF | ACHIVE | 14 | 104.3% | [52 empty] | 3 | MAN | Quick Action | 20 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 7 | 98%
[16 empty] | MTBF | ACHIVE | 15 | 114.3% | [52 empty] | 3 | MAN | Quick Action | 21 | 100% | FACTOR | PA ALL DOZER | PLAN | 8 | 90%
[16 empty] | MTBF | ACHIVE | 16 | 85.71% | [52 empty] | 3 | MAN | Quick Action | 22 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 8 | 93%
[16 empty] | MTBF | ACHIVE | 17 | 71.43% | [52 empty] | 3 | MAN | Quick Action | 23 | 100% | FACTOR | PA ALL DOZER | PLAN | 9 | 90%
[16 empty] | MTBF | ACHIVE | 18 | 107.1% | [52 empty] | 3 | MAN | Quick Action | 24 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 9 | 87%
[16 empty] | MTBF | ACHIVE | 19 | 118.6% | [52 empty] | 3 | MAN | Quick Action | 25 | 100% | FACTOR | PA ALL DOZER | PLAN | 10 | 90%
[16 empty] | MTBF | ACHIVE | 20 | 92.86% | [52 empty] | 3 | MAN | Quick Action | 26 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 10 | 80%
[16 empty] | MTBF | ACHIVE | 21 | 104.3% | [52 empty] | 3 | MAN | Quick Action | 27 | 100% | FACTOR | PA ALL DOZER | PLAN | 11 | 90%
[16 empty] | MTBF | ACHIVE | 22 | 114.3% | [52 empty] | 3 | MAN | Quick Action | 28 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 11 | 83%
[16 empty] | MTBF | ACHIVE | 23 | 85.71% | [52 empty] | 3 | MAN | Quick Action | 29 | 100% | FACTOR | PA ALL DOZER | PLAN | 12 | 90%
[16 empty] | MTBF | ACHIVE | 24 | 71.43% | [52 empty] | 3 | MAN | Quick Action | 30 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 12 | 72%
[16 empty] | MTBF | ACHIVE | 25 | 107.1% | [52 empty] | 3 | MAN | Quick Action | 31 | 100% | FACTOR | PA ALL DOZER | PLAN | 13 | 90%
[16 empty] | MTBF | ACHIVE | 26 | 118.6% | [52 empty] | 4 | MAN | Quick Action | 1 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 13 | 100%
[16 empty] | MTBF | ACHIVE | 27 | 92.86% | [52 empty] | 4 | MAN | Quick Action | 2 | 100% | FACTOR | PA ALL DOZER | PLAN | 14 | 90%
[16 empty] | MTBF | ACHIVE | 28 | 104.3% | [52 empty] | 4 | MAN | Quick Action | 3 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 14 | 90%
[16 empty] | MTBF | ACHIVE | 29 | 107.1% | [52 empty] | 4 | MAN | Quick Action | 4 | 100% | FACTOR | PA ALL DOZER | PLAN | 15 | 90%
[16 empty] | MTBF | ACHIVE | 30 | 118.6% | [52 empty] | 4 | MAN | Quick Action | 5 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 15 | 98%
[16 empty] | MTBF | ACHIVE | 31 | #N/A | [52 empty] | 4 | MAN | Quick Action | 6 | 100% | FACTOR | PA ALL DOZER | PLAN | 16 | 90%
[16 empty] | MTTR | ACHIVE | 1 | 100% | [52 empty] | 4 | MAN | Quick Action | 7 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 16 | 93%
[16 empty] | MTTR | ACHIVE | 2 | 75% | [52 empty] | 4 | MAN | Quick Action | 8 | 100% | FACTOR | PA ALL DOZER | PLAN | 17 | 90%
[16 empty] | MTTR | ACHIVE | 3 | 62.5% | [52 empty] | 4 | MAN | Quick Action | 9 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 17 | 87%
[16 empty] | MTTR | ACHIVE | 4 | 93.75% | [52 empty] | 4 | MAN | Quick Action | 10 | 100% | FACTOR | PA ALL DOZER | PLAN | 18 | 90%
[16 empty] | MTTR | ACHIVE | 5 | 103.8% | [52 empty] | 4 | MAN | Quick Action | 11 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 18 | 80%
[16 empty] | MTTR | ACHIVE | 6 | 81.25% | [52 empty] | 4 | MAN | Quick Action | 12 | 100% | FACTOR | PA ALL DOZER | PLAN | 19 | 90%
[16 empty] | MTTR | ACHIVE | 7 | 91.25% | [52 empty] | 4 | MAN | Quick Action | 13 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 19 | 83%
[16 empty] | MTTR | ACHIVE | 8 | 100% | [52 empty] | 4 | MAN | Quick Action | 14 | 100% | FACTOR | PA ALL DOZER | PLAN | 20 | 90%
[16 empty] | MTTR | ACHIVE | 9 | 75% | [52 empty] | 4 | MAN | Quick Action | 15 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 20 | 72%
[16 empty] | MTTR | ACHIVE | 10 | 62.5% | [52 empty] | 4 | MAN | Quick Action | 16 | 100% | FACTOR | PA ALL DOZER | PLAN | 21 | 90%
[16 empty] | MTTR | ACHIVE | 11 | 93.75% | [52 empty] | 4 | MAN | Quick Action | 17 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 21 | 100%
[16 empty] | MTTR | ACHIVE | 12 | 103.8% | [52 empty] | 4 | MAN | Quick Action | 18 | 100% | FACTOR | PA ALL DOZER | PLAN | 22 | 90%
[16 empty] | MTTR | ACHIVE | 13 | 81.25% | [52 empty] | 4 | MAN | Quick Action | 19 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 22 | 90%
[16 empty] | MTTR | ACHIVE | 14 | 91.25% | [52 empty] | 4 | MAN | Quick Action | 20 | 100% | FACTOR | PA ALL DOZER | PLAN | 23 | 90%
[16 empty] | MTTR | ACHIVE | 15 | 100% | [52 empty] | 4 | MAN | Quick Action | 21 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 23 | 98%
[16 empty] | MTTR | ACHIVE | 16 | 75% | [52 empty] | 4 | MAN | Quick Action | 22 | 100% | FACTOR | PA ALL DOZER | PLAN | 24 | 90%
[16 empty] | MTTR | ACHIVE | 17 | 62.5% | [52 empty] | 4 | MAN | Quick Action | 23 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 24 | 93%
[16 empty] | MTTR | ACHIVE | 18 | 93.75% | [52 empty] | 4 | MAN | Quick Action | 24 | 100% | FACTOR | PA ALL DOZER | PLAN | 25 | 90%
[16 empty] | MTTR | ACHIVE | 19 | 103.8% | [52 empty] | 4 | MAN | Quick Action | 25 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 25 | 87%
[16 empty] | MTTR | ACHIVE | 20 | 81.25% | [52 empty] | 4 | MAN | Quick Action | 26 | 100% | FACTOR | PA ALL DOZER | PLAN | 26 | 90%
[16 empty] | MTTR | ACHIVE | 21 | 91.25% | [52 empty] | 4 | MAN | Quick Action | 27 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 26 | 80%
[16 empty] | MTTR | ACHIVE | 22 | 100% | [52 empty] | 4 | MAN | Quick Action | 28 | 100% | FACTOR | PA ALL DOZER | PLAN | 27 | 90%
[16 empty] | MTTR | ACHIVE | 23 | 75% | [52 empty] | 4 | MAN | Quick Action | 29 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 27 | 83%
[16 empty] | MTTR | ACHIVE | 24 | 62.5% | [52 empty] | 4 | MAN | Quick Action | 30 | 100% | FACTOR | PA ALL DOZER | PLAN | 28 | 90%
[16 empty] | MTTR | ACHIVE | 25 | 93.75% | [52 empty] | 4 | MAN | Quick Action | 31 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 28 | 72%
[16 empty] | MTTR | ACHIVE | 26 | 103.8% | [52 empty] | 5 | MAN | Long Term / Development | 3 | 100% | FACTOR | PA ALL DOZER | PLAN | 29 | 90%
[16 empty] | MTTR | ACHIVE | 27 | 81.25% | [52 empty] | 5 | MAN | Long Term / Development | 4 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 29 | 100%
[16 empty] | MTTR | ACHIVE | 28 | 91.25% | [52 empty] | 5 | MAN | Long Term / Development | 5 | 100% | FACTOR | PA ALL DOZER | PLAN | 30 | 90%
[16 empty] | MTTR | ACHIVE | 29 | 93.75% | [52 empty] | 5 | MAN | Long Term / Development | 6 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 30 | 90%
[16 empty] | MTTR | ACHIVE | 30 | 103.8% | [52 empty] | 5 | MAN | Long Term / Development | 7 | 100% | FACTOR | PA ALL DOZER | PLAN | 31 | #N/A
[16 empty] | MTTR | ACHIVE | 31 | #N/A | [52 empty] | 5 | MAN | Long Term / Development | 8 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 31 | #N/A
[72 empty] | 5 | MAN | Long Term / Development | 9 | 100% | FACTOR | MTBF | PLAN | 1 | 70
[72 empty] | 5 | MAN | Long Term / Development | 10 | 100% | FACTOR | MTBF | ACTUAL | 1 | 80
[72 empty] | 5 | MAN | Long Term / Development | 11 | 100% | FACTOR | MTBF | PLAN | 2 | 70
[72 empty] | 5 | MAN | Long Term / Development | 12 | 100% | FACTOR | MTBF | ACTUAL | 2 | 60
[72 empty] | 5 | MAN | Long Term / Development | 13 | 100% | FACTOR | MTBF | PLAN | 3 | 70
[72 empty] | 5 | MAN | Long Term / Development | 14 | 100% | FACTOR | MTBF | ACTUAL | 3 | 50
[72 empty] | 5 | MAN | Long Term / Development | 15 | 100% | FACTOR | MTBF | PLAN | 4 | 70
[72 empty] | 5 | MAN | Long Term / Development | 16 | 100% | FACTOR | MTBF | ACTUAL | 4 | 75
[72 empty] | 5 | MAN | Long Term / Development | 17 | 100% | FACTOR | MTBF | PLAN | 5 | 70
[72 empty] | 5 | MAN | Long Term / Development | 18 | 100% | FACTOR | MTBF | ACTUAL | 5 | 83
[72 empty] | 5 | MAN | Long Term / Development | 19 | 100% | FACTOR | MTBF | PLAN | 6 | 70
[72 empty] | 5 | MAN | Long Term / Development | 20 | 100% | FACTOR | MTBF | ACTUAL | 6 | 65
[72 empty] | 5 | MAN | Long Term / Development | 21 | 100% | FACTOR | MTBF | PLAN | 7 | 70
[72 empty] | 5 | MAN | Long Term / Development | 22 | 100% | FACTOR | MTBF | ACTUAL | 7 | 73
[72 empty] | 5 | MAN | Long Term / Development | 23 | 100% | FACTOR | MTBF | PLAN | 8 | 70
[72 empty] | 5 | MAN | Long Term / Development | 24 | 100% | FACTOR | MTBF | ACTUAL | 8 | 80
[72 empty] | 5 | MAN | Long Term / Development | 25 | 100% | FACTOR | MTBF | PLAN | 9 | 70
[72 empty] | 5 | MAN | Long Term / Development | 26 | 100% | FACTOR | MTBF | ACTUAL | 9 | 60
[72 empty] | 5 | MAN | Long Term / Development | 27 | 100% | FACTOR | MTBF | PLAN | 10 | 70
[72 empty] | 5 | MAN | Long Term / Development | 28 | 100% | FACTOR | MTBF | ACTUAL | 10 | 50
[72 empty] | 5 | MAN | Long Term / Development | 29 | 100% | FACTOR | MTBF | PLAN | 11 | 70
[72 empty] | 5 | MAN | Long Term / Development | 30 | 100% | FACTOR | MTBF | ACTUAL | 11 | 75
[72 empty] | 5 | MAN | Long Term / Development | 31 | 100% | FACTOR | MTBF | PLAN | 12 | 70
[72 empty] | 6 | MAN | Long Term / Development | 2 | 0% | FACTOR | MTBF | ACTUAL | 12 | 83
[72 empty] | 6 | MAN | Long Term / Development | 3 | 0% | FACTOR | MTBF | PLAN | 13 | 70
[72 empty] | 6 | MAN | Long Term / Development | 4 | 0% | FACTOR | MTBF | ACTUAL | 13 | 65
[72 empty] | 6 | MAN | Long Term / Development | 5 | 100% | FACTOR | MTBF | PLAN | 14 | 70
[72 empty] | 6 | MAN | Long Term / Development | 6 | 100% | FACTOR | MTBF | ACTUAL | 14 | 73
[72 empty] | 6 | MAN | Long Term / Development | 7 | 100% | FACTOR | MTBF | PLAN | 15 | 70
[72 empty] | 6 | MAN | Long Term / Development | 8 | 100% | FACTOR | MTBF | ACTUAL | 15 | 80
[72 empty] | 6 | MAN | Long Term / Development | 9 | 100% | FACTOR | MTBF | PLAN | 16 | 70
[72 empty] | 6 | MAN | Long Term / Development | 10 | 100% | FACTOR | MTBF | ACTUAL | 16 | 60
[72 empty] | 6 | MAN | Long Term / Development | 11 | 100% | FACTOR | MTBF | PLAN | 17 | 70
[72 empty] | 6 | MAN | Long Term / Development | 12 | 100% | FACTOR | MTBF | ACTUAL | 17 | 50
[72 empty] | 6 | MAN | Long Term / Development | 13 | 100% | FACTOR | MTBF | PLAN | 18 | 70
[72 empty] | 6 | MAN | Long Term / Development | 14 | 100% | FACTOR | MTBF | ACTUAL | 18 | 75
[72 empty] | 6 | MAN | Long Term / Development | 15 | 100% | FACTOR | MTBF | PLAN | 19 | 70
[72 empty] | 6 | MAN | Long Term / Development | 16 | 100% | FACTOR | MTBF | ACTUAL | 19 | 83
[72 empty] | 6 | MAN | Long Term / Development | 17 | 100% | FACTOR | MTBF | PLAN | 20 | 70
[72 empty] | 6 | MAN | Long Term / Development | 18 | 100% | FACTOR | MTBF | ACTUAL | 20 | 65
[72 empty] | 6 | MAN | Long Term / Development | 19 | 100% | FACTOR | MTBF | PLAN | 21 | 70
[72 empty] | 6 | MAN | Long Term / Development | 20 | 100% | FACTOR | MTBF | ACTUAL | 21 | 73
[72 empty] | 6 | MAN | Long Term / Development | 21 | 100% | FACTOR | MTBF | PLAN | 22 | 70
[72 empty] | 6 | MAN | Long Term / Development | 22 | 100% | FACTOR | MTBF | ACTUAL | 22 | 80
[72 empty] | 6 | MAN | Long Term / Development | 23 | 100% | FACTOR | MTBF | PLAN | 23 | 70
[72 empty] | 6 | MAN | Long Term / Development | 24 | 100% | FACTOR | MTBF | ACTUAL | 23 | 60
[72 empty] | 6 | MAN | Long Term / Development | 25 | 100% | FACTOR | MTBF | PLAN | 24 | 70
[72 empty] | 6 | MAN | Long Term / Development | 26 | 100% | FACTOR | MTBF | ACTUAL | 24 | 50
[72 empty] | 6 | MAN | Long Term / Development | 27 | 100% | FACTOR | MTBF | PLAN | 25 | 70
[72 empty] | 6 | MAN | Long Term / Development | 28 | 100% | FACTOR | MTBF | ACTUAL | 25 | 75
[72 empty] | 6 | MAN | Long Term / Development | 29 | 100% | FACTOR | MTBF | PLAN | 26 | 70
[72 empty] | 6 | MAN | Long Term / Development | 30 | 100% | FACTOR | MTBF | ACTUAL | 26 | 83
[72 empty] | 6 | MAN | Long Term / Development | 31 | 100% | FACTOR | MTBF | PLAN | 27 | 70
[72 empty] | 7 | MAN | Long Term / Development | 1 | 0% | FACTOR | MTBF | ACTUAL | 27 | 65
[72 empty] | 7 | MAN | Long Term / Development | 2 | 0% | FACTOR | MTBF | PLAN | 28 | 70
[72 empty] | 7 | MAN | Long Term / Development | 3 | 0% | FACTOR | MTBF | ACTUAL | 28 | 73
[72 empty] | 7 | MAN | Long Term / Development | 4 | 0% | FACTOR | MTBF | PLAN | 29 | 70
[72 empty] | 7 | MAN | Long Term / Development | 5 | 0% | FACTOR | MTBF | ACTUAL | 29 | 75
[72 empty] | 7 | MAN | Long Term / Development | 6 | 0% | FACTOR | MTBF | PLAN | 30 | 70
[72 empty] | 7 | MAN | Long Term / Development | 7 | 0% | FACTOR | MTBF | ACTUAL | 30 | 83
[72 empty] | 7 | MAN | Long Term / Development | 8 | 0% | FACTOR | MTBF | PLAN | 31 | #N/A
[72 empty] | 7 | MAN | Long Term / Development | 9 | 100% | FACTOR | MTBF | ACTUAL | 31 | #N/A
[72 empty] | 7 | MAN | Long Term / Development | 10 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 1 | 5%
[72 empty] | 7 | MAN | Long Term / Development | 11 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 2 | 8%
[72 empty] | 7 | MAN | Long Term / Development | 12 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 3 | 10%
[72 empty] | 7 | MAN | Long Term / Development | 13 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 4 | 12.67%
[72 empty] | 7 | MAN | Long Term / Development | 14 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 5 | 15.17%
[72 empty] | 7 | MAN | Long Term / Development | 15 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 6 | 17.67%
[72 empty] | 7 | MAN | Long Term / Development | 16 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 7 | 20.17%
[72 empty] | 7 | MAN | Long Term / Development | 17 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 8 | 22.67%
[72 empty] | 7 | MAN | Long Term / Development | 18 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 9 | 25.17%
[72 empty] | 7 | MAN | Long Term / Development | 19 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 10 | 27.67%
[72 empty] | 7 | MAN | Long Term / Development | 20 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 11 | 30.17%
[72 empty] | 7 | MAN | Long Term / Development | 21 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 12 | 32.67%
[72 empty] | 7 | MAN | Long Term / Development | 22 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 13 | 35.17%
[72 empty] | 7 | MAN | Long Term / Development | 23 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 14 | 37.67%
[72 empty] | 7 | MAN | Long Term / Development | 24 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 15 | 40.17%
[72 empty] | 7 | MAN | Long Term / Development | 25 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 16 | 42.67%
[72 empty] | 7 | MAN | Long Term / Development | 26 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 17 | 45.17%
[72 empty] | 7 | MAN | Long Term / Development | 27 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 18 | 47.67%
[72 empty] | 7 | MAN | Long Term / Development | 28 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 19 | 50.17%
[72 empty] | 7 | MAN | Long Term / Development | 29 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 20 | 50.17%
[72 empty] | 7 | MAN | Long Term / Development | 30 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 21 | 50.17%
[72 empty] | 7 | MAN | Long Term / Development | 31 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 22 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 3 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 23 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 4 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 24 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 5 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 25 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 6 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 26 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 7 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 27 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 8 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 28 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 9 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 29 | 51%
[72 empty] | 8 | MAN | Long Term / Development | 10 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 30 | 51.83%
[72 empty] | 8 | MAN | Long Term / Development | 11 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 31 | 52.67%
[72 empty] | 8 | MAN | Long Term / Development | 12 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 1 | 53.5%
[72 empty] | 8 | MAN | Long Term / Development | 13 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 2 | 54.33%
[72 empty] | 8 | MAN | Long Term / Development | 14 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 3 | 55.17%
[72 empty] | 8 | MAN | Long Term / Development | 15 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 4 | 56%
[72 empty] | 8 | MAN | Long Term / Development | 16 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 5 | 56.83%
[72 empty] | 8 | MAN | Long Term / Development | 17 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 6 | 60%
[72 empty] | 8 | MAN | Long Term / Development | 18 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 7 | 63%
[72 empty] | 8 | MAN | Long Term / Development | 19 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 8 | 66%
[72 empty] | 8 | MAN | Long Term / Development | 20 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 9 | 69%
[72 empty] | 8 | MAN | Long Term / Development | 21 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 10 | 72%
[72 empty] | 8 | MAN | Long Term / Development | 22 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 11 | 75%
[72 empty] | 8 | MAN | Long Term / Development | 23 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 12 | 78%
[72 empty] | 8 | MAN | Long Term / Development | 24 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 13 | 81%
[72 empty] | 8 | MAN | Long Term / Development | 25 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 14 | 84%
[72 empty] | 8 | MAN | Long Term / Development | 26 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 15 | 87%
[72 empty] | 8 | MAN | Long Term / Development | 27 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 16 | 90%
[72 empty] | 8 | MAN | Long Term / Development | 28 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 17 | 93%
[72 empty] | 8 | MAN | Long Term / Development | 29 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 18 | 96%
[72 empty] | 8 | MAN | Long Term / Development | 30 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 19 | 99%
[72 empty] | 8 | MAN | Long Term / Development | 31 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 20 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 1 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 21 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 2 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 22 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 3 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 23 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 4 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 24 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 5 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 25 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 6 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 26 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 7 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 27 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 8 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 28 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 9 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 29 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 10 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 30 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 11 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 31 | 0%
[72 empty] | 9 | MAN | Long Term / Development | 12 | 100% | FACTOR | MTTR | PLAN | 1 | 80
[72 empty] | 9 | MAN | Long Term / Development | 13 | 100% | FACTOR | MTTR | ACTUAL | 1 | 80
[72 empty] | 9 | MAN | Long Term / Development | 14 | 100% | FACTOR | MTTR | PLAN | 2 | 80
[72 empty] | 9 | MAN | Long Term / Development | 15 | 100% | FACTOR | MTTR | ACTUAL | 2 | 60
[72 empty] | 9 | MAN | Long Term / Development | 16 | 100% | FACTOR | MTTR | PLAN | 3 | 80
[72 empty] | 9 | MAN | Long Term / Development | 17 | 100% | FACTOR | MTTR | ACTUAL | 3 | 50
[72 empty] | 9 | MAN | Long Term / Development | 18 | 100% | FACTOR | MTTR | PLAN | 4 | 80
[72 empty] | 9 | MAN | Long Term / Development | 19 | 100% | FACTOR | MTTR | ACTUAL | 4 | 75
[72 empty] | 9 | MAN | Long Term / Development | 20 | 100% | FACTOR | MTTR | PLAN | 5 | 80
[72 empty] | 9 | MAN | Long Term / Development | 21 | 100% | FACTOR | MTTR | ACTUAL | 5 | 83
[72 empty] | 9 | MAN | Long Term / Development | 22 | 100% | FACTOR | MTTR | PLAN | 6 | 80
[72 empty] | 9 | MAN | Long Term / Development | 23 | 100% | FACTOR | MTTR | ACTUAL | 6 | 65
[72 empty] | 9 | MAN | Long Term / Development | 24 | 100% | FACTOR | MTTR | PLAN | 7 | 80
[72 empty] | 9 | MAN | Long Term / Development | 25 | 100% | FACTOR | MTTR | ACTUAL | 7 | 73
[72 empty] | 9 | MAN | Long Term / Development | 26 | 100% | FACTOR | MTTR | PLAN | 8 | 80
[72 empty] | 9 | MAN | Long Term / Development | 27 | 100% | FACTOR | MTTR | ACTUAL | 8 | 80
[72 empty] | 9 | MAN | Long Term / Development | 28 | 100% | FACTOR | MTTR | PLAN | 9 | 80
[72 empty] | 9 | MAN | Long Term / Development | 29 | 100% | FACTOR | MTTR | ACTUAL | 9 | 60
[72 empty] | 9 | MAN | Long Term / Development | 30 | 100% | FACTOR | MTTR | PLAN | 10 | 80
[72 empty] | 9 | MAN | Long Term / Development | 31 | 100% | FACTOR | MTTR | ACTUAL | 10 | 50
[72 empty] | 10 | MATERIAL | Quick Action | 6 | 0% | FACTOR | MTTR | PLAN | 11 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 7 | 100% | FACTOR | MTTR | ACTUAL | 11 | 75
[72 empty] | 10 | MATERIAL | Quick Action | 8 | 100% | FACTOR | MTTR | PLAN | 12 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 9 | 100% | FACTOR | MTTR | ACTUAL | 12 | 83
[72 empty] | 10 | MATERIAL | Quick Action | 10 | 100% | FACTOR | MTTR | PLAN | 13 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 11 | 100% | FACTOR | MTTR | ACTUAL | 13 | 65
[72 empty] | 10 | MATERIAL | Quick Action | 12 | 100% | FACTOR | MTTR | PLAN | 14 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 13 | 100% | FACTOR | MTTR | ACTUAL | 14 | 73
[72 empty] | 10 | MATERIAL | Quick Action | 14 | 100% | FACTOR | MTTR | PLAN | 15 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 15 | 100% | FACTOR | MTTR | ACTUAL | 15 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 16 | 100% | FACTOR | MTTR | PLAN | 16 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 17 | 100% | FACTOR | MTTR | ACTUAL | 16 | 60
[72 empty] | 10 | MATERIAL | Quick Action | 18 | 100% | FACTOR | MTTR | PLAN | 17 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 19 | 100% | FACTOR | MTTR | ACTUAL | 17 | 50
[72 empty] | 10 | MATERIAL | Quick Action | 20 | 100% | FACTOR | MTTR | PLAN | 18 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 21 | 100% | FACTOR | MTTR | ACTUAL | 18 | 75
[72 empty] | 10 | MATERIAL | Quick Action | 22 | 100% | FACTOR | MTTR | PLAN | 19 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 23 | 100% | FACTOR | MTTR | ACTUAL | 19 | 83
[72 empty] | 10 | MATERIAL | Quick Action | 24 | 100% | FACTOR | MTTR | PLAN | 20 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 25 | 100% | FACTOR | MTTR | ACTUAL | 20 | 65
[72 empty] | 10 | MATERIAL | Quick Action | 26 | 100% | FACTOR | MTTR | PLAN | 21 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 27 | 100% | FACTOR | MTTR | ACTUAL | 21 | 73
[72 empty] | 10 | MATERIAL | Quick Action | 28 | 100% | FACTOR | MTTR | PLAN | 22 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 29 | 100% | FACTOR | MTTR | ACTUAL | 22 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 30 | 100% | FACTOR | MTTR | PLAN | 23 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 31 | 100% | FACTOR | MTTR | ACTUAL | 23 | 60
[72 empty] | 11 | MATERIAL | Quick Action | 6 | 0% | FACTOR | MTTR | PLAN | 24 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 7 | 100% | FACTOR | MTTR | ACTUAL | 24 | 50
[72 empty] | 11 | MATERIAL | Quick Action | 8 | 100% | FACTOR | MTTR | PLAN | 25 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 9 | 100% | FACTOR | MTTR | ACTUAL | 25 | 75
[72 empty] | 11 | MATERIAL | Quick Action | 10 | 100% | FACTOR | MTTR | PLAN | 26 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 11 | 100% | FACTOR | MTTR | ACTUAL | 26 | 83
[72 empty] | 11 | MATERIAL | Quick Action | 12 | 100% | FACTOR | MTTR | PLAN | 27 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 13 | 100% | FACTOR | MTTR | ACTUAL | 27 | 65
[72 empty] | 11 | MATERIAL | Quick Action | 14 | 100% | FACTOR | MTTR | PLAN | 28 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 15 | 100% | FACTOR | MTTR | ACTUAL | 28 | 73
[72 empty] | 11 | MATERIAL | Quick Action | 16 | 100% | FACTOR | MTTR | PLAN | 29 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 17 | 100% | FACTOR | MTTR | ACTUAL | 29 | 75
[72 empty] | 11 | MATERIAL | Quick Action | 18 | 100% | FACTOR | MTTR | PLAN | 30 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 19 | 100% | FACTOR | MTTR | ACTUAL | 30 | 83
[72 empty] | 11 | MATERIAL | Quick Action | 20 | 100% | FACTOR | MTTR | PLAN | 31 | #N/A
[72 empty] | 11 | MATERIAL | Quick Action | 21 | 100% | FACTOR | MTTR | ACTUAL | 31 | #N/A
[72 empty] | 11 | MATERIAL | Quick Action | 22 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 23 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 24 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 25 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 26 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 27 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 28 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 29 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 30 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 31 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 6 | 0%
[72 empty] | 12 | MATERIAL | Quick Action | 7 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 8 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 9 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 10 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 11 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 12 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 13 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 14 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 15 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 16 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 17 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 18 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 19 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 20 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 21 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 22 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 23 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 24 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 25 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 26 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 27 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 28 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 29 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 30 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 31 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 6 | 0%
[72 empty] | 13 | MATERIAL | Quick Action | 7 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 8 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 9 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 10 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 11 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 12 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 13 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 14 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 15 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 16 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 17 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 18 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 19 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 20 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 21 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 22 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 23 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 24 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 25 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 26 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 27 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 28 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 29 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 30 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 31 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 6 | 0%
[72 empty] | 14 | MATERIAL | Quick Action | 7 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 8 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 9 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 10 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 11 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 12 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 13 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 14 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 15 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 16 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 17 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 18 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 19 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 20 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 21 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 22 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 23 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 24 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 25 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 26 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 27 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 28 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 29 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 30 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 31 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 6 | 0%
[72 empty] | 15 | MATERIAL | Long Term / Development | 7 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 8 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 9 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 10 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 11 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 12 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 13 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 14 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 15 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 16 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 17 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 18 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 19 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 20 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 21 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 22 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 23 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 24 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 25 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 26 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 27 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 28 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 29 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 30 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 31 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 4 | 0%
[72 empty] | 16 | MACHINE | Quick Action | 5 | 0%
[72 empty] | 16 | MACHINE | Quick Action | 6 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 7 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 8 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 9 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 10 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 11 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 12 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 13 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 14 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 15 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 16 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 17 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 18 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 19 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 20 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 21 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 22 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 23 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 24 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 25 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 26 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 27 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 28 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 29 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 30 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 31 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 4 | 0%
[72 empty] | 17 | MACHINE | Long Term / Development | 5 | 0%
[72 empty] | 17 | MACHINE | Long Term / Development | 6 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 7 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 8 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 9 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 10 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 11 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 12 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 13 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 14 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 15 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 16 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 17 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 18 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 19 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 20 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 21 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 22 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 23 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 24 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 25 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 26 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 27 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 28 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 29 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 30 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 31 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 4 | 0%
[72 empty] | 18 | MACHINE | Quick Action | 5 | 0%
[72 empty] | 18 | MACHINE | Quick Action | 6 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 7 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 8 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 9 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 10 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 11 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 12 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 13 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 14 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 15 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 16 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 17 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 18 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 19 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 20 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 21 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 22 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 23 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 24 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 25 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 26 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 27 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 28 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 29 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 30 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 31 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 4 | 0%
[72 empty] | 19 | MACHINE | Quick Action | 5 | 0%
[72 empty] | 19 | MACHINE | Quick Action | 6 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 7 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 8 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 9 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 10 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 11 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 12 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 13 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 14 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 15 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 16 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 17 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 18 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 19 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 20 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 21 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 22 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 23 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 24 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 25 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 26 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 27 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 28 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 29 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 30 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 31 | 100%
[72 empty] | 20 | METHOD | Quick Action | 1 | 0%
[72 empty] | 20 | METHOD | Quick Action | 2 | 0%
[72 empty] | 20 | METHOD | Quick Action | 3 | 100%
[72 empty] | 20 | METHOD | Quick Action | 4 | 100%
[72 empty] | 20 | METHOD | Quick Action | 5 | 100%
[72 empty] | 20 | METHOD | Quick Action | 6 | 100%
[72 empty] | 20 | METHOD | Quick Action | 7 | 100%
[72 empty] | 20 | METHOD | Quick Action | 8 | 100%
[72 empty] | 20 | METHOD | Quick Action | 9 | 100%
[72 empty] | 20 | METHOD | Quick Action | 10 | 100%
[72 empty] | 20 | METHOD | Quick Action | 11 | 100%
[72 empty] | 20 | METHOD | Quick Action | 12 | 100%
[72 empty] | 20 | METHOD | Quick Action | 13 | 100%
[72 empty] | 20 | METHOD | Quick Action | 14 | 100%
[72 empty] | 20 | METHOD | Quick Action | 15 | 100%
[72 empty] | 20 | METHOD | Quick Action | 16 | 100%
[72 empty] | 20 | METHOD | Quick Action | 17 | 100%
[72 empty] | 20 | METHOD | Quick Action | 18 | 100%
[72 empty] | 20 | METHOD | Quick Action | 19 | 100%
[72 empty] | 20 | METHOD | Quick Action | 20 | 100%
[72 empty] | 20 | METHOD | Quick Action | 21 | 100%
[72 empty] | 20 | METHOD | Quick Action | 22 | 100%
[72 empty] | 20 | METHOD | Quick Action | 23 | 100%
[72 empty] | 20 | METHOD | Quick Action | 24 | 100%
[72 empty] | 20 | METHOD | Quick Action | 25 | 100%
[72 empty] | 20 | METHOD | Quick Action | 26 | 100%
[72 empty] | 20 | METHOD | Quick Action | 27 | 100%
[72 empty] | 20 | METHOD | Quick Action | 28 | 100%
[72 empty] | 20 | METHOD | Quick Action | 29 | 100%
[72 empty] | 20 | METHOD | Quick Action | 30 | 100%
[72 empty] | 20 | METHOD | Quick Action | 31 | 100%
[72 empty] | 21 | METHOD | Quick Action | 1 | 0%
[72 empty] | 21 | METHOD | Quick Action | 2 | 0%
[72 empty] | 21 | METHOD | Quick Action | 3 | 100%
[72 empty] | 21 | METHOD | Quick Action | 4 | 100%
[72 empty] | 21 | METHOD | Quick Action | 5 | 100%
[72 empty] | 21 | METHOD | Quick Action | 6 | 100%
[72 empty] | 21 | METHOD | Quick Action | 7 | 100%
[72 empty] | 21 | METHOD | Quick Action | 8 | 100%
[72 empty] | 21 | METHOD | Quick Action | 9 | 100%
[72 empty] | 21 | METHOD | Quick Action | 10 | 100%
[72 empty] | 21 | METHOD | Quick Action | 11 | 100%
[72 empty] | 21 | METHOD | Quick Action | 12 | 100%
[72 empty] | 21 | METHOD | Quick Action | 13 | 100%
[72 empty] | 21 | METHOD | Quick Action | 14 | 100%
[72 empty] | 21 | METHOD | Quick Action | 15 | 100%
[72 empty] | 21 | METHOD | Quick Action | 16 | 100%
[72 empty] | 21 | METHOD | Quick Action | 17 | 100%
[72 empty] | 21 | METHOD | Quick Action | 18 | 100%
[72 empty] | 21 | METHOD | Quick Action | 19 | 100%
[72 empty] | 21 | METHOD | Quick Action | 20 | 100%
[72 empty] | 21 | METHOD | Quick Action | 21 | 100%
[72 empty] | 21 | METHOD | Quick Action | 22 | 100%
[72 empty] | 21 | METHOD | Quick Action | 23 | 100%
[72 empty] | 21 | METHOD | Quick Action | 24 | 100%
[72 empty] | 21 | METHOD | Quick Action | 25 | 100%
[72 empty] | 21 | METHOD | Quick Action | 26 | 100%
[72 empty] | 21 | METHOD | Quick Action | 27 | 100%
[72 empty] | 21 | METHOD | Quick Action | 28 | 100%
[72 empty] | 21 | METHOD | Quick Action | 29 | 100%
[72 empty] | 21 | METHOD | Quick Action | 30 | 100%
[72 empty] | 21 | METHOD | Quick Action | 31 | 100%
[72 empty] | 22 | METHOD | Quick Action | 1 | 0%
[72 empty] | 22 | METHOD | Quick Action | 2 | 0%
[72 empty] | 22 | METHOD | Quick Action | 3 | 100%
[72 empty] | 22 | METHOD | Quick Action | 4 | 100%
[72 empty] | 22 | METHOD | Quick Action | 5 | 100%
[72 empty] | 22 | METHOD | Quick Action | 6 | 100%
[72 empty] | 22 | METHOD | Quick Action | 7 | 100%
[72 empty] | 22 | METHOD | Quick Action | 8 | 100%
[72 empty] | 22 | METHOD | Quick Action | 9 | 100%
[72 empty] | 22 | METHOD | Quick Action | 10 | 100%
[72 empty] | 22 | METHOD | Quick Action | 11 | 100%
[72 empty] | 22 | METHOD | Quick Action | 12 | 100%
[72 empty] | 22 | METHOD | Quick Action | 13 | 100%
[72 empty] | 22 | METHOD | Quick Action | 14 | 100%
[72 empty] | 22 | METHOD | Quick Action | 15 | 100%
[72 empty] | 22 | METHOD | Quick Action | 16 | 100%
[72 empty] | 22 | METHOD | Quick Action | 17 | 100%
[72 empty] | 22 | METHOD | Quick Action | 18 | 100%
[72 empty] | 22 | METHOD | Quick Action | 19 | 100%
[72 empty] | 22 | METHOD | Quick Action | 20 | 100%
[72 empty] | 22 | METHOD | Quick Action | 21 | 100%
[72 empty] | 22 | METHOD | Quick Action | 22 | 100%
[72 empty] | 22 | METHOD | Quick Action | 23 | 100%
[72 empty] | 22 | METHOD | Quick Action | 24 | 100%
[72 empty] | 22 | METHOD | Quick Action | 25 | 100%
[72 empty] | 22 | METHOD | Quick Action | 26 | 100%
[72 empty] | 22 | METHOD | Quick Action | 27 | 100%
[72 empty] | 22 | METHOD | Quick Action | 28 | 100%
[72 empty] | 22 | METHOD | Quick Action | 29 | 100%
[72 empty] | 22 | METHOD | Quick Action | 30 | 100%
[72 empty] | 22 | METHOD | Quick Action | 31 | 100%
[72 empty] | 23 | METHOD | Quick Action | 1 | 0%
[72 empty] | 23 | METHOD | Quick Action | 2 | 0%
[72 empty] | 23 | METHOD | Quick Action | 3 | 100%
[72 empty] | 23 | METHOD | Quick Action | 4 | 100%
[72 empty] | 23 | METHOD | Quick Action | 5 | 100%
[72 empty] | 23 | METHOD | Quick Action | 6 | 100%
[72 empty] | 23 | METHOD | Quick Action | 7 | 100%
[72 empty] | 23 | METHOD | Quick Action | 8 | 100%
[72 empty] | 23 | METHOD | Quick Action | 9 | 100%
[72 empty] | 23 | METHOD | Quick Action | 10 | 100%
[72 empty] | 23 | METHOD | Quick Action | 11 | 100%
[72 empty] | 23 | METHOD | Quick Action | 12 | 100%
[72 empty] | 23 | METHOD | Quick Action | 13 | 100%
[72 empty] | 23 | METHOD | Quick Action | 14 | 100%
[72 empty] | 23 | METHOD | Quick Action | 15 | 100%
[72 empty] | 23 | METHOD | Quick Action | 16 | 100%
[72 empty] | 23 | METHOD | Quick Action | 17 | 100%
[72 empty] | 23 | METHOD | Quick Action | 18 | 100%
[72 empty] | 23 | METHOD | Quick Action | 19 | 100%
[72 empty] | 23 | METHOD | Quick Action | 20 | 100%
[72 empty] | 23 | METHOD | Quick Action | 21 | 100%
[72 empty] | 23 | METHOD | Quick Action | 22 | 100%
[72 empty] | 23 | METHOD | Quick Action | 23 | 100%
[72 empty] | 23 | METHOD | Quick Action | 24 | 100%
[72 empty] | 23 | METHOD | Quick Action | 25 | 100%
[72 empty] | 23 | METHOD | Quick Action | 26 | 100%
[72 empty] | 23 | METHOD | Quick Action | 27 | 100%
[72 empty] | 23 | METHOD | Quick Action | 28 | 100%
[72 empty] | 23 | METHOD | Quick Action | 29 | 100%
[72 empty] | 23 | METHOD | Quick Action | 30 | 100%
[72 empty] | 23 | METHOD | Quick Action | 31 | 100%
[72 empty] | 24 | METHOD | Quick Action | 1 | 0%
[72 empty] | 24 | METHOD | Quick Action | 2 | 0%
[72 empty] | 24 | METHOD | Quick Action | 3 | 100%
[72 empty] | 24 | METHOD | Quick Action | 4 | 100%
[72 empty] | 24 | METHOD | Quick Action | 5 | 100%
[72 empty] | 24 | METHOD | Quick Action | 6 | 100%
[72 empty] | 24 | METHOD | Quick Action | 7 | 100%
[72 empty] | 24 | METHOD | Quick Action | 8 | 100%
[72 empty] | 24 | METHOD | Quick Action | 9 | 100%
[72 empty] | 24 | METHOD | Quick Action | 10 | 100%
[72 empty] | 24 | METHOD | Quick Action | 11 | 100%
[72 empty] | 24 | METHOD | Quick Action | 12 | 100%
[72 empty] | 24 | METHOD | Quick Action | 13 | 100%
[72 empty] | 24 | METHOD | Quick Action | 14 | 100%
[72 empty] | 24 | METHOD | Quick Action | 15 | 100%
[72 empty] | 24 | METHOD | Quick Action | 16 | 100%
[72 empty] | 24 | METHOD | Quick Action | 17 | 100%
[72 empty] | 24 | METHOD | Quick Action | 18 | 100%
[72 empty] | 24 | METHOD | Quick Action | 19 | 100%
[72 empty] | 24 | METHOD | Quick Action | 20 | 100%
[72 empty] | 24 | METHOD | Quick Action | 21 | 100%
[72 empty] | 24 | METHOD | Quick Action | 22 | 100%
[72 empty] | 24 | METHOD | Quick Action | 23 | 100%
[72 empty] | 24 | METHOD | Quick Action | 24 | 100%
[72 empty] | 24 | METHOD | Quick Action | 25 | 100%
[72 empty] | 24 | METHOD | Quick Action | 26 | 100%
[72 empty] | 24 | METHOD | Quick Action | 27 | 100%
[72 empty] | 24 | METHOD | Quick Action | 28 | 100%
[72 empty] | 24 | METHOD | Quick Action | 29 | 100%
[72 empty] | 24 | METHOD | Quick Action | 30 | 100%
[72 empty] | 24 | METHOD | Quick Action | 31 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 1 | 0%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 2 | 0%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 3 | 0%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 4 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 5 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 6 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 7 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 8 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 9 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 10 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 11 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 12 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 13 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 14 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 15 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 16 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 17 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 18 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 19 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 20 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 21 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 22 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 23 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 24 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 25 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 26 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 27 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 28 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 29 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 30 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 31 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 1 | 0%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 2 | 0%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 3 | 0%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 4 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 5 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 6 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 7 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 8 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 9 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 10 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 11 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 12 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 13 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 14 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 15 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 16 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 17 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 18 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 19 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 20 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 21 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 22 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 23 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 24 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 25 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 26 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 27 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 28 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 29 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 30 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 31 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 1 | 0%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 2 | 0%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 3 | 0%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 4 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 5 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 6 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 7 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 8 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 9 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 10 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 11 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 12 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 13 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 14 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 15 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 16 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 17 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 18 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 19 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 20 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 21 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 22 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 23 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 24 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 25 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 26 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 27 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 28 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 29 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 30 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 31 | 100%

## PIVOT
| 5 FACTOR | (Multiple Items)
| CATEGORY | (Multiple Items) |  |  |  | JUMLAH TOTAL
[6 empty] | CATEGORY | JUMLAH | COMPLETION RATE
PT2 | Row Labels | Count of NO |  |  |  | CLOSE | 19 | 70.37% | 29.63%
| CLOSE | 19 |  |  |  | OPEN | 1 | 29.63%
| ON PROGRESS | 7 |  |  |  | ON PROGRESS | 7
| OPEN | 1 |  |  |  | TOTAL | 27
| Grand Total | 27
| 5 FACTOR | (Multiple Items)
| CATEGORY | (Multiple Items)
JUMLAH OVERDUE
PT3 |  | Column Labels |  |  |  | JUMLAH | STATUS
|  | < 14 HARI | OVERDUE |  |  | 0 | > 14 Hari
| Count of NO | 1 | 7 |  |  | 1 | < 14 Hari
[6 empty] | 0 | < 7 Hari
[6 empty] | 0 | < 3 Hari
[6 empty] | 7 | Overdue
PT7 | 5 FACTOR | (Multiple Items)
| CATEGORY | (Multiple Items)
| Count of STATUS | Column Labels | [11 empty] | OPEN | CLOSED
| Row Labels | OPEN | ON PROGRESS | CLOSE |  |  |  | DEPARTMENT | TOTAL | OPEN | PROGRESS | UNCLOSED | CLOSE | COMPLETION RATE
| AGUS Y |  |  | 3 |  |  |  | AGUS Y | 3 | 0 | 0 | 0 | 3 | 0% | 100%
| AMIN |  |  | 2 |  |  |  | AMIN | 2 | 0 | 0 | 0 | 2 | 0% | 100%
| ANDREAS |  | 4 | 2 |  |  |  | ANDREAS | 6 | 0 | 4 | 4 | 2 | 66.67% | 33.33%
| GS |  |  | 1 |  |  |  | GS | 1 | 0 | 0 | 0 | 1 | 0% | 100%
| GS HO |  |  | 2 |  |  |  | GS HO | 2 | 0 | 0 | 0 | 2 | 0% | 100%
| HC | 1 | 1 |  |  |  |  | HC | 2 | 1 | 1 | 2 | 0 | 100% | 0%
| HO |  |  | 2 |  |  |  | HO | 2 | 0 | 0 | 0 | 2 | 0% | 100%
| OLOWAN |  |  | 1 |  |  |  | OLOWAN | 1 | 0 | 0 | 0 | 1 | 0% | 100%
| PLANT-LOG |  |  | 1 |  |  |  | PLANT-LOG | 1 | 0 | 0 | 0 | 1 | 0% | 100%
| SLD |  | 2 | 3 |  |  |  | SLD | 5 | 0 | 2 | 2 | 3 | 40% | 60%
| YOHANES |  |  | 2 |  |  |  | YOHANES | 2 | 0 | 0 | 0 | 2 | 0% | 100%
[8 empty] | #N/A |  |  |  | #VALUE! |  |  | #N/A
[8 empty] | #N/A |  |  |  | #VALUE! |  |  | #N/A
[8 empty] | #N/A |  |  |  | #VALUE! |  |  | #N/A
[8 empty] | #N/A |  |  |  | #VALUE! |  |  | #N/A
PT5 | 5 FACTOR | (Multiple Items)
| CATEGORY | (Multiple Items)
| Row Labels | COMPLETION RATE
| AGUS Y | 100%
| AMIN | 100%
| ANDREAS | 33.33%
| GS | 100%
| GS HO | 100%
| HC | 0%
| HO | 100%
| OLOWAN | 100%
| PLANT-LOG | 100%
| SLD | 60%
| YOHANES | 100%
| Sum of VALUE | Column Labels |  |  | DOZER READINESS
| Row Labels | PLAN | ACTUAL
| 1 | 16 | 15
| 2 | 16 | 13
| 3 | 16 | 14
| 4 | 16 | 11
| 5 | 16 | 16
| 6 | 16 | 14
| 7 | 16 | 16
| 8 | 16 | 15
| 9 | 16 | 13
| 10 | 16 | 14
| 11 | 16 | 11
| 12 | 16 | 16
| 13 | 16 | 14
| 14 | 16 | 16
| 15 | 16 | 15
| 16 | 16 | 13
| 17 | 16 | 14
| 18 | 16 | 11
| 19 | 16 | 16
| 20 | 16 | 14
| 21 | 16 | 16
| 22 | 16 | 15
| 23 | 16 | 13
| 24 | 16 | 14
| 25 | 16 | 11
| 26 | 16 | 16
| 27 | 16 | 14
| 28 | 16 | 16
| 29 | 16 | 12
| 30 | 16 | 11
| 31 | 16 | 15
| Sum of VALUE | Column Labels |  |  | PA DOZER
| Row Labels | PLAN | ACTUAL
| 1 | 90% | 87%
| 2 | 90% | 80%
| 3 | 90% | 83%
| 4 | 90% | 72%
| 5 | 90% | 100%
| 6 | 90% | 90%
| 7 | 90% | 98%
| 8 | 90% | 93%
| 9 | 90% | 87%
| 10 | 90% | 80%
| 11 | 90% | 83%
| 12 | 90% | 72%
| 13 | 90% | 100%
| 14 | 90% | 90%
| 15 | 90% | 98%
| 16 | 90% | 93%
| 17 | 90% | 87%
| 18 | 90% | 80%
| 19 | 90% | 83%
| 20 | 90% | 72%
| 21 | 90% | 100%
| 22 | 90% | 90%
| 23 | 90% | 98%
| 24 | 90% | 93%
| 25 | 90% | 87%
| 26 | 90% | 80%
| 27 | 90% | 83%
| 28 | 90% | 72%
| 29 | 90% | 100%
| 30 | 90% | 90%
| 31 | 90% | 98%
| Sum of VALUE | Column Labels |  |  | MTBF
| Row Labels | PLAN | ACTUAL
| 1 | 70 | 80
| 2 | 70 | 60
| 3 | 70 | 50
| 4 | 70 | 75
| 5 | 70 | 83
| 6 | 70 | 65
| 7 | 70 | 73
| 8 | 70 | 80
| 9 | 70 | 60
| 10 | 70 | 50
| 11 | 70 | 75
| 12 | 70 | 83
| 13 | 70 | 65
| 14 | 70 | 73
| 15 | 70 | 80
| 16 | 70 | 60
| 17 | 70 | 50
| 18 | 70 | 75
| 19 | 70 | 83
| 20 | 70 | 65
| 21 | 70 | 73
| 22 | 70 | 80
| 23 | 70 | 60
| 24 | 70 | 50
| 25 | 70 | 75
| 26 | 70 | 83
| 27 | 70 | 65
| 28 | 70 | 73
| 29 | 70 | 75
| 30 | 70 | 83
| 31 | 70 | 65
| Grand Total | 2170 | 2167
| Sum of VALUE | Column Labels
| Row Labels | PLAN | ACTUAL |  | MTTR
| 1 | 80 | 80
| 2 | 80 | 60
| 3 | 80 | 50
| 4 | 80 | 75
| 5 | 80 | 83
| 6 | 80 | 65
| 7 | 80 | 73
| 8 | 80 | 80
| 9 | 80 | 60
| 10 | 80 | 50
| 11 | 80 | 75
| 12 | 80 | 83
| 13 | 80 | 65
| 14 | 80 | 73
| 15 | 80 | 80
| 16 | 80 | 60
| 17 | 80 | 50
| 18 | 80 | 75
| 19 | 80 | 83
| 20 | 80 | 65
| 21 | 80 | 73
| 22 | 80 | 80
| 23 | 80 | 60
| 24 | 80 | 50
| 25 | 80 | 75
| 26 | 80 | 83
| 27 | 80 | 65
| 28 | 80 | 73
| 29 | 80 | 75
| 30 | 80 | 83
| 31 | 80 | 65
| Grand Total | 2480 | 2167
| Sum of VALUE | Column Labels
| Row Labels | DOZER READINESS | MTBF | PA ALL DOZER | MTTR
| 1 | 93.75% | 114.3% | 96.67% | 100%
| 2 | 81.25% | 85.71% | 88.89% | 75%
| 3 | 87.5% | 71.43% | 92.22% | 62.5%
| 4 | 68.75% | 107.1% | 80% | 93.75%
| 5 | 100% | 118.6% | 111.1% | 103.8%
| 6 | 87.5% | 92.86% | 100% | 81.25%
| 7 | 100% | 104.3% | 108.9% | 91.25%
| 8 | 93.75% | 114.3% | 103.3% | 100%
| 9 | 81.25% | 85.71% | 96.67% | 75%
| 10 | 87.5% | 71.43% | 88.89% | 62.5%
| 11 | 68.75% | 107.1% | 92.22% | 93.75%
| 12 | 100% | 118.6% | 80% | 103.8%
| 13 | 87.5% | 92.86% | 111.1% | 81.25%
| 14 | 100% | 104.3% | 100% | 91.25%
| 15 | 93.75% | 114.3% | 108.9% | 100%
| 16 | 81.25% | 85.71% | 103.3% | 75%
| 17 | 87.5% | 71.43% | 96.67% | 62.5%
| 18 | 68.75% | 107.1% | 88.89% | 93.75%
| 19 | 100% | 118.6% | 92.22% | 103.8%
| 20 | 87.5% | 92.86% | 80% | 81.25%
| 21 | 100% | 104.3% | 111.1% | 91.25%
| 22 | 93.75% | 114.3% | 100% | 100%
| 23 | 81.25% | 85.71% | 108.9% | 75%
| 24 | 87.5% | 71.43% | 103.3% | 62.5%
| 25 | 68.75% | 107.1% | 96.67% | 93.75%
| 26 | 100% | 118.6% | 88.89% | 103.8%
| 27 | 87.5% | 92.86% | 92.22% | 81.25%
| 28 | 100% | 104.3% | 80% | 91.25%
| 29 | 75% | 107.1% | 111.1% | 93.75%
| 30 | 68.75% | 118.6% | 100% | 103.8%
| 31 | 93.75% | 92.86% | 108.9% | 81.25%
| Grand Total | 2712% | 3096% | 3021% | 2709%
| Sum of VALUE | Column Labels
|  | DOZER READINESS |  | DAILY ACHIVEMENT
| Row Labels | ACTUAL | PLAN | ACTUAL | PLAN
| 1 | 15 | 16 | 0.025926 | 0.022222
| 2 | 13 | 16 | 0.059259 | 0.044444
| 3 | 14 | 16 | 0.1 | 0.096296
| 4 | 11 | 16 | 0.18519 | 0.14815
| 5 | 16 | 16 | 0.26296 | 0.21111
| 6 | 14 | 16 | 0.35556 | 0.28889
| 7 | 16 | 16 | 0.47037 | 0.38889
| 8 | 15 | 16 | 0.57037 | 0.48889
| 9 | 13 | 16 | 0.65556 | 0.58889
| 10 | 14 | 16 | 0.74074 | 0.68889
| 11 | 11 | 16 | 0.8 | 0.76667
| 12 | 16 | 16 | 0.85926 | 0.84444
| 13 | 14 | 16 | 0.91852 | 0.89259
| 14 | 16 | 16 | 0.97037 | 0.94074
| 15 | 15 | 16 | 1 | 0.97778
| 16 | 13 | 16 | 1 | 1
| 17 | 14 | 16 | 1 | 1
| 18 | 11 | 16 | 1 | 1
| 19 | 16 | 16 | 1 | 1
| 20 | 14 | 16 | 1 | 1
| 21 | 16 | 16 | 1 | 1
| 22 | 15 | 16 | 1 | 1
| 23 | 13 | 16 | 1 | 1
| 24 | 14 | 16 | 1 | 1
| 25 | 11 | 16 | 1 | 1
| 26 | 16 | 16 | 1 | 1
| 27 | 14 | 16 | 1 | 1
| 28 | 16 | 16 | 1 | 1
| 29 | 12 | 16 | 1 | 1
| 30 | 11 | 16 | 1 | 1
| 31 | 15 | 16 | 1 | 1
| Grand Total | 434 | 496 | 23.9741 | 23.3889
| ACH | Column Labels
| DAYS | ACTUAL | PLAN
| 1 | 2.593% | 2.222%
| 2 | 5.926% | 4.444%
| 3 | 10% | 9.63%
| 4 | 18.52% | 14.81%
| 5 | 26.3% | 21.11%
| 6 | 35.56% | 28.89%
| 7 | 47.04% | 38.89%
| 8 | 57.04% | 48.89%
| 9 | 65.56% | 58.89%
| 10 | 74.07% | 68.89%
| 11 | 80% | 76.67%
| 12 | 85.93% | 84.44%
| 13 | 91.85% | 89.26%
| 14 | 97.04% | 94.07%
| 15 | 100% | 97.78%
| 16 | 100% | 100%
| 17 | 100% | 100%
| 18 | 100% | 100%
| 19 | 100% | 100%
| 20 | 100% | 100%
| 21 | 100% | 100%
| 22 | 100% | 100%
| 23 | 100% | 100%
| 24 | 100% | 100%
| 25 | 100% | 100%
| 26 | 100% | 100%
| 27 | 100% | 100%
| 28 | 100% | 100%
| 29 | 100% | 100%
| 30 | 100% | 100%
| 31 | 100% | 100%
| DATE | DOZER READINESS | DAILY ACTUAL | DAILY PLAN
| 1 | 15 | 2.593% | 2.222%
| 2 | 15 | 5.926% | 4.444%
| 3 | 13 | 10% | 9.63%
| 4 | 13 | 18.52% | 14.81%
| 5 | 14 | 26.3% | 21.11%
| 6 | 14 | 35.56% | 28.89%
| 7 | 11 | 47.04% | 38.89%
| 8 | 11 | 57.04% | 48.89%
| 9 | 16 | 65.56% | 58.89%
| 10 | 16 | 74.07% | 68.89%
| 11 | 14 | 80% | 76.67%
| 12 | 14 | 85.93% | 84.44%
| 13 | 16 | 91.85% | 89.26%
| 14 | 16 | 97.04% | 94.07%
| 15 | 15 | 100% | 97.78%
| 16 | 15 | 100% | 100%
| 17 | 13 | 100% | 100%
| 18 | 13 | 100% | 100%
| 19 | 14 | 100% | 100%
| 20 | 14 | 100% | 100%
| 21 | 11 | 100% | 100%
| 22 | 11 | 100% | 100%
| 23 | 16 | 100% | 100%
| 24 | 16 | 100% | 100%
| 25 | 14 | 100% | 100%
| 26 | 14 | 100% | 100%
| 27 | 16 | 100% | 100%
| 28 | 16 | 100% | 100%
| 29 | 15 | 100% | 100%
| 30 | 15 | 100% | 100%
| 31 | 13 | 100% | 100%
| DATE | PA DOZER | DAILY ACTUAL | DAILY PLAN
| 1 | 87% | 2.593% | 2.222%
| 2 | 87% | 5.926% | 4.444%
| 3 | 80% | 10% | 9.63%
| 4 | 80% | 18.52% | 14.81%
| 5 | 83% | 26.3% | 21.11%
| 6 | 83% | 35.56% | 28.89%
| 7 | 72% | 47.04% | 38.89%
| 8 | 72% | 57.04% | 48.89%
| 9 | 100% | 65.56% | 58.89%
| 10 | 100% | 74.07% | 68.89%
| 11 | 90% | 80% | 76.67%
| 12 | 90% | 85.93% | 84.44%
| 13 | 98% | 91.85% | 89.26%
| 14 | 98% | 97.04% | 94.07%
| 15 | 93% | 100% | 97.78%
| 16 | 93% | 100% | 100%
| 17 | 87% | 100% | 100%
| 18 | 87% | 100% | 100%
| 19 | 80% | 100% | 100%
| 20 | 80% | 100% | 100%
| 21 | 83% | 100% | 100%
| 22 | 83% | 100% | 100%
| 23 | 72% | 100% | 100%
| 24 | 72% | 100% | 100%
| 25 | 100% | 100% | 100%
| 26 | 100% | 100% | 100%
| 27 | 90% | 100% | 100%
| 28 | 90% | 100% | 100%
| 29 | 98% | 100% | 100%
| 30 | 98% | 100% | 100%
| 31 | 93% | 100% | 100%
| DATE | MTBF (H) | DAILY ACTUAL | DAILY PLAN
| 1 | 80 | 2.593% | 2.222%
| 2 | 80 | 5.926% | 4.444%
| 3 | 60 | 10% | 9.63%
| 4 | 60 | 18.52% | 14.81%
| 5 | 50 | 26.3% | 21.11%
| 6 | 50 | 35.56% | 28.89%
| 7 | 75 | 47.04% | 38.89%
| 8 | 75 | 57.04% | 48.89%
| 9 | 83 | 65.56% | 58.89%
| 10 | 83 | 74.07% | 68.89%
| 11 | 65 | 80% | 76.67%
| 12 | 65 | 85.93% | 84.44%
| 13 | 73 | 91.85% | 89.26%
| 14 | 73 | 97.04% | 94.07%
| 15 | 80 | 100% | 97.78%
| 16 | 80 | 100% | 100%
| 17 | 60 | 100% | 100%
| 18 | 60 | 100% | 100%
| 19 | 50 | 100% | 100%
| 20 | 50 | 100% | 100%
| 21 | 75 | 100% | 100%
| 22 | 75 | 100% | 100%
| 23 | 83 | 100% | 100%
| 24 | 83 | 100% | 100%
| 25 | 65 | 100% | 100%
| 26 | 65 | 100% | 100%
| 27 | 73 | 100% | 100%
| 28 | 73 | 100% | 100%
| 29 | 80 | 100% | 100%
| 30 | 80 | 100% | 100%
| 31 | 60 | 100% | 100%
| DATE | MTTR (H) | DAILY ACTUAL | DAILY PLAN
| 1 | 80 | 2.593% | 2.222%
| 2 | 80 | 5.926% | 4.444%
| 3 | 60 | 10% | 9.63%
| 4 | 60 | 18.52% | 14.81%
| 5 | 50 | 26.3% | 21.11%
| 6 | 50 | 35.56% | 28.89%
| 7 | 75 | 47.04% | 38.89%
| 8 | 75 | 57.04% | 48.89%
| 9 | 83 | 65.56% | 58.89%
| 10 | 83 | 74.07% | 68.89%
| 11 | 65 | 80% | 76.67%
| 12 | 65 | 85.93% | 84.44%
| 13 | 73 | 91.85% | 89.26%
| 14 | 73 | 97.04% | 94.07%
| 15 | 80 | 100% | 97.78%
| 16 | 80 | 100% | 100%
| 17 | 60 | 100% | 100%
| 18 | 60 | 100% | 100%
| 19 | 50 | 100% | 100%
| 20 | 50 | 100% | 100%
| 21 | 75 | 100% | 100%
| 22 | 75 | 100% | 100%
| 23 | 83 | 100% | 100%
| 24 | 83 | 100% | 100%
| 25 | 65 | 100% | 100%
| 26 | 65 | 100% | 100%
| 27 | 73 | 100% | 100%
| 28 | 73 | 100% | 100%
| 29 | 80 | 100% | 100%
| 30 | 80 | 100% | 100%
| 31 | 60 | 100% | 100%
| DATE | DAILY ACTUAL | DAILY PLAN | MTTR (H) | Sum of DOZER_READINESS | Sum of PA_DOZER | Sum of MTBF
| 1 | 2.593% | 2.222% | 80 | 15 | 87% | 80
| 2 | 5.926% | 4.444% | 80 | 15 | 87% | 80
| 3 | 10% | 9.63% | 60 | 13 | 80% | 60
| 4 | 18.52% | 14.81% | 60 | 13 | 80% | 60
| 5 | 26.3% | 21.11% | 50 | 14 | 83% | 50
| 6 | 35.56% | 28.89% | 50 | 14 | 83% | 50
| 7 | 47.04% | 38.89% | 75 | 11 | 72% | 75
| 8 | 57.04% | 48.89% | 75 | 11 | 72% | 75
| 9 | 65.56% | 58.89% | 83 | 16 | 100% | 83
| 10 | 74.07% | 68.89% | 83 | 16 | 100% | 83
| 11 | 80% | 76.67% | 65 | 14 | 90% | 65
| 12 | 85.93% | 84.44% | 65 | 14 | 90% | 65
| 13 | 91.85% | 89.26% | 73 | 16 | 98% | 73
| 14 | 97.04% | 94.07% | 73 | 16 | 98% | 73
| 15 | 100% | 97.78% | 80 | 15 | 93% | 80
| 16 | 100% | 100% | 80 | 15 | 93% | 80
| 17 | 100% | 100% | 60 | 13 | 87% | 60
| 18 | 100% | 100% | 60 | 13 | 87% | 60
| 19 | 100% | 100% | 50 | 14 | 80% | 50
| 20 | 100% | 100% | 50 | 14 | 80% | 50
| 21 | 100% | 100% | 75 | 11 | 83% | 75
| 22 | 100% | 100% | 75 | 11 | 83% | 75
| 23 | 100% | 100% | 83 | 16 | 72% | 83
| 24 | 100% | 100% | 83 | 16 | 72% | 83
| 25 | 100% | 100% | 65 | 14 | 100% | 65
| 26 | 100% | 100% | 65 | 14 | 100% | 65
| 27 | 100% | 100% | 73 | 16 | 90% | 73
| 28 | 100% | 100% | 73 | 16 | 90% | 73
| 29 | 100% | 100% | 80 | 15 | 98% | 80
| 30 | 100% | 100% | 80 | 15 | 98% | 80
| 31 | 100% | 100% | 60 | 13 | 93% | 60
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## DASHBOARD
DASHBOARD IMPROVEMENT DOZER
ACHIVEMENT ACTION PLAN VS ACTUAL
ACHIVEMENT PARAMETER
27
1
7
70,37%
TOTAL ISSUE
OPEN
OVERDUE
COMPLETION RATE
DISTRIBUSI STATUS
19
CLOSED
7
PROGRESS
COMPLETION RATE
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
DOZER READINESS VS ACH
MTBF VS ACH
PA DOZER VS ACH
MTTR VS ACH
PLAN VS ACTUAL DOZER READINESS
PLAN VS ACTUAL MTBF
PLAN VS ACTUAL PA DOZER
PLAN VS ACTUAL MTTR