## Activity Plan
IMPROVEMENT LEADTIME SITE CAM — PROJECT DEVELOPMENT PLAN | [15 empty] | PROJECT START |  | BULAN |  | TAHUN |  | DURASI (D)
[18 empty] | JUNI |  | 2026 |  | 90 |  |  |  |  | COMPLETE |  |  |  | STILL PROGRESS | [77 empty] | UNDER TARGET (Actual < Plan) | [5 empty] | DELAY / GAP / KETERLAMBATAN | [6 empty] | PROGRESS ON SCHEDULE | [5 empty] | COMPLETED ON PLAN |  |  |  |  | AHEAD OF SCHEDULE | [7 empty] | < 80% |  |  | > 80% & < 90% |  |  |  | > 90% & < 95% |  |  |  | > 95% & < 100% |  |  |  | > 100%
4617400%
TEMA : MENINGKATKAN LEADTIME SUPPLY PARTS
JUDUL : MENINGKATKAN LEADTIME SUPPLY PARTS SANY DI SITE CAM | [15 empty] | PLAN | [90 empty] | ACTUAL | [90 empty] | ACHIVE
[6 empty] | PLAN |  |  | ACTUAL | [6 empty] | Jun 2026 | [29 empty] | Jul 2026 | [30 empty] | Aug 2026 | [29 empty] | Jun 2026 | [29 empty] | Jul 2026 | [30 empty] | Aug 2026 | [29 empty] | Jun 2026 | [29 empty] | Jul 2026 | [30 empty] | Aug 2026
NO | 5 FACTOR | BRAINSTORMING (PROBLEM) | CATEGORY | ACTION PLAN | PIC | PLAN START | DUE DATA | PLAN DURATION | ACTUAL START | ACTUAL FINISH | ACTUAL DURATION | STATUS | DUE STATUS | COMPLETION | COMPLETION_FLAG | [91 empty] | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | time axis 2026-06-01 to 2026-08-30
1 | METHOD | Refueling unit DT OB (SKT) - Waktu refueling unit DT tidak beraturan - Unit antri panjang - Unit loader gantung DT refueling antri bersamaan - Durasi / waktu refueling lama | Quick Action | Program refueling parkir bebek saat rest time (Saat jam oprasional unit DT tidak antri refueling, tidak ada unit loader menunggu DT) 1. Unit DT parkir bebek saat rest time 2. Fuel Truck Khusu refueling saat restime 3. Monitoring unit refueling parkir bebek - Fleet loader = DT loader act vs DT loader refueling =......% | ANDREAS | 2026-05-15 | 2026-05-31 | 17 |  |  | No Progress | OPEN | OVERDUE | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | METHOD | Avaibility Parts Fast Moving (MR To GI) < 80% proses RM Plant waiting part | Quick Action | Proses pelaksanaan monitoring ketersediaan part Fast moving 1. Program Akurasi budget part fast moving (Continue) 2. Ketersediaan part On site (Pengadaan stock Inventory) tidak ada waiting part fast moving | HC | 2026-05-20 | 2026-05-31 | 12 |  |  | No Progress | OPEN | OVERDUE | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | MAN | Part fast moving tidak masuk stock inventory | Quick Action | Daily meeting koordinasi Logistic & Plant penentuan item wajib stock * Item New Inventory Create NISR lanjut subtitusi item inventory masuk budget tidak wajib stock | ANDREAS | 2026-05-01 | 2026-05-31 | 31 |  |  | No Progress | OPEN | OVERDUE | 52.67% | 0 | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | DAILY ACHIVEMENT | [13 empty] | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  | DOZER READINESS | PLAN | [12 empty] | 2026-06-01: 16; 2026-06-02: 16; 2026-06-03: 16; 2026-06-04: 16; 2026-06-05: 16; 2026-06-06: 16; 2026-06-07: 16; 2026-06-08: 16; 2026-06-09: 16; 2026-06-10: 16; 2026-06-11: 16; 2026-06-12: 16; 2026-06-13: 16; 2026-06-14: 16; 2026-06-15: 16; 2026-06-16: 16; 2026-06-17: 16; 2026-06-18: 16; 2026-06-19: 16; 2026-06-20: 16; 2026-06-21: 16; 2026-06-22: 16; 2026-06-23: 16; 2026-06-24: 16; 2026-06-25: 16; 2026-06-26: 16; 2026-06-27: 16; 2026-06-28: 16; 2026-06-29: 16; 2026-06-30: 16; 2026-07-01: 16
|  |  | ACTUAL | [12 empty] | 2026-06-01: 15; 2026-06-02: 13; 2026-06-03: 14; 2026-06-04: 11; 2026-06-05: 16; 2026-06-06: 14; 2026-06-07: 16; 2026-06-08: 15; 2026-06-09: 13; 2026-06-10: 14; 2026-06-11: 11; 2026-06-12: 16; 2026-06-13: 14; 2026-06-14: 16; 2026-06-15: 15; 2026-06-16: 13; 2026-06-17: 14; 2026-06-18: 11; 2026-06-19: 16; 2026-06-20: 14; 2026-06-21: 16; 2026-06-22: 15; 2026-06-23: 13; 2026-06-24: 14; 2026-06-25: 11; 2026-06-26: 16; 2026-06-27: 14; 2026-06-28: 16; 2026-06-29: 12; 2026-06-30: 11; 2026-07-01: 15
|  |  | ACHIVE | [12 empty] | 2026-06-01: 93.75%; 2026-06-02: 81.25%; 2026-06-03: 87.5%; 2026-06-04: 68.75%; 2026-06-05: 100%; 2026-06-06: 87.5%; 2026-06-07: 100%; 2026-06-08: 93.75%; 2026-06-09: 81.25%; 2026-06-10: 87.5%; 2026-06-11: 68.75%; 2026-06-12: 100%; 2026-06-13: 87.5%; 2026-06-14: 100%; 2026-06-15: 93.75%; 2026-06-16: 81.25%; 2026-06-17: 87.5%; 2026-06-18: 68.75%; 2026-06-19: 100%; 2026-06-20: 87.5%; 2026-06-21: 100%; 2026-06-22: 93.75%; 2026-06-23: 81.25%; 2026-06-24: 87.5%; 2026-06-25: 68.75%; 2026-06-26: 100%; 2026-06-27: 87.5%; 2026-06-28: 100%; 2026-06-29: 75%; 2026-06-30: 68.75%; 2026-07-01: 93.75%
|  | PA ALL DOZER | PLAN | [12 empty] | 2026-06-01: 90%; 2026-06-02: 90%; 2026-06-03: 90%; 2026-06-04: 90%; 2026-06-05: 90%; 2026-06-06: 90%; 2026-06-07: 90%; 2026-06-08: 90%; 2026-06-09: 90%; 2026-06-10: 90%; 2026-06-11: 90%; 2026-06-12: 90%; 2026-06-13: 90%; 2026-06-14: 90%; 2026-06-15: 90%; 2026-06-16: 90%; 2026-06-17: 90%; 2026-06-18: 90%; 2026-06-19: 90%; 2026-06-20: 90%; 2026-06-21: 90%; 2026-06-22: 90%; 2026-06-23: 90%; 2026-06-24: 90%; 2026-06-25: 90%; 2026-06-26: 90%; 2026-06-27: 90%; 2026-06-28: 90%; 2026-06-29: 90%; 2026-06-30: 90%; 2026-07-01: 90%
|  |  | ACTUAL | [12 empty] | 2026-06-01: 87%; 2026-06-02: 80%; 2026-06-03: 83%; 2026-06-04: 72%; 2026-06-05: 100%; 2026-06-06: 90%; 2026-06-07: 98%; 2026-06-08: 93%; 2026-06-09: 87%; 2026-06-10: 80%; 2026-06-11: 83%; 2026-06-12: 72%; 2026-06-13: 100%; 2026-06-14: 90%; 2026-06-15: 98%; 2026-06-16: 93%; 2026-06-17: 87%; 2026-06-18: 80%; 2026-06-19: 83%; 2026-06-20: 72%; 2026-06-21: 100%; 2026-06-22: 90%; 2026-06-23: 98%; 2026-06-24: 93%; 2026-06-25: 87%; 2026-06-26: 80%; 2026-06-27: 83%; 2026-06-28: 72%; 2026-06-29: 100%; 2026-06-30: 90%; 2026-07-01: 98%
|  |  | ACHIVE | [12 empty] | 2026-06-01: 96.67%; 2026-06-02: 88.89%; 2026-06-03: 92.22%; 2026-06-04: 80%; 2026-06-05: 111.1%; 2026-06-06: 100%; 2026-06-07: 108.9%; 2026-06-08: 103.3%; 2026-06-09: 96.67%; 2026-06-10: 88.89%; 2026-06-11: 92.22%; 2026-06-12: 80%; 2026-06-13: 111.1%; 2026-06-14: 100%; 2026-06-15: 108.9%; 2026-06-16: 103.3%; 2026-06-17: 96.67%; 2026-06-18: 88.89%; 2026-06-19: 92.22%; 2026-06-20: 80%; 2026-06-21: 111.1%; 2026-06-22: 100%; 2026-06-23: 108.9%; 2026-06-24: 103.3%; 2026-06-25: 96.67%; 2026-06-26: 88.89%; 2026-06-27: 92.22%; 2026-06-28: 80%; 2026-06-29: 111.1%; 2026-06-30: 100%; 2026-07-01: 108.9%
|  | MTBF | PLAN | [12 empty] | 2026-06-01: 70; 2026-06-02: 70; 2026-06-03: 70; 2026-06-04: 70; 2026-06-05: 70; 2026-06-06: 70; 2026-06-07: 70; 2026-06-08: 70; 2026-06-09: 70; 2026-06-10: 70; 2026-06-11: 70; 2026-06-12: 70; 2026-06-13: 70; 2026-06-14: 70; 2026-06-15: 70; 2026-06-16: 70; 2026-06-17: 70; 2026-06-18: 70; 2026-06-19: 70; 2026-06-20: 70; 2026-06-21: 70; 2026-06-22: 70; 2026-06-23: 70; 2026-06-24: 70; 2026-06-25: 70; 2026-06-26: 70; 2026-06-27: 70; 2026-06-28: 70; 2026-06-29: 70; 2026-06-30: 70; 2026-07-01: 70
|  |  | ACTUAL | [12 empty] | 2026-06-01: 80; 2026-06-02: 60; 2026-06-03: 50; 2026-06-04: 75; 2026-06-05: 83; 2026-06-06: 65; 2026-06-07: 73; 2026-06-08: 80; 2026-06-09: 60; 2026-06-10: 50; 2026-06-11: 75; 2026-06-12: 83; 2026-06-13: 65; 2026-06-14: 73; 2026-06-15: 80; 2026-06-16: 60; 2026-06-17: 50; 2026-06-18: 75; 2026-06-19: 83; 2026-06-20: 65; 2026-06-21: 73; 2026-06-22: 80; 2026-06-23: 60; 2026-06-24: 50; 2026-06-25: 75; 2026-06-26: 83; 2026-06-27: 65; 2026-06-28: 73; 2026-06-29: 75; 2026-06-30: 83; 2026-07-01: 65
|  |  | ACHIVE | [12 empty] | 2026-06-01: 114.3%; 2026-06-02: 85.71%; 2026-06-03: 71.43%; 2026-06-04: 107.1%; 2026-06-05: 118.6%; 2026-06-06: 92.86%; 2026-06-07: 104.3%; 2026-06-08: 114.3%; 2026-06-09: 85.71%; 2026-06-10: 71.43%; 2026-06-11: 107.1%; 2026-06-12: 118.6%; 2026-06-13: 92.86%; 2026-06-14: 104.3%; 2026-06-15: 114.3%; 2026-06-16: 85.71%; 2026-06-17: 71.43%; 2026-06-18: 107.1%; 2026-06-19: 118.6%; 2026-06-20: 92.86%; 2026-06-21: 104.3%; 2026-06-22: 114.3%; 2026-06-23: 85.71%; 2026-06-24: 71.43%; 2026-06-25: 107.1%; 2026-06-26: 118.6%; 2026-06-27: 92.86%; 2026-06-28: 104.3%; 2026-06-29: 107.1%; 2026-06-30: 118.6%; 2026-07-01: 92.86%
|  | MTTR | PLAN | [12 empty] | 2026-06-01: 80; 2026-06-02: 80; 2026-06-03: 80; 2026-06-04: 80; 2026-06-05: 80; 2026-06-06: 80; 2026-06-07: 80; 2026-06-08: 80; 2026-06-09: 80; 2026-06-10: 80; 2026-06-11: 80; 2026-06-12: 80; 2026-06-13: 80; 2026-06-14: 80; 2026-06-15: 80; 2026-06-16: 80; 2026-06-17: 80; 2026-06-18: 80; 2026-06-19: 80; 2026-06-20: 80; 2026-06-21: 80; 2026-06-22: 80; 2026-06-23: 80; 2026-06-24: 80; 2026-06-25: 80; 2026-06-26: 80; 2026-06-27: 80; 2026-06-28: 80; 2026-06-29: 80; 2026-06-30: 80; 2026-07-01: 80
|  |  | ACTUAL | [12 empty] | 2026-06-01: 80; 2026-06-02: 60; 2026-06-03: 50; 2026-06-04: 75; 2026-06-05: 83; 2026-06-06: 65; 2026-06-07: 73; 2026-06-08: 80; 2026-06-09: 60; 2026-06-10: 50; 2026-06-11: 75; 2026-06-12: 83; 2026-06-13: 65; 2026-06-14: 73; 2026-06-15: 80; 2026-06-16: 60; 2026-06-17: 50; 2026-06-18: 75; 2026-06-19: 83; 2026-06-20: 65; 2026-06-21: 73; 2026-06-22: 80; 2026-06-23: 60; 2026-06-24: 50; 2026-06-25: 75; 2026-06-26: 83; 2026-06-27: 65; 2026-06-28: 73; 2026-06-29: 75; 2026-06-30: 83; 2026-07-01: 65
|  |  | ACHIVE | [12 empty] | 2026-06-01: 100%; 2026-06-02: 75%; 2026-06-03: 62.5%; 2026-06-04: 93.75%; 2026-06-05: 103.8%; 2026-06-06: 81.25%; 2026-06-07: 91.25%; 2026-06-08: 100%; 2026-06-09: 75%; 2026-06-10: 62.5%; 2026-06-11: 93.75%; 2026-06-12: 103.8%; 2026-06-13: 81.25%; 2026-06-14: 91.25%; 2026-06-15: 100%; 2026-06-16: 75%; 2026-06-17: 62.5%; 2026-06-18: 93.75%; 2026-06-19: 103.8%; 2026-06-20: 81.25%; 2026-06-21: 91.25%; 2026-06-22: 100%; 2026-06-23: 75%; 2026-06-24: 62.5%; 2026-06-25: 93.75%; 2026-06-26: 103.8%; 2026-06-27: 81.25%; 2026-06-28: 91.25%; 2026-06-29: 93.75%; 2026-06-30: 103.8%; 2026-07-01: 81.25%
[6 empty] | klo perlu MTBF | klo perlu MTBF

## DATA
TBL_DOZER_READINESS |  |  |  | TBL_PA ALL DOZER |  |  |  | TBL_MTBF |  |  |  | TBL_MTTR |  |  |  | ACHIVEMENT | [7 empty] | Tbl_Summary | [13 empty] | Tbl_ACH | [33 empty] | Tbl_Daily | [14 empty] | SUM_ACT
PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | PARAMETER | CATEGORY | DATE | VALUE | NO | 5 FACTOR | CATEGORY | PIC | PLAN START | DUE DATA | PLAN DURATION | ACTUAL START | ACTUAL FINISH | ACTUAL DURATION | STATUS | DUE STATUS | COMPLETION | COMPLETION_FLAG | ACHIVEMENT | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 |  |  | NO | 5 FACTOR | CATEGORY | Attribute | Value | SS | PARAMETER | CATEGORY | DATE | VALUE | BULAN |  | DAY | TYPE | ACHIEVEMENT | DATE | DAILY_PLAN | DAILY_ACTUAL | DOZER_READINESS | PA_DOZER | MTBF | MTTR
DOZER READINESS | PLAN | 1 | 16 | PA ALL DOZER | PLAN | 1 | 90% | MTBF | PLAN | 1 | 70 | MTTR | PLAN | 1 | 80 | DOZER READINESS | ACHIVE | 1 | 93.75% | DAILY ACHIVEMENT | PLAN | 1 | 5% | 1 | METHOD | Quick Action | ANDREAS | 2026-05-15 | 2026-05-31 | 17 | 0 | N/A | No Progress | OPEN | OVERDUE | 52.67% | 0 | PLAN | 5% | 8% | 10% | 12.67% | 15.17% | 17.67% | 20.17% | 22.67% | 25.17% | 27.67% | 30.17% | 32.67% | 35.17% | 37.67% | 40.17% | 42.67% | 45.17% | 47.67% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 50.17% | 51% | 51.83% | 52.67% |  |  | 1 | MAN | Quick Action | 1 | 0% | FACTOR | DOZER READINESS | PLAN | 1 | 16 | 1 | JANUARI | 46174 | PLAN | 5% | 1 | 5% | 53.5% | 15 | 87% | 80 | 80
DOZER READINESS | ACTUAL | 1 | 15 | PA ALL DOZER | ACTUAL | 1 | 87% | MTBF | ACTUAL | 1 | 80 | MTTR | ACTUAL | 1 | 80 | DOZER READINESS | ACHIVE | 2 | 81.25% | DAILY ACHIVEMENT | PLAN | 2 | 8% | 2 | METHOD | Quick Action | HC | 2026-05-20 | 2026-05-31 | 12 | 0 | N/A | No Progress | OPEN | OVERDUE | 52.67% | 0 | ACTUAL | 53.5% | 54.33% | 55.17% | 56% | 56.83% | 60% | 63% | 66% | 69% | 72% | 75% | 78% | 81% | 84% | 87% | 90% | 93% | 96% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A |  |  | 1 | MAN | Quick Action | 2 | 0% | FACTOR | DOZER READINESS | ACTUAL | 1 | 15 | 2 | FEBRUARI | 46174 | ACTUAL | 53.5% | 2 | 8% | 54.33% | 15 | 87% | 80 | 80
DOZER READINESS | PLAN | 2 | 16 | PA ALL DOZER | PLAN | 2 | 90% | MTBF | PLAN | 2 | 70 | MTTR | PLAN | 2 | 80 | DOZER READINESS | ACHIVE | 3 | 87.5% | DAILY ACHIVEMENT | PLAN | 3 | 10% | 3 | MAN | Quick Action | ANDREAS | 2026-05-01 | 2026-05-31 | 31 | 0 | N/A | No Progress | OPEN | OVERDUE | 52.67% | 0 | [34 empty] | 1 | MAN | Quick Action | 3 | 0% | FACTOR | DOZER READINESS | PLAN | 2 | 16 | 3 | MARET | 46175 | PLAN | 8% | 3 | 10% | 55.17% | 13 | 80% | 60 | 60
DOZER READINESS | ACTUAL | 2 | 13 | PA ALL DOZER | ACTUAL | 2 | 80% | MTBF | ACTUAL | 2 | 60 | MTTR | ACTUAL | 2 | 60 | DOZER READINESS | ACHIVE | 4 | 68.75% | DAILY ACHIVEMENT | PLAN | 4 | 12.67% | N/A | [7 empty] | N/A | [5 empty] | Tbl_Daily ACH | [33 empty] | 1 | MAN | Quick Action | 4 | 0% | FACTOR | DOZER READINESS | ACTUAL | 2 | 13 | 4 | APRIL | 46175 | ACTUAL | 54.33% | 4 | 12.67% | 56% | 13 | 80% | 60 | 60
DOZER READINESS | PLAN | 3 | 16 | PA ALL DOZER | PLAN | 3 | 90% | MTBF | PLAN | 3 | 70 | MTTR | PLAN | 3 | 80 | DOZER READINESS | ACHIVE | 5 | 100% | DAILY ACHIVEMENT | PLAN | 5 | 15.17% | N/A | [7 empty] | N/A | [5 empty] | NO | 5 FACTOR | CATEGORY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | MAN | Quick Action | 5 | 0% | FACTOR | DOZER READINESS | PLAN | 3 | 16 | 5 | MEI | 46176 | PLAN | 10% | 5 | 15.17% | 56.83% | 14 | 83% | 50 | 50
DOZER READINESS | ACTUAL | 3 | 14 | PA ALL DOZER | ACTUAL | 3 | 83% | MTBF | ACTUAL | 3 | 50 | MTTR | ACTUAL | 3 | 50 | DOZER READINESS | ACHIVE | 6 | 87.5% | DAILY ACHIVEMENT | PLAN | 6 | 17.67% | N/A | [7 empty] | N/A | [5 empty] | 1 | METHOD | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 6 | 0% | FACTOR | DOZER READINESS | ACTUAL | 3 | 14 | 6 | JUNI | 46176 | ACTUAL | 55.17% | 6 | 17.67% | 60% | 14 | 83% | 50 | 50
DOZER READINESS | PLAN | 4 | 16 | PA ALL DOZER | PLAN | 4 | 90% | MTBF | PLAN | 4 | 70 | MTTR | PLAN | 4 | 80 | DOZER READINESS | ACHIVE | 7 | 100% | DAILY ACHIVEMENT | PLAN | 7 | 20.17% | N/A | [7 empty] | N/A | [5 empty] | 2 | METHOD | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 7 | 100% | FACTOR | DOZER READINESS | PLAN | 4 | 16 | 7 | JULI | 46177 | PLAN | 12.67% | 7 | 20.17% | 63% | 11 | 72% | 75 | 75
DOZER READINESS | ACTUAL | 4 | 11 | PA ALL DOZER | ACTUAL | 4 | 72% | MTBF | ACTUAL | 4 | 75 | MTTR | ACTUAL | 4 | 75 | DOZER READINESS | ACHIVE | 8 | 93.75% | DAILY ACHIVEMENT | PLAN | 8 | 22.67% | N/A | [7 empty] | N/A | [5 empty] | 3 | MAN | Quick Action | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1 | MAN | Quick Action | 8 | 100% | FACTOR | DOZER READINESS | ACTUAL | 4 | 11 | 8 | AGUSTUS | 46177 | ACTUAL | 56% | 8 | 22.67% | 66% | 11 | 72% | 75 | 75
DOZER READINESS | PLAN | 5 | 16 | PA ALL DOZER | PLAN | 5 | 90% | MTBF | PLAN | 5 | 70 | MTTR | PLAN | 5 | 80 | DOZER READINESS | ACHIVE | 9 | 81.25% | DAILY ACHIVEMENT | PLAN | 9 | 25.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 9 | 100% | FACTOR | DOZER READINESS | PLAN | 5 | 16 | 9 | SEPTEMBER | 46178 | PLAN | 15.17% | 9 | 25.17% | 69% | 16 | 100% | 83 | 83
DOZER READINESS | ACTUAL | 5 | 16 | PA ALL DOZER | ACTUAL | 5 | 100% | MTBF | ACTUAL | 5 | 83 | MTTR | ACTUAL | 5 | 83 | DOZER READINESS | ACHIVE | 10 | 87.5% | DAILY ACHIVEMENT | PLAN | 10 | 27.67% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 10 | 100% | FACTOR | DOZER READINESS | ACTUAL | 5 | 16 | 10 | OKTOBER | 46178 | ACTUAL | 56.83% | 10 | 27.67% | 72% | 16 | 100% | 83 | 83
DOZER READINESS | PLAN | 6 | 16 | PA ALL DOZER | PLAN | 6 | 90% | MTBF | PLAN | 6 | 70 | MTTR | PLAN | 6 | 80 | DOZER READINESS | ACHIVE | 11 | 68.75% | DAILY ACHIVEMENT | PLAN | 11 | 30.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 11 | 100% | FACTOR | DOZER READINESS | PLAN | 6 | 16 | 11 | NOVEMBER | 46179 | PLAN | 17.67% | 11 | 30.17% | 75% | 14 | 90% | 65 | 65
DOZER READINESS | ACTUAL | 6 | 14 | PA ALL DOZER | ACTUAL | 6 | 90% | MTBF | ACTUAL | 6 | 65 | MTTR | ACTUAL | 6 | 65 | DOZER READINESS | ACHIVE | 12 | 100% | DAILY ACHIVEMENT | PLAN | 12 | 32.67% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 12 | 100% | FACTOR | DOZER READINESS | ACTUAL | 6 | 14 | 12 | DESEMBER | 46179 | ACTUAL | 60% | 12 | 32.67% | 78% | 14 | 90% | 65 | 65
DOZER READINESS | PLAN | 7 | 16 | PA ALL DOZER | PLAN | 7 | 90% | MTBF | PLAN | 7 | 70 | MTTR | PLAN | 7 | 80 | DOZER READINESS | ACHIVE | 13 | 87.5% | DAILY ACHIVEMENT | PLAN | 13 | 35.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 13 | 100% | FACTOR | DOZER READINESS | PLAN | 7 | 16 |  |  | 46180 | PLAN | 20.17% | 13 | 35.17% | 81% | 16 | 98% | 73 | 73
DOZER READINESS | ACTUAL | 7 | 16 | PA ALL DOZER | ACTUAL | 7 | 98% | MTBF | ACTUAL | 7 | 73 | MTTR | ACTUAL | 7 | 73 | DOZER READINESS | ACHIVE | 14 | 100% | DAILY ACHIVEMENT | PLAN | 14 | 37.67% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 14 | 100% | FACTOR | DOZER READINESS | ACTUAL | 7 | 16 |  | 5 FACTOR | 46180 | ACTUAL | 63% | 14 | 37.67% | 84% | 16 | 98% | 73 | 73
DOZER READINESS | PLAN | 8 | 16 | PA ALL DOZER | PLAN | 8 | 90% | MTBF | PLAN | 8 | 70 | MTTR | PLAN | 8 | 80 | DOZER READINESS | ACHIVE | 15 | 93.75% | DAILY ACHIVEMENT | PLAN | 15 | 40.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 15 | 100% | FACTOR | DOZER READINESS | PLAN | 8 | 16 |  | MAN | 46181 | PLAN | 22.67% | 15 | 40.17% | 87% | 15 | 93% | 80 | 80
DOZER READINESS | ACTUAL | 8 | 15 | PA ALL DOZER | ACTUAL | 8 | 93% | MTBF | ACTUAL | 8 | 80 | MTTR | ACTUAL | 8 | 80 | DOZER READINESS | ACHIVE | 16 | 81.25% | DAILY ACHIVEMENT | PLAN | 16 | 42.67% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 16 | 100% | FACTOR | DOZER READINESS | ACTUAL | 8 | 15 |  | METHOD | 46181 | ACTUAL | 66% | 16 | 42.67% | 90% | 15 | 93% | 80 | 80
DOZER READINESS | PLAN | 9 | 16 | PA ALL DOZER | PLAN | 9 | 90% | MTBF | PLAN | 9 | 70 | MTTR | PLAN | 9 | 80 | DOZER READINESS | ACHIVE | 17 | 87.5% | DAILY ACHIVEMENT | PLAN | 17 | 45.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 17 | 100% | FACTOR | DOZER READINESS | PLAN | 9 | 16 |  | MACHINE | 46182 | PLAN | 25.17% | 17 | 45.17% | 93% | 13 | 87% | 60 | 60
DOZER READINESS | ACTUAL | 9 | 13 | PA ALL DOZER | ACTUAL | 9 | 87% | MTBF | ACTUAL | 9 | 60 | MTTR | ACTUAL | 9 | 60 | DOZER READINESS | ACHIVE | 18 | 68.75% | DAILY ACHIVEMENT | PLAN | 18 | 47.67% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 18 | 100% | FACTOR | DOZER READINESS | ACTUAL | 9 | 13 |  | MATERIAL | 46182 | ACTUAL | 69% | 18 | 47.67% | 96% | 13 | 87% | 60 | 60
DOZER READINESS | PLAN | 10 | 16 | PA ALL DOZER | PLAN | 10 | 90% | MTBF | PLAN | 10 | 70 | MTTR | PLAN | 10 | 80 | DOZER READINESS | ACHIVE | 19 | 100% | DAILY ACHIVEMENT | PLAN | 19 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 19 | 100% | FACTOR | DOZER READINESS | PLAN | 10 | 16 |  | ENVIRONTMENT | 46183 | PLAN | 27.67% | 19 | 50.17% | 99% | 14 | 80% | 50 | 50
DOZER READINESS | ACTUAL | 10 | 14 | PA ALL DOZER | ACTUAL | 10 | 80% | MTBF | ACTUAL | 10 | 50 | MTTR | ACTUAL | 10 | 50 | DOZER READINESS | ACHIVE | 20 | 87.5% | DAILY ACHIVEMENT | PLAN | 20 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 20 | 100% | FACTOR | DOZER READINESS | ACTUAL | 10 | 14 |  |  | 46183 | ACTUAL | 72% | 20 | 50.17% | 100% | 14 | 80% | 50 | 50
DOZER READINESS | PLAN | 11 | 16 | PA ALL DOZER | PLAN | 11 | 90% | MTBF | PLAN | 11 | 70 | MTTR | PLAN | 11 | 80 | DOZER READINESS | ACHIVE | 21 | 100% | DAILY ACHIVEMENT | PLAN | 21 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 21 | 100% | FACTOR | DOZER READINESS | PLAN | 11 | 16 |  |  | 46184 | PLAN | 30.17% | 21 | 50.17% | 100% | 11 | 83% | 75 | 75
DOZER READINESS | ACTUAL | 11 | 11 | PA ALL DOZER | ACTUAL | 11 | 83% | MTBF | ACTUAL | 11 | 75 | MTTR | ACTUAL | 11 | 75 | DOZER READINESS | ACHIVE | 22 | 93.75% | DAILY ACHIVEMENT | PLAN | 22 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 22 | 100% | FACTOR | DOZER READINESS | ACTUAL | 11 | 11 |  |  | 46184 | ACTUAL | 75% | 22 | 50.17% | 100% | 11 | 83% | 75 | 75
DOZER READINESS | PLAN | 12 | 16 | PA ALL DOZER | PLAN | 12 | 90% | MTBF | PLAN | 12 | 70 | MTTR | PLAN | 12 | 80 | DOZER READINESS | ACHIVE | 23 | 81.25% | DAILY ACHIVEMENT | PLAN | 23 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 23 | 100% | FACTOR | DOZER READINESS | PLAN | 12 | 16 |  |  | 46185 | PLAN | 32.67% | 23 | 50.17% | 100% | 16 | 72% | 83 | 83
DOZER READINESS | ACTUAL | 12 | 16 | PA ALL DOZER | ACTUAL | 12 | 72% | MTBF | ACTUAL | 12 | 83 | MTTR | ACTUAL | 12 | 83 | DOZER READINESS | ACHIVE | 24 | 87.5% | DAILY ACHIVEMENT | PLAN | 24 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 24 | 100% | FACTOR | DOZER READINESS | ACTUAL | 12 | 16 |  |  | 46185 | ACTUAL | 78% | 24 | 50.17% | 100% | 16 | 72% | 83 | 83
DOZER READINESS | PLAN | 13 | 16 | PA ALL DOZER | PLAN | 13 | 90% | MTBF | PLAN | 13 | 70 | MTTR | PLAN | 13 | 80 | DOZER READINESS | ACHIVE | 25 | 68.75% | DAILY ACHIVEMENT | PLAN | 25 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 25 | 100% | FACTOR | DOZER READINESS | PLAN | 13 | 16 |  |  | 46186 | PLAN | 35.17% | 25 | 50.17% | 100% | 14 | 100% | 65 | 65
DOZER READINESS | ACTUAL | 13 | 14 | PA ALL DOZER | ACTUAL | 13 | 100% | MTBF | ACTUAL | 13 | 65 | MTTR | ACTUAL | 13 | 65 | DOZER READINESS | ACHIVE | 26 | 100% | DAILY ACHIVEMENT | PLAN | 26 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 26 | 100% | FACTOR | DOZER READINESS | ACTUAL | 13 | 14 |  |  | 46186 | ACTUAL | 81% | 26 | 50.17% | 100% | 14 | 100% | 65 | 65
DOZER READINESS | PLAN | 14 | 16 | PA ALL DOZER | PLAN | 14 | 90% | MTBF | PLAN | 14 | 70 | MTTR | PLAN | 14 | 80 | DOZER READINESS | ACHIVE | 27 | 87.5% | DAILY ACHIVEMENT | PLAN | 27 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 27 | 100% | FACTOR | DOZER READINESS | PLAN | 14 | 16 |  |  | 46187 | PLAN | 37.67% | 27 | 50.17% | 100% | 16 | 90% | 73 | 73
DOZER READINESS | ACTUAL | 14 | 16 | PA ALL DOZER | ACTUAL | 14 | 90% | MTBF | ACTUAL | 14 | 73 | MTTR | ACTUAL | 14 | 73 | DOZER READINESS | ACHIVE | 28 | 100% | DAILY ACHIVEMENT | PLAN | 28 | 50.17% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 28 | 100% | FACTOR | DOZER READINESS | ACTUAL | 14 | 16 |  |  | 46187 | ACTUAL | 84% | 28 | 50.17% | 100% | 16 | 90% | 73 | 73
DOZER READINESS | PLAN | 15 | 16 | PA ALL DOZER | PLAN | 15 | 90% | MTBF | PLAN | 15 | 70 | MTTR | PLAN | 15 | 80 | DOZER READINESS | ACHIVE | 29 | 75% | DAILY ACHIVEMENT | PLAN | 29 | 51% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 29 | 100% | FACTOR | DOZER READINESS | PLAN | 15 | 16 |  |  | 46188 | PLAN | 40.17% | 29 | 51% | 100% | 15 | 98% | 80 | 80
DOZER READINESS | ACTUAL | 15 | 15 | PA ALL DOZER | ACTUAL | 15 | 98% | MTBF | ACTUAL | 15 | 80 | MTTR | ACTUAL | 15 | 80 | DOZER READINESS | ACHIVE | 30 | 68.75% | DAILY ACHIVEMENT | PLAN | 30 | 51.83% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 30 | 100% | FACTOR | DOZER READINESS | ACTUAL | 15 | 15 |  |  | 46188 | ACTUAL | 87% | 30 | 51.83% | 100% | 15 | 98% | 80 | 80
DOZER READINESS | PLAN | 16 | 16 | PA ALL DOZER | PLAN | 16 | 90% | MTBF | PLAN | 16 | 70 | MTTR | PLAN | 16 | 80 | DOZER READINESS | ACHIVE | 31 | #N/A | DAILY ACHIVEMENT | PLAN | 31 | 52.67% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | MAN | Quick Action | 31 | 100% | FACTOR | DOZER READINESS | PLAN | 16 | 16 |  |  | 46189 | PLAN | 42.67% | 31 | 52.67% | 0% | 13 | 93% | 60 | 60
DOZER READINESS | ACTUAL | 16 | 13 | PA ALL DOZER | ACTUAL | 16 | 93% | MTBF | ACTUAL | 16 | 60 | MTTR | ACTUAL | 16 | 60 | PA ALL DOZER | ACHIVE | 1 | 96.67% | DAILY ACHIVEMENT | ACTUAL | 1 | 53.5% | N/A | [7 empty] | N/A | [5 empty] | N/A |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2 | MAN | Quick Action | 3 | 0% | FACTOR | DOZER READINESS | ACTUAL | 16 | 13 |  |  | 46189 | ACTUAL | 90%
DOZER READINESS | PLAN | 17 | 16 | PA ALL DOZER | PLAN | 17 | 90% | MTBF | PLAN | 17 | 70 | MTTR | PLAN | 17 | 80 | PA ALL DOZER | ACHIVE | 2 | 88.89% | DAILY ACHIVEMENT | ACTUAL | 2 | 54.33% | N/A | [7 empty] | N/A | [39 empty] | 2 | MAN | Quick Action | 4 | 0% | FACTOR | DOZER READINESS | PLAN | 17 | 16 |  |  | 46190 | PLAN | 45.17%
DOZER READINESS | ACTUAL | 17 | 14 | PA ALL DOZER | ACTUAL | 17 | 87% | MTBF | ACTUAL | 17 | 50 | MTTR | ACTUAL | 17 | 50 | PA ALL DOZER | ACHIVE | 3 | 92.22% | DAILY ACHIVEMENT | ACTUAL | 3 | 55.17% | N/A | [7 empty] | N/A | [39 empty] | 2 | MAN | Quick Action | 5 | 100% | FACTOR | DOZER READINESS | ACTUAL | 17 | 14 |  |  | 46190 | ACTUAL | 93%
DOZER READINESS | PLAN | 18 | 16 | PA ALL DOZER | PLAN | 18 | 90% | MTBF | PLAN | 18 | 70 | MTTR | PLAN | 18 | 80 | PA ALL DOZER | ACHIVE | 4 | 80% | DAILY ACHIVEMENT | ACTUAL | 4 | 56% | [48 empty] | 2 | MAN | Quick Action | 6 | 0% | FACTOR | DOZER READINESS | PLAN | 18 | 16 |  |  | 46191 | PLAN | 47.67%
DOZER READINESS | ACTUAL | 18 | 11 | PA ALL DOZER | ACTUAL | 18 | 80% | MTBF | ACTUAL | 18 | 75 | MTTR | ACTUAL | 18 | 75 | PA ALL DOZER | ACHIVE | 5 | 111.1% | DAILY ACHIVEMENT | ACTUAL | 5 | 56.83% | [48 empty] | 2 | MAN | Quick Action | 7 | 100% | FACTOR | DOZER READINESS | ACTUAL | 18 | 11 |  |  | 46191 | ACTUAL | 96%
DOZER READINESS | PLAN | 19 | 16 | PA ALL DOZER | PLAN | 19 | 90% | MTBF | PLAN | 19 | 70 | MTTR | PLAN | 19 | 80 | PA ALL DOZER | ACHIVE | 6 | 100% | DAILY ACHIVEMENT | ACTUAL | 6 | 60% | [48 empty] | 2 | MAN | Quick Action | 8 | 100% | FACTOR | DOZER READINESS | PLAN | 19 | 16 |  |  | 46192 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 19 | 16 | PA ALL DOZER | ACTUAL | 19 | 83% | MTBF | ACTUAL | 19 | 83 | MTTR | ACTUAL | 19 | 83 | PA ALL DOZER | ACHIVE | 7 | 108.9% | DAILY ACHIVEMENT | ACTUAL | 7 | 63% | [48 empty] | 2 | MAN | Quick Action | 9 | 100% | FACTOR | DOZER READINESS | ACTUAL | 19 | 16 |  |  | 46192 | ACTUAL | 99%
DOZER READINESS | PLAN | 20 | 16 | PA ALL DOZER | PLAN | 20 | 90% | MTBF | PLAN | 20 | 70 | MTTR | PLAN | 20 | 80 | PA ALL DOZER | ACHIVE | 8 | 103.3% | DAILY ACHIVEMENT | ACTUAL | 8 | 66% | [48 empty] | 2 | MAN | Quick Action | 10 | 100% | FACTOR | DOZER READINESS | PLAN | 20 | 16 |  |  | 46193 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 20 | 14 | PA ALL DOZER | ACTUAL | 20 | 72% | MTBF | ACTUAL | 20 | 65 | MTTR | ACTUAL | 20 | 65 | PA ALL DOZER | ACHIVE | 9 | 96.67% | DAILY ACHIVEMENT | ACTUAL | 9 | 69% | [48 empty] | 2 | MAN | Quick Action | 11 | 100% | FACTOR | DOZER READINESS | ACTUAL | 20 | 14 |  |  | 46193 | ACTUAL | 100%
DOZER READINESS | PLAN | 21 | 16 | PA ALL DOZER | PLAN | 21 | 90% | MTBF | PLAN | 21 | 70 | MTTR | PLAN | 21 | 80 | PA ALL DOZER | ACHIVE | 10 | 88.89% | DAILY ACHIVEMENT | ACTUAL | 10 | 72% | [48 empty] | 2 | MAN | Quick Action | 12 | 100% | FACTOR | DOZER READINESS | PLAN | 21 | 16 |  |  | 46194 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 21 | 16 | PA ALL DOZER | ACTUAL | 21 | 100% | MTBF | ACTUAL | 21 | 73 | MTTR | ACTUAL | 21 | 73 | PA ALL DOZER | ACHIVE | 11 | 92.22% | DAILY ACHIVEMENT | ACTUAL | 11 | 75% | [48 empty] | 2 | MAN | Quick Action | 13 | 100% | FACTOR | DOZER READINESS | ACTUAL | 21 | 16 |  |  | 46194 | ACTUAL | 100%
DOZER READINESS | PLAN | 22 | 16 | PA ALL DOZER | PLAN | 22 | 90% | MTBF | PLAN | 22 | 70 | MTTR | PLAN | 22 | 80 | PA ALL DOZER | ACHIVE | 12 | 80% | DAILY ACHIVEMENT | ACTUAL | 12 | 78% | [48 empty] | 2 | MAN | Quick Action | 14 | 100% | FACTOR | DOZER READINESS | PLAN | 22 | 16 |  |  | 46195 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 22 | 15 | PA ALL DOZER | ACTUAL | 22 | 90% | MTBF | ACTUAL | 22 | 80 | MTTR | ACTUAL | 22 | 80 | PA ALL DOZER | ACHIVE | 13 | 111.1% | DAILY ACHIVEMENT | ACTUAL | 13 | 81% | [48 empty] | 2 | MAN | Quick Action | 15 | 100% | FACTOR | DOZER READINESS | ACTUAL | 22 | 15 |  |  | 46195 | ACTUAL | 100%
DOZER READINESS | PLAN | 23 | 16 | PA ALL DOZER | PLAN | 23 | 90% | MTBF | PLAN | 23 | 70 | MTTR | PLAN | 23 | 80 | PA ALL DOZER | ACHIVE | 14 | 100% | DAILY ACHIVEMENT | ACTUAL | 14 | 84% | [48 empty] | 2 | MAN | Quick Action | 16 | 100% | FACTOR | DOZER READINESS | PLAN | 23 | 16 |  |  | 46196 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 23 | 13 | PA ALL DOZER | ACTUAL | 23 | 98% | MTBF | ACTUAL | 23 | 60 | MTTR | ACTUAL | 23 | 60 | PA ALL DOZER | ACHIVE | 15 | 108.9% | DAILY ACHIVEMENT | ACTUAL | 15 | 87% | [48 empty] | 2 | MAN | Quick Action | 17 | 100% | FACTOR | DOZER READINESS | ACTUAL | 23 | 13 |  |  | 46196 | ACTUAL | 100%
DOZER READINESS | PLAN | 24 | 16 | PA ALL DOZER | PLAN | 24 | 90% | MTBF | PLAN | 24 | 70 | MTTR | PLAN | 24 | 80 | PA ALL DOZER | ACHIVE | 16 | 103.3% | DAILY ACHIVEMENT | ACTUAL | 16 | 90% | [48 empty] | 2 | MAN | Quick Action | 18 | 100% | FACTOR | DOZER READINESS | PLAN | 24 | 16 |  |  | 46197 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 24 | 14 | PA ALL DOZER | ACTUAL | 24 | 93% | MTBF | ACTUAL | 24 | 50 | MTTR | ACTUAL | 24 | 50 | PA ALL DOZER | ACHIVE | 17 | 96.67% | DAILY ACHIVEMENT | ACTUAL | 17 | 93% | [48 empty] | 2 | MAN | Quick Action | 19 | 100% | FACTOR | DOZER READINESS | ACTUAL | 24 | 14 |  |  | 46197 | ACTUAL | 100%
DOZER READINESS | PLAN | 25 | 16 | PA ALL DOZER | PLAN | 25 | 90% | MTBF | PLAN | 25 | 70 | MTTR | PLAN | 25 | 80 | PA ALL DOZER | ACHIVE | 18 | 88.89% | DAILY ACHIVEMENT | ACTUAL | 18 | 96% | [48 empty] | 2 | MAN | Quick Action | 20 | 100% | FACTOR | DOZER READINESS | PLAN | 25 | 16 |  |  | 46198 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 25 | 11 | PA ALL DOZER | ACTUAL | 25 | 87% | MTBF | ACTUAL | 25 | 75 | MTTR | ACTUAL | 25 | 75 | PA ALL DOZER | ACHIVE | 19 | 92.22% | DAILY ACHIVEMENT | ACTUAL | 19 | 99% | [48 empty] | 2 | MAN | Quick Action | 21 | 100% | FACTOR | DOZER READINESS | ACTUAL | 25 | 11 |  |  | 46198 | ACTUAL | 100%
DOZER READINESS | PLAN | 26 | 16 | PA ALL DOZER | PLAN | 26 | 90% | MTBF | PLAN | 26 | 70 | MTTR | PLAN | 26 | 80 | PA ALL DOZER | ACHIVE | 20 | 80% | DAILY ACHIVEMENT | ACTUAL | 20 | 100% | [48 empty] | 2 | MAN | Quick Action | 22 | 100% | FACTOR | DOZER READINESS | PLAN | 26 | 16 |  |  | 46199 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 26 | 16 | PA ALL DOZER | ACTUAL | 26 | 80% | MTBF | ACTUAL | 26 | 83 | MTTR | ACTUAL | 26 | 83 | PA ALL DOZER | ACHIVE | 21 | 111.1% | DAILY ACHIVEMENT | ACTUAL | 21 | 100% | [48 empty] | 2 | MAN | Quick Action | 23 | 100% | FACTOR | DOZER READINESS | ACTUAL | 26 | 16 |  |  | 46199 | ACTUAL | 100%
DOZER READINESS | PLAN | 27 | 16 | PA ALL DOZER | PLAN | 27 | 90% | MTBF | PLAN | 27 | 70 | MTTR | PLAN | 27 | 80 | PA ALL DOZER | ACHIVE | 22 | 100% | DAILY ACHIVEMENT | ACTUAL | 22 | 100% | [48 empty] | 2 | MAN | Quick Action | 24 | 100% | FACTOR | DOZER READINESS | PLAN | 27 | 16 |  |  | 46200 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 27 | 14 | PA ALL DOZER | ACTUAL | 27 | 83% | MTBF | ACTUAL | 27 | 65 | MTTR | ACTUAL | 27 | 65 | PA ALL DOZER | ACHIVE | 23 | 108.9% | DAILY ACHIVEMENT | ACTUAL | 23 | 100% | [48 empty] | 2 | MAN | Quick Action | 25 | 100% | FACTOR | DOZER READINESS | ACTUAL | 27 | 14 |  |  | 46200 | ACTUAL | 100%
DOZER READINESS | PLAN | 28 | 16 | PA ALL DOZER | PLAN | 28 | 90% | MTBF | PLAN | 28 | 70 | MTTR | PLAN | 28 | 80 | PA ALL DOZER | ACHIVE | 24 | 103.3% | DAILY ACHIVEMENT | ACTUAL | 24 | 100% | [48 empty] | 2 | MAN | Quick Action | 26 | 100% | FACTOR | DOZER READINESS | PLAN | 28 | 16 |  |  | 46201 | PLAN | 50.17%
DOZER READINESS | ACTUAL | 28 | 16 | PA ALL DOZER | ACTUAL | 28 | 72% | MTBF | ACTUAL | 28 | 73 | MTTR | ACTUAL | 28 | 73 | PA ALL DOZER | ACHIVE | 25 | 96.67% | DAILY ACHIVEMENT | ACTUAL | 25 | 100% | [48 empty] | 2 | MAN | Quick Action | 27 | 100% | FACTOR | DOZER READINESS | ACTUAL | 28 | 16 |  |  | 46201 | ACTUAL | 100%
DOZER READINESS | PLAN | 29 | 16 | PA ALL DOZER | PLAN | 29 | 90% | MTBF | PLAN | 29 | 70 | MTTR | PLAN | 29 | 80 | PA ALL DOZER | ACHIVE | 26 | 88.89% | DAILY ACHIVEMENT | ACTUAL | 26 | 100% | [48 empty] | 2 | MAN | Quick Action | 28 | 100% | FACTOR | DOZER READINESS | PLAN | 29 | 16 |  |  | 46202 | PLAN | 51%
DOZER READINESS | ACTUAL | 29 | 12 | PA ALL DOZER | ACTUAL | 29 | 100% | MTBF | ACTUAL | 29 | 75 | MTTR | ACTUAL | 29 | 75 | PA ALL DOZER | ACHIVE | 27 | 92.22% | DAILY ACHIVEMENT | ACTUAL | 27 | 100% | [48 empty] | 2 | MAN | Quick Action | 29 | 100% | FACTOR | DOZER READINESS | ACTUAL | 29 | 12 |  |  | 46202 | ACTUAL | 100%
DOZER READINESS | PLAN | 30 | 16 | PA ALL DOZER | PLAN | 30 | 90% | MTBF | PLAN | 30 | 70 | MTTR | PLAN | 30 | 80 | PA ALL DOZER | ACHIVE | 28 | 80% | DAILY ACHIVEMENT | ACTUAL | 28 | 100% | [48 empty] | 2 | MAN | Quick Action | 30 | 100% | FACTOR | DOZER READINESS | PLAN | 30 | 16 |  |  | 46203 | PLAN | 51.83%
DOZER READINESS | ACTUAL | 30 | 11 | PA ALL DOZER | ACTUAL | 30 | 90% | MTBF | ACTUAL | 30 | 83 | MTTR | ACTUAL | 30 | 83 | PA ALL DOZER | ACHIVE | 29 | 111.1% | DAILY ACHIVEMENT | ACTUAL | 29 | 100% | [48 empty] | 2 | MAN | Quick Action | 31 | 100% | FACTOR | DOZER READINESS | ACTUAL | 30 | 11 |  |  | 46203 | ACTUAL | 100%
DOZER READINESS | PLAN | 31 | #N/A | PA ALL DOZER | PLAN | 31 | #N/A | MTBF | PLAN | 31 | #N/A | MTTR | PLAN | 31 | #N/A | PA ALL DOZER | ACHIVE | 30 | 100% | DAILY ACHIVEMENT | ACTUAL | 30 | 100% | [48 empty] | 3 | MAN | Quick Action | 5 | 0% | FACTOR | DOZER READINESS | PLAN | 31 | #N/A |  |  | 46204 | PLAN | 52.67%
DOZER READINESS | ACTUAL | 31 | #N/A | PA ALL DOZER | ACTUAL | 31 | #N/A | MTBF | ACTUAL | 31 | #N/A | MTTR | ACTUAL | 31 | #N/A | PA ALL DOZER | ACHIVE | 31 | #N/A | DAILY ACHIVEMENT | ACTUAL | 31 | 0% | [48 empty] | 3 | MAN | Quick Action | 6 | 0% | FACTOR | DOZER READINESS | ACTUAL | 31 | #N/A |  |  | 46204 | ACTUAL | N/A
[16 empty] | MTBF | ACHIVE | 1 | 114.3% | [52 empty] | 3 | MAN | Quick Action | 7 | 100% | FACTOR | PA ALL DOZER | PLAN | 1 | 90%
[16 empty] | MTBF | ACHIVE | 2 | 85.71% | [52 empty] | 3 | MAN | Quick Action | 8 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 1 | 87%
[16 empty] | MTBF | ACHIVE | 3 | 71.43% | [52 empty] | 3 | MAN | Quick Action | 9 | 100% | FACTOR | PA ALL DOZER | PLAN | 2 | 90%
[16 empty] | MTBF | ACHIVE | 4 | 107.1% | [52 empty] | 3 | MAN | Quick Action | 10 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 2 | 80%
[16 empty] | MTBF | ACHIVE | 5 | 118.6% | [52 empty] | 3 | MAN | Quick Action | 11 | 100% | FACTOR | PA ALL DOZER | PLAN | 3 | 90%
[16 empty] | MTBF | ACHIVE | 6 | 92.86% | [52 empty] | 3 | MAN | Quick Action | 12 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 3 | 83%
[16 empty] | MTBF | ACHIVE | 7 | 104.3% | [52 empty] | 3 | MAN | Quick Action | 13 | 100% | FACTOR | PA ALL DOZER | PLAN | 4 | 90%
[16 empty] | MTBF | ACHIVE | 8 | 114.3% | [52 empty] | 3 | MAN | Quick Action | 14 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 4 | 72%
[16 empty] | MTBF | ACHIVE | 9 | 85.71% | [52 empty] | 3 | MAN | Quick Action | 15 | 100% | FACTOR | PA ALL DOZER | PLAN | 5 | 90%
[16 empty] | MTBF | ACHIVE | 10 | 71.43% | [52 empty] | 3 | MAN | Quick Action | 16 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 5 | 100%
[16 empty] | MTBF | ACHIVE | 11 | 107.1% | [52 empty] | 3 | MAN | Quick Action | 17 | 100% | FACTOR | PA ALL DOZER | PLAN | 6 | 90%
[16 empty] | MTBF | ACHIVE | 12 | 118.6% | [52 empty] | 3 | MAN | Quick Action | 18 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 6 | 90%
[16 empty] | MTBF | ACHIVE | 13 | 92.86% | [52 empty] | 3 | MAN | Quick Action | 19 | 100% | FACTOR | PA ALL DOZER | PLAN | 7 | 90%
[16 empty] | MTBF | ACHIVE | 14 | 104.3% | [52 empty] | 3 | MAN | Quick Action | 20 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 7 | 98%
[16 empty] | MTBF | ACHIVE | 15 | 114.3% | [52 empty] | 3 | MAN | Quick Action | 21 | 100% | FACTOR | PA ALL DOZER | PLAN | 8 | 90%
[16 empty] | MTBF | ACHIVE | 16 | 85.71% | [52 empty] | 3 | MAN | Quick Action | 22 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 8 | 93%
[16 empty] | MTBF | ACHIVE | 17 | 71.43% | [52 empty] | 3 | MAN | Quick Action | 23 | 100% | FACTOR | PA ALL DOZER | PLAN | 9 | 90%
[16 empty] | MTBF | ACHIVE | 18 | 107.1% | [52 empty] | 3 | MAN | Quick Action | 24 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 9 | 87%
[16 empty] | MTBF | ACHIVE | 19 | 118.6% | [52 empty] | 3 | MAN | Quick Action | 25 | 100% | FACTOR | PA ALL DOZER | PLAN | 10 | 90%
[16 empty] | MTBF | ACHIVE | 20 | 92.86% | [52 empty] | 3 | MAN | Quick Action | 26 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 10 | 80%
[16 empty] | MTBF | ACHIVE | 21 | 104.3% | [52 empty] | 3 | MAN | Quick Action | 27 | 100% | FACTOR | PA ALL DOZER | PLAN | 11 | 90%
[16 empty] | MTBF | ACHIVE | 22 | 114.3% | [52 empty] | 3 | MAN | Quick Action | 28 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 11 | 83%
[16 empty] | MTBF | ACHIVE | 23 | 85.71% | [52 empty] | 3 | MAN | Quick Action | 29 | 100% | FACTOR | PA ALL DOZER | PLAN | 12 | 90%
[16 empty] | MTBF | ACHIVE | 24 | 71.43% | [52 empty] | 3 | MAN | Quick Action | 30 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 12 | 72%
[16 empty] | MTBF | ACHIVE | 25 | 107.1% | [52 empty] | 3 | MAN | Quick Action | 31 | 100% | FACTOR | PA ALL DOZER | PLAN | 13 | 90%
[16 empty] | MTBF | ACHIVE | 26 | 118.6% | [52 empty] | 4 | MAN | Quick Action | 1 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 13 | 100%
[16 empty] | MTBF | ACHIVE | 27 | 92.86% | [52 empty] | 4 | MAN | Quick Action | 2 | 100% | FACTOR | PA ALL DOZER | PLAN | 14 | 90%
[16 empty] | MTBF | ACHIVE | 28 | 104.3% | [52 empty] | 4 | MAN | Quick Action | 3 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 14 | 90%
[16 empty] | MTBF | ACHIVE | 29 | 107.1% | [52 empty] | 4 | MAN | Quick Action | 4 | 100% | FACTOR | PA ALL DOZER | PLAN | 15 | 90%
[16 empty] | MTBF | ACHIVE | 30 | 118.6% | [52 empty] | 4 | MAN | Quick Action | 5 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 15 | 98%
[16 empty] | MTBF | ACHIVE | 31 | #N/A | [52 empty] | 4 | MAN | Quick Action | 6 | 100% | FACTOR | PA ALL DOZER | PLAN | 16 | 90%
[16 empty] | MTTR | ACHIVE | 1 | 100% | [52 empty] | 4 | MAN | Quick Action | 7 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 16 | 93%
[16 empty] | MTTR | ACHIVE | 2 | 75% | [52 empty] | 4 | MAN | Quick Action | 8 | 100% | FACTOR | PA ALL DOZER | PLAN | 17 | 90%
[16 empty] | MTTR | ACHIVE | 3 | 62.5% | [52 empty] | 4 | MAN | Quick Action | 9 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 17 | 87%
[16 empty] | MTTR | ACHIVE | 4 | 93.75% | [52 empty] | 4 | MAN | Quick Action | 10 | 100% | FACTOR | PA ALL DOZER | PLAN | 18 | 90%
[16 empty] | MTTR | ACHIVE | 5 | 103.8% | [52 empty] | 4 | MAN | Quick Action | 11 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 18 | 80%
[16 empty] | MTTR | ACHIVE | 6 | 81.25% | [52 empty] | 4 | MAN | Quick Action | 12 | 100% | FACTOR | PA ALL DOZER | PLAN | 19 | 90%
[16 empty] | MTTR | ACHIVE | 7 | 91.25% | [52 empty] | 4 | MAN | Quick Action | 13 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 19 | 83%
[16 empty] | MTTR | ACHIVE | 8 | 100% | [52 empty] | 4 | MAN | Quick Action | 14 | 100% | FACTOR | PA ALL DOZER | PLAN | 20 | 90%
[16 empty] | MTTR | ACHIVE | 9 | 75% | [52 empty] | 4 | MAN | Quick Action | 15 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 20 | 72%
[16 empty] | MTTR | ACHIVE | 10 | 62.5% | [52 empty] | 4 | MAN | Quick Action | 16 | 100% | FACTOR | PA ALL DOZER | PLAN | 21 | 90%
[16 empty] | MTTR | ACHIVE | 11 | 93.75% | [52 empty] | 4 | MAN | Quick Action | 17 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 21 | 100%
[16 empty] | MTTR | ACHIVE | 12 | 103.8% | [52 empty] | 4 | MAN | Quick Action | 18 | 100% | FACTOR | PA ALL DOZER | PLAN | 22 | 90%
[16 empty] | MTTR | ACHIVE | 13 | 81.25% | [52 empty] | 4 | MAN | Quick Action | 19 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 22 | 90%
[16 empty] | MTTR | ACHIVE | 14 | 91.25% | [52 empty] | 4 | MAN | Quick Action | 20 | 100% | FACTOR | PA ALL DOZER | PLAN | 23 | 90%
[16 empty] | MTTR | ACHIVE | 15 | 100% | [52 empty] | 4 | MAN | Quick Action | 21 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 23 | 98%
[16 empty] | MTTR | ACHIVE | 16 | 75% | [52 empty] | 4 | MAN | Quick Action | 22 | 100% | FACTOR | PA ALL DOZER | PLAN | 24 | 90%
[16 empty] | MTTR | ACHIVE | 17 | 62.5% | [52 empty] | 4 | MAN | Quick Action | 23 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 24 | 93%
[16 empty] | MTTR | ACHIVE | 18 | 93.75% | [52 empty] | 4 | MAN | Quick Action | 24 | 100% | FACTOR | PA ALL DOZER | PLAN | 25 | 90%
[16 empty] | MTTR | ACHIVE | 19 | 103.8% | [52 empty] | 4 | MAN | Quick Action | 25 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 25 | 87%
[16 empty] | MTTR | ACHIVE | 20 | 81.25% | [52 empty] | 4 | MAN | Quick Action | 26 | 100% | FACTOR | PA ALL DOZER | PLAN | 26 | 90%
[16 empty] | MTTR | ACHIVE | 21 | 91.25% | [52 empty] | 4 | MAN | Quick Action | 27 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 26 | 80%
[16 empty] | MTTR | ACHIVE | 22 | 100% | [52 empty] | 4 | MAN | Quick Action | 28 | 100% | FACTOR | PA ALL DOZER | PLAN | 27 | 90%
[16 empty] | MTTR | ACHIVE | 23 | 75% | [52 empty] | 4 | MAN | Quick Action | 29 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 27 | 83%
[16 empty] | MTTR | ACHIVE | 24 | 62.5% | [52 empty] | 4 | MAN | Quick Action | 30 | 100% | FACTOR | PA ALL DOZER | PLAN | 28 | 90%
[16 empty] | MTTR | ACHIVE | 25 | 93.75% | [52 empty] | 4 | MAN | Quick Action | 31 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 28 | 72%
[16 empty] | MTTR | ACHIVE | 26 | 103.8% | [52 empty] | 5 | MAN | Long Term / Development | 3 | 100% | FACTOR | PA ALL DOZER | PLAN | 29 | 90%
[16 empty] | MTTR | ACHIVE | 27 | 81.25% | [52 empty] | 5 | MAN | Long Term / Development | 4 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 29 | 100%
[16 empty] | MTTR | ACHIVE | 28 | 91.25% | [52 empty] | 5 | MAN | Long Term / Development | 5 | 100% | FACTOR | PA ALL DOZER | PLAN | 30 | 90%
[16 empty] | MTTR | ACHIVE | 29 | 93.75% | [52 empty] | 5 | MAN | Long Term / Development | 6 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 30 | 90%
[16 empty] | MTTR | ACHIVE | 30 | 103.8% | [52 empty] | 5 | MAN | Long Term / Development | 7 | 100% | FACTOR | PA ALL DOZER | PLAN | 31 | #N/A
[16 empty] | MTTR | ACHIVE | 31 | #N/A | [52 empty] | 5 | MAN | Long Term / Development | 8 | 100% | FACTOR | PA ALL DOZER | ACTUAL | 31 | #N/A
[72 empty] | 5 | MAN | Long Term / Development | 9 | 100% | FACTOR | MTBF | PLAN | 1 | 70
[72 empty] | 5 | MAN | Long Term / Development | 10 | 100% | FACTOR | MTBF | ACTUAL | 1 | 80
[72 empty] | 5 | MAN | Long Term / Development | 11 | 100% | FACTOR | MTBF | PLAN | 2 | 70
[72 empty] | 5 | MAN | Long Term / Development | 12 | 100% | FACTOR | MTBF | ACTUAL | 2 | 60
[72 empty] | 5 | MAN | Long Term / Development | 13 | 100% | FACTOR | MTBF | PLAN | 3 | 70
[72 empty] | 5 | MAN | Long Term / Development | 14 | 100% | FACTOR | MTBF | ACTUAL | 3 | 50
[72 empty] | 5 | MAN | Long Term / Development | 15 | 100% | FACTOR | MTBF | PLAN | 4 | 70
[72 empty] | 5 | MAN | Long Term / Development | 16 | 100% | FACTOR | MTBF | ACTUAL | 4 | 75
[72 empty] | 5 | MAN | Long Term / Development | 17 | 100% | FACTOR | MTBF | PLAN | 5 | 70
[72 empty] | 5 | MAN | Long Term / Development | 18 | 100% | FACTOR | MTBF | ACTUAL | 5 | 83
[72 empty] | 5 | MAN | Long Term / Development | 19 | 100% | FACTOR | MTBF | PLAN | 6 | 70
[72 empty] | 5 | MAN | Long Term / Development | 20 | 100% | FACTOR | MTBF | ACTUAL | 6 | 65
[72 empty] | 5 | MAN | Long Term / Development | 21 | 100% | FACTOR | MTBF | PLAN | 7 | 70
[72 empty] | 5 | MAN | Long Term / Development | 22 | 100% | FACTOR | MTBF | ACTUAL | 7 | 73
[72 empty] | 5 | MAN | Long Term / Development | 23 | 100% | FACTOR | MTBF | PLAN | 8 | 70
[72 empty] | 5 | MAN | Long Term / Development | 24 | 100% | FACTOR | MTBF | ACTUAL | 8 | 80
[72 empty] | 5 | MAN | Long Term / Development | 25 | 100% | FACTOR | MTBF | PLAN | 9 | 70
[72 empty] | 5 | MAN | Long Term / Development | 26 | 100% | FACTOR | MTBF | ACTUAL | 9 | 60
[72 empty] | 5 | MAN | Long Term / Development | 27 | 100% | FACTOR | MTBF | PLAN | 10 | 70
[72 empty] | 5 | MAN | Long Term / Development | 28 | 100% | FACTOR | MTBF | ACTUAL | 10 | 50
[72 empty] | 5 | MAN | Long Term / Development | 29 | 100% | FACTOR | MTBF | PLAN | 11 | 70
[72 empty] | 5 | MAN | Long Term / Development | 30 | 100% | FACTOR | MTBF | ACTUAL | 11 | 75
[72 empty] | 5 | MAN | Long Term / Development | 31 | 100% | FACTOR | MTBF | PLAN | 12 | 70
[72 empty] | 6 | MAN | Long Term / Development | 2 | 0% | FACTOR | MTBF | ACTUAL | 12 | 83
[72 empty] | 6 | MAN | Long Term / Development | 3 | 0% | FACTOR | MTBF | PLAN | 13 | 70
[72 empty] | 6 | MAN | Long Term / Development | 4 | 0% | FACTOR | MTBF | ACTUAL | 13 | 65
[72 empty] | 6 | MAN | Long Term / Development | 5 | 100% | FACTOR | MTBF | PLAN | 14 | 70
[72 empty] | 6 | MAN | Long Term / Development | 6 | 100% | FACTOR | MTBF | ACTUAL | 14 | 73
[72 empty] | 6 | MAN | Long Term / Development | 7 | 100% | FACTOR | MTBF | PLAN | 15 | 70
[72 empty] | 6 | MAN | Long Term / Development | 8 | 100% | FACTOR | MTBF | ACTUAL | 15 | 80
[72 empty] | 6 | MAN | Long Term / Development | 9 | 100% | FACTOR | MTBF | PLAN | 16 | 70
[72 empty] | 6 | MAN | Long Term / Development | 10 | 100% | FACTOR | MTBF | ACTUAL | 16 | 60
[72 empty] | 6 | MAN | Long Term / Development | 11 | 100% | FACTOR | MTBF | PLAN | 17 | 70
[72 empty] | 6 | MAN | Long Term / Development | 12 | 100% | FACTOR | MTBF | ACTUAL | 17 | 50
[72 empty] | 6 | MAN | Long Term / Development | 13 | 100% | FACTOR | MTBF | PLAN | 18 | 70
[72 empty] | 6 | MAN | Long Term / Development | 14 | 100% | FACTOR | MTBF | ACTUAL | 18 | 75
[72 empty] | 6 | MAN | Long Term / Development | 15 | 100% | FACTOR | MTBF | PLAN | 19 | 70
[72 empty] | 6 | MAN | Long Term / Development | 16 | 100% | FACTOR | MTBF | ACTUAL | 19 | 83
[72 empty] | 6 | MAN | Long Term / Development | 17 | 100% | FACTOR | MTBF | PLAN | 20 | 70
[72 empty] | 6 | MAN | Long Term / Development | 18 | 100% | FACTOR | MTBF | ACTUAL | 20 | 65
[72 empty] | 6 | MAN | Long Term / Development | 19 | 100% | FACTOR | MTBF | PLAN | 21 | 70
[72 empty] | 6 | MAN | Long Term / Development | 20 | 100% | FACTOR | MTBF | ACTUAL | 21 | 73
[72 empty] | 6 | MAN | Long Term / Development | 21 | 100% | FACTOR | MTBF | PLAN | 22 | 70
[72 empty] | 6 | MAN | Long Term / Development | 22 | 100% | FACTOR | MTBF | ACTUAL | 22 | 80
[72 empty] | 6 | MAN | Long Term / Development | 23 | 100% | FACTOR | MTBF | PLAN | 23 | 70
[72 empty] | 6 | MAN | Long Term / Development | 24 | 100% | FACTOR | MTBF | ACTUAL | 23 | 60
[72 empty] | 6 | MAN | Long Term / Development | 25 | 100% | FACTOR | MTBF | PLAN | 24 | 70
[72 empty] | 6 | MAN | Long Term / Development | 26 | 100% | FACTOR | MTBF | ACTUAL | 24 | 50
[72 empty] | 6 | MAN | Long Term / Development | 27 | 100% | FACTOR | MTBF | PLAN | 25 | 70
[72 empty] | 6 | MAN | Long Term / Development | 28 | 100% | FACTOR | MTBF | ACTUAL | 25 | 75
[72 empty] | 6 | MAN | Long Term / Development | 29 | 100% | FACTOR | MTBF | PLAN | 26 | 70
[72 empty] | 6 | MAN | Long Term / Development | 30 | 100% | FACTOR | MTBF | ACTUAL | 26 | 83
[72 empty] | 6 | MAN | Long Term / Development | 31 | 100% | FACTOR | MTBF | PLAN | 27 | 70
[72 empty] | 7 | MAN | Long Term / Development | 1 | 0% | FACTOR | MTBF | ACTUAL | 27 | 65
[72 empty] | 7 | MAN | Long Term / Development | 2 | 0% | FACTOR | MTBF | PLAN | 28 | 70
[72 empty] | 7 | MAN | Long Term / Development | 3 | 0% | FACTOR | MTBF | ACTUAL | 28 | 73
[72 empty] | 7 | MAN | Long Term / Development | 4 | 0% | FACTOR | MTBF | PLAN | 29 | 70
[72 empty] | 7 | MAN | Long Term / Development | 5 | 0% | FACTOR | MTBF | ACTUAL | 29 | 75
[72 empty] | 7 | MAN | Long Term / Development | 6 | 0% | FACTOR | MTBF | PLAN | 30 | 70
[72 empty] | 7 | MAN | Long Term / Development | 7 | 0% | FACTOR | MTBF | ACTUAL | 30 | 83
[72 empty] | 7 | MAN | Long Term / Development | 8 | 0% | FACTOR | MTBF | PLAN | 31 | #N/A
[72 empty] | 7 | MAN | Long Term / Development | 9 | 100% | FACTOR | MTBF | ACTUAL | 31 | #N/A
[72 empty] | 7 | MAN | Long Term / Development | 10 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 1 | 5%
[72 empty] | 7 | MAN | Long Term / Development | 11 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 2 | 8%
[72 empty] | 7 | MAN | Long Term / Development | 12 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 3 | 10%
[72 empty] | 7 | MAN | Long Term / Development | 13 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 4 | 12.67%
[72 empty] | 7 | MAN | Long Term / Development | 14 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 5 | 15.17%
[72 empty] | 7 | MAN | Long Term / Development | 15 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 6 | 17.67%
[72 empty] | 7 | MAN | Long Term / Development | 16 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 7 | 20.17%
[72 empty] | 7 | MAN | Long Term / Development | 17 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 8 | 22.67%
[72 empty] | 7 | MAN | Long Term / Development | 18 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 9 | 25.17%
[72 empty] | 7 | MAN | Long Term / Development | 19 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 10 | 27.67%
[72 empty] | 7 | MAN | Long Term / Development | 20 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 11 | 30.17%
[72 empty] | 7 | MAN | Long Term / Development | 21 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 12 | 32.67%
[72 empty] | 7 | MAN | Long Term / Development | 22 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 13 | 35.17%
[72 empty] | 7 | MAN | Long Term / Development | 23 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 14 | 37.67%
[72 empty] | 7 | MAN | Long Term / Development | 24 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 15 | 40.17%
[72 empty] | 7 | MAN | Long Term / Development | 25 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 16 | 42.67%
[72 empty] | 7 | MAN | Long Term / Development | 26 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 17 | 45.17%
[72 empty] | 7 | MAN | Long Term / Development | 27 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 18 | 47.67%
[72 empty] | 7 | MAN | Long Term / Development | 28 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 19 | 50.17%
[72 empty] | 7 | MAN | Long Term / Development | 29 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 20 | 50.17%
[72 empty] | 7 | MAN | Long Term / Development | 30 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 21 | 50.17%
[72 empty] | 7 | MAN | Long Term / Development | 31 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 22 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 3 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 23 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 4 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 24 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 5 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 25 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 6 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 26 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 7 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 27 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 8 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 28 | 50.17%
[72 empty] | 8 | MAN | Long Term / Development | 9 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 29 | 51%
[72 empty] | 8 | MAN | Long Term / Development | 10 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 30 | 51.83%
[72 empty] | 8 | MAN | Long Term / Development | 11 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | PLAN | 31 | 52.67%
[72 empty] | 8 | MAN | Long Term / Development | 12 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 1 | 53.5%
[72 empty] | 8 | MAN | Long Term / Development | 13 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 2 | 54.33%
[72 empty] | 8 | MAN | Long Term / Development | 14 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 3 | 55.17%
[72 empty] | 8 | MAN | Long Term / Development | 15 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 4 | 56%
[72 empty] | 8 | MAN | Long Term / Development | 16 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 5 | 56.83%
[72 empty] | 8 | MAN | Long Term / Development | 17 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 6 | 60%
[72 empty] | 8 | MAN | Long Term / Development | 18 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 7 | 63%
[72 empty] | 8 | MAN | Long Term / Development | 19 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 8 | 66%
[72 empty] | 8 | MAN | Long Term / Development | 20 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 9 | 69%
[72 empty] | 8 | MAN | Long Term / Development | 21 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 10 | 72%
[72 empty] | 8 | MAN | Long Term / Development | 22 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 11 | 75%
[72 empty] | 8 | MAN | Long Term / Development | 23 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 12 | 78%
[72 empty] | 8 | MAN | Long Term / Development | 24 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 13 | 81%
[72 empty] | 8 | MAN | Long Term / Development | 25 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 14 | 84%
[72 empty] | 8 | MAN | Long Term / Development | 26 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 15 | 87%
[72 empty] | 8 | MAN | Long Term / Development | 27 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 16 | 90%
[72 empty] | 8 | MAN | Long Term / Development | 28 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 17 | 93%
[72 empty] | 8 | MAN | Long Term / Development | 29 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 18 | 96%
[72 empty] | 8 | MAN | Long Term / Development | 30 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 19 | 99%
[72 empty] | 8 | MAN | Long Term / Development | 31 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 20 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 1 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 21 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 2 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 22 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 3 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 23 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 4 | 0% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 24 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 5 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 25 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 6 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 26 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 7 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 27 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 8 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 28 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 9 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 29 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 10 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 30 | 100%
[72 empty] | 9 | MAN | Long Term / Development | 11 | 100% | ACHIVEMENT | DAILY ACHIVEMENT | ACTUAL | 31 | 0%
[72 empty] | 9 | MAN | Long Term / Development | 12 | 100% | FACTOR | MTTR | PLAN | 1 | 80
[72 empty] | 9 | MAN | Long Term / Development | 13 | 100% | FACTOR | MTTR | ACTUAL | 1 | 80
[72 empty] | 9 | MAN | Long Term / Development | 14 | 100% | FACTOR | MTTR | PLAN | 2 | 80
[72 empty] | 9 | MAN | Long Term / Development | 15 | 100% | FACTOR | MTTR | ACTUAL | 2 | 60
[72 empty] | 9 | MAN | Long Term / Development | 16 | 100% | FACTOR | MTTR | PLAN | 3 | 80
[72 empty] | 9 | MAN | Long Term / Development | 17 | 100% | FACTOR | MTTR | ACTUAL | 3 | 50
[72 empty] | 9 | MAN | Long Term / Development | 18 | 100% | FACTOR | MTTR | PLAN | 4 | 80
[72 empty] | 9 | MAN | Long Term / Development | 19 | 100% | FACTOR | MTTR | ACTUAL | 4 | 75
[72 empty] | 9 | MAN | Long Term / Development | 20 | 100% | FACTOR | MTTR | PLAN | 5 | 80
[72 empty] | 9 | MAN | Long Term / Development | 21 | 100% | FACTOR | MTTR | ACTUAL | 5 | 83
[72 empty] | 9 | MAN | Long Term / Development | 22 | 100% | FACTOR | MTTR | PLAN | 6 | 80
[72 empty] | 9 | MAN | Long Term / Development | 23 | 100% | FACTOR | MTTR | ACTUAL | 6 | 65
[72 empty] | 9 | MAN | Long Term / Development | 24 | 100% | FACTOR | MTTR | PLAN | 7 | 80
[72 empty] | 9 | MAN | Long Term / Development | 25 | 100% | FACTOR | MTTR | ACTUAL | 7 | 73
[72 empty] | 9 | MAN | Long Term / Development | 26 | 100% | FACTOR | MTTR | PLAN | 8 | 80
[72 empty] | 9 | MAN | Long Term / Development | 27 | 100% | FACTOR | MTTR | ACTUAL | 8 | 80
[72 empty] | 9 | MAN | Long Term / Development | 28 | 100% | FACTOR | MTTR | PLAN | 9 | 80
[72 empty] | 9 | MAN | Long Term / Development | 29 | 100% | FACTOR | MTTR | ACTUAL | 9 | 60
[72 empty] | 9 | MAN | Long Term / Development | 30 | 100% | FACTOR | MTTR | PLAN | 10 | 80
[72 empty] | 9 | MAN | Long Term / Development | 31 | 100% | FACTOR | MTTR | ACTUAL | 10 | 50
[72 empty] | 10 | MATERIAL | Quick Action | 6 | 0% | FACTOR | MTTR | PLAN | 11 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 7 | 100% | FACTOR | MTTR | ACTUAL | 11 | 75
[72 empty] | 10 | MATERIAL | Quick Action | 8 | 100% | FACTOR | MTTR | PLAN | 12 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 9 | 100% | FACTOR | MTTR | ACTUAL | 12 | 83
[72 empty] | 10 | MATERIAL | Quick Action | 10 | 100% | FACTOR | MTTR | PLAN | 13 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 11 | 100% | FACTOR | MTTR | ACTUAL | 13 | 65
[72 empty] | 10 | MATERIAL | Quick Action | 12 | 100% | FACTOR | MTTR | PLAN | 14 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 13 | 100% | FACTOR | MTTR | ACTUAL | 14 | 73
[72 empty] | 10 | MATERIAL | Quick Action | 14 | 100% | FACTOR | MTTR | PLAN | 15 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 15 | 100% | FACTOR | MTTR | ACTUAL | 15 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 16 | 100% | FACTOR | MTTR | PLAN | 16 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 17 | 100% | FACTOR | MTTR | ACTUAL | 16 | 60
[72 empty] | 10 | MATERIAL | Quick Action | 18 | 100% | FACTOR | MTTR | PLAN | 17 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 19 | 100% | FACTOR | MTTR | ACTUAL | 17 | 50
[72 empty] | 10 | MATERIAL | Quick Action | 20 | 100% | FACTOR | MTTR | PLAN | 18 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 21 | 100% | FACTOR | MTTR | ACTUAL | 18 | 75
[72 empty] | 10 | MATERIAL | Quick Action | 22 | 100% | FACTOR | MTTR | PLAN | 19 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 23 | 100% | FACTOR | MTTR | ACTUAL | 19 | 83
[72 empty] | 10 | MATERIAL | Quick Action | 24 | 100% | FACTOR | MTTR | PLAN | 20 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 25 | 100% | FACTOR | MTTR | ACTUAL | 20 | 65
[72 empty] | 10 | MATERIAL | Quick Action | 26 | 100% | FACTOR | MTTR | PLAN | 21 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 27 | 100% | FACTOR | MTTR | ACTUAL | 21 | 73
[72 empty] | 10 | MATERIAL | Quick Action | 28 | 100% | FACTOR | MTTR | PLAN | 22 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 29 | 100% | FACTOR | MTTR | ACTUAL | 22 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 30 | 100% | FACTOR | MTTR | PLAN | 23 | 80
[72 empty] | 10 | MATERIAL | Quick Action | 31 | 100% | FACTOR | MTTR | ACTUAL | 23 | 60
[72 empty] | 11 | MATERIAL | Quick Action | 6 | 0% | FACTOR | MTTR | PLAN | 24 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 7 | 100% | FACTOR | MTTR | ACTUAL | 24 | 50
[72 empty] | 11 | MATERIAL | Quick Action | 8 | 100% | FACTOR | MTTR | PLAN | 25 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 9 | 100% | FACTOR | MTTR | ACTUAL | 25 | 75
[72 empty] | 11 | MATERIAL | Quick Action | 10 | 100% | FACTOR | MTTR | PLAN | 26 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 11 | 100% | FACTOR | MTTR | ACTUAL | 26 | 83
[72 empty] | 11 | MATERIAL | Quick Action | 12 | 100% | FACTOR | MTTR | PLAN | 27 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 13 | 100% | FACTOR | MTTR | ACTUAL | 27 | 65
[72 empty] | 11 | MATERIAL | Quick Action | 14 | 100% | FACTOR | MTTR | PLAN | 28 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 15 | 100% | FACTOR | MTTR | ACTUAL | 28 | 73
[72 empty] | 11 | MATERIAL | Quick Action | 16 | 100% | FACTOR | MTTR | PLAN | 29 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 17 | 100% | FACTOR | MTTR | ACTUAL | 29 | 75
[72 empty] | 11 | MATERIAL | Quick Action | 18 | 100% | FACTOR | MTTR | PLAN | 30 | 80
[72 empty] | 11 | MATERIAL | Quick Action | 19 | 100% | FACTOR | MTTR | ACTUAL | 30 | 83
[72 empty] | 11 | MATERIAL | Quick Action | 20 | 100% | FACTOR | MTTR | PLAN | 31 | #N/A
[72 empty] | 11 | MATERIAL | Quick Action | 21 | 100% | FACTOR | MTTR | ACTUAL | 31 | #N/A
[72 empty] | 11 | MATERIAL | Quick Action | 22 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 23 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 24 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 25 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 26 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 27 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 28 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 29 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 30 | 100%
[72 empty] | 11 | MATERIAL | Quick Action | 31 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 6 | 0%
[72 empty] | 12 | MATERIAL | Quick Action | 7 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 8 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 9 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 10 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 11 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 12 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 13 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 14 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 15 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 16 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 17 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 18 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 19 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 20 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 21 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 22 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 23 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 24 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 25 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 26 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 27 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 28 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 29 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 30 | 100%
[72 empty] | 12 | MATERIAL | Quick Action | 31 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 6 | 0%
[72 empty] | 13 | MATERIAL | Quick Action | 7 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 8 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 9 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 10 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 11 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 12 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 13 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 14 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 15 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 16 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 17 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 18 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 19 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 20 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 21 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 22 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 23 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 24 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 25 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 26 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 27 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 28 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 29 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 30 | 100%
[72 empty] | 13 | MATERIAL | Quick Action | 31 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 6 | 0%
[72 empty] | 14 | MATERIAL | Quick Action | 7 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 8 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 9 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 10 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 11 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 12 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 13 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 14 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 15 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 16 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 17 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 18 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 19 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 20 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 21 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 22 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 23 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 24 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 25 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 26 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 27 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 28 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 29 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 30 | 100%
[72 empty] | 14 | MATERIAL | Quick Action | 31 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 6 | 0%
[72 empty] | 15 | MATERIAL | Long Term / Development | 7 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 8 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 9 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 10 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 11 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 12 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 13 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 14 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 15 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 16 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 17 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 18 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 19 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 20 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 21 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 22 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 23 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 24 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 25 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 26 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 27 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 28 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 29 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 30 | 100%
[72 empty] | 15 | MATERIAL | Long Term / Development | 31 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 4 | 0%
[72 empty] | 16 | MACHINE | Quick Action | 5 | 0%
[72 empty] | 16 | MACHINE | Quick Action | 6 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 7 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 8 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 9 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 10 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 11 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 12 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 13 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 14 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 15 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 16 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 17 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 18 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 19 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 20 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 21 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 22 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 23 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 24 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 25 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 26 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 27 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 28 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 29 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 30 | 100%
[72 empty] | 16 | MACHINE | Quick Action | 31 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 4 | 0%
[72 empty] | 17 | MACHINE | Long Term / Development | 5 | 0%
[72 empty] | 17 | MACHINE | Long Term / Development | 6 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 7 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 8 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 9 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 10 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 11 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 12 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 13 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 14 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 15 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 16 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 17 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 18 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 19 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 20 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 21 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 22 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 23 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 24 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 25 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 26 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 27 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 28 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 29 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 30 | 100%
[72 empty] | 17 | MACHINE | Long Term / Development | 31 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 4 | 0%
[72 empty] | 18 | MACHINE | Quick Action | 5 | 0%
[72 empty] | 18 | MACHINE | Quick Action | 6 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 7 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 8 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 9 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 10 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 11 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 12 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 13 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 14 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 15 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 16 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 17 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 18 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 19 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 20 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 21 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 22 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 23 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 24 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 25 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 26 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 27 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 28 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 29 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 30 | 100%
[72 empty] | 18 | MACHINE | Quick Action | 31 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 4 | 0%
[72 empty] | 19 | MACHINE | Quick Action | 5 | 0%
[72 empty] | 19 | MACHINE | Quick Action | 6 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 7 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 8 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 9 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 10 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 11 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 12 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 13 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 14 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 15 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 16 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 17 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 18 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 19 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 20 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 21 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 22 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 23 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 24 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 25 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 26 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 27 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 28 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 29 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 30 | 100%
[72 empty] | 19 | MACHINE | Quick Action | 31 | 100%
[72 empty] | 20 | METHOD | Quick Action | 1 | 0%
[72 empty] | 20 | METHOD | Quick Action | 2 | 0%
[72 empty] | 20 | METHOD | Quick Action | 3 | 100%
[72 empty] | 20 | METHOD | Quick Action | 4 | 100%
[72 empty] | 20 | METHOD | Quick Action | 5 | 100%
[72 empty] | 20 | METHOD | Quick Action | 6 | 100%
[72 empty] | 20 | METHOD | Quick Action | 7 | 100%
[72 empty] | 20 | METHOD | Quick Action | 8 | 100%
[72 empty] | 20 | METHOD | Quick Action | 9 | 100%
[72 empty] | 20 | METHOD | Quick Action | 10 | 100%
[72 empty] | 20 | METHOD | Quick Action | 11 | 100%
[72 empty] | 20 | METHOD | Quick Action | 12 | 100%
[72 empty] | 20 | METHOD | Quick Action | 13 | 100%
[72 empty] | 20 | METHOD | Quick Action | 14 | 100%
[72 empty] | 20 | METHOD | Quick Action | 15 | 100%
[72 empty] | 20 | METHOD | Quick Action | 16 | 100%
[72 empty] | 20 | METHOD | Quick Action | 17 | 100%
[72 empty] | 20 | METHOD | Quick Action | 18 | 100%
[72 empty] | 20 | METHOD | Quick Action | 19 | 100%
[72 empty] | 20 | METHOD | Quick Action | 20 | 100%
[72 empty] | 20 | METHOD | Quick Action | 21 | 100%
[72 empty] | 20 | METHOD | Quick Action | 22 | 100%
[72 empty] | 20 | METHOD | Quick Action | 23 | 100%
[72 empty] | 20 | METHOD | Quick Action | 24 | 100%
[72 empty] | 20 | METHOD | Quick Action | 25 | 100%
[72 empty] | 20 | METHOD | Quick Action | 26 | 100%
[72 empty] | 20 | METHOD | Quick Action | 27 | 100%
[72 empty] | 20 | METHOD | Quick Action | 28 | 100%
[72 empty] | 20 | METHOD | Quick Action | 29 | 100%
[72 empty] | 20 | METHOD | Quick Action | 30 | 100%
[72 empty] | 20 | METHOD | Quick Action | 31 | 100%
[72 empty] | 21 | METHOD | Quick Action | 1 | 0%
[72 empty] | 21 | METHOD | Quick Action | 2 | 0%
[72 empty] | 21 | METHOD | Quick Action | 3 | 100%
[72 empty] | 21 | METHOD | Quick Action | 4 | 100%
[72 empty] | 21 | METHOD | Quick Action | 5 | 100%
[72 empty] | 21 | METHOD | Quick Action | 6 | 100%
[72 empty] | 21 | METHOD | Quick Action | 7 | 100%
[72 empty] | 21 | METHOD | Quick Action | 8 | 100%
[72 empty] | 21 | METHOD | Quick Action | 9 | 100%
[72 empty] | 21 | METHOD | Quick Action | 10 | 100%
[72 empty] | 21 | METHOD | Quick Action | 11 | 100%
[72 empty] | 21 | METHOD | Quick Action | 12 | 100%
[72 empty] | 21 | METHOD | Quick Action | 13 | 100%
[72 empty] | 21 | METHOD | Quick Action | 14 | 100%
[72 empty] | 21 | METHOD | Quick Action | 15 | 100%
[72 empty] | 21 | METHOD | Quick Action | 16 | 100%
[72 empty] | 21 | METHOD | Quick Action | 17 | 100%
[72 empty] | 21 | METHOD | Quick Action | 18 | 100%
[72 empty] | 21 | METHOD | Quick Action | 19 | 100%
[72 empty] | 21 | METHOD | Quick Action | 20 | 100%
[72 empty] | 21 | METHOD | Quick Action | 21 | 100%
[72 empty] | 21 | METHOD | Quick Action | 22 | 100%
[72 empty] | 21 | METHOD | Quick Action | 23 | 100%
[72 empty] | 21 | METHOD | Quick Action | 24 | 100%
[72 empty] | 21 | METHOD | Quick Action | 25 | 100%
[72 empty] | 21 | METHOD | Quick Action | 26 | 100%
[72 empty] | 21 | METHOD | Quick Action | 27 | 100%
[72 empty] | 21 | METHOD | Quick Action | 28 | 100%
[72 empty] | 21 | METHOD | Quick Action | 29 | 100%
[72 empty] | 21 | METHOD | Quick Action | 30 | 100%
[72 empty] | 21 | METHOD | Quick Action | 31 | 100%
[72 empty] | 22 | METHOD | Quick Action | 1 | 0%
[72 empty] | 22 | METHOD | Quick Action | 2 | 0%
[72 empty] | 22 | METHOD | Quick Action | 3 | 100%
[72 empty] | 22 | METHOD | Quick Action | 4 | 100%
[72 empty] | 22 | METHOD | Quick Action | 5 | 100%
[72 empty] | 22 | METHOD | Quick Action | 6 | 100%
[72 empty] | 22 | METHOD | Quick Action | 7 | 100%
[72 empty] | 22 | METHOD | Quick Action | 8 | 100%
[72 empty] | 22 | METHOD | Quick Action | 9 | 100%
[72 empty] | 22 | METHOD | Quick Action | 10 | 100%
[72 empty] | 22 | METHOD | Quick Action | 11 | 100%
[72 empty] | 22 | METHOD | Quick Action | 12 | 100%
[72 empty] | 22 | METHOD | Quick Action | 13 | 100%
[72 empty] | 22 | METHOD | Quick Action | 14 | 100%
[72 empty] | 22 | METHOD | Quick Action | 15 | 100%
[72 empty] | 22 | METHOD | Quick Action | 16 | 100%
[72 empty] | 22 | METHOD | Quick Action | 17 | 100%
[72 empty] | 22 | METHOD | Quick Action | 18 | 100%
[72 empty] | 22 | METHOD | Quick Action | 19 | 100%
[72 empty] | 22 | METHOD | Quick Action | 20 | 100%
[72 empty] | 22 | METHOD | Quick Action | 21 | 100%
[72 empty] | 22 | METHOD | Quick Action | 22 | 100%
[72 empty] | 22 | METHOD | Quick Action | 23 | 100%
[72 empty] | 22 | METHOD | Quick Action | 24 | 100%
[72 empty] | 22 | METHOD | Quick Action | 25 | 100%
[72 empty] | 22 | METHOD | Quick Action | 26 | 100%
[72 empty] | 22 | METHOD | Quick Action | 27 | 100%
[72 empty] | 22 | METHOD | Quick Action | 28 | 100%
[72 empty] | 22 | METHOD | Quick Action | 29 | 100%
[72 empty] | 22 | METHOD | Quick Action | 30 | 100%
[72 empty] | 22 | METHOD | Quick Action | 31 | 100%
[72 empty] | 23 | METHOD | Quick Action | 1 | 0%
[72 empty] | 23 | METHOD | Quick Action | 2 | 0%
[72 empty] | 23 | METHOD | Quick Action | 3 | 100%
[72 empty] | 23 | METHOD | Quick Action | 4 | 100%
[72 empty] | 23 | METHOD | Quick Action | 5 | 100%
[72 empty] | 23 | METHOD | Quick Action | 6 | 100%
[72 empty] | 23 | METHOD | Quick Action | 7 | 100%
[72 empty] | 23 | METHOD | Quick Action | 8 | 100%
[72 empty] | 23 | METHOD | Quick Action | 9 | 100%
[72 empty] | 23 | METHOD | Quick Action | 10 | 100%
[72 empty] | 23 | METHOD | Quick Action | 11 | 100%
[72 empty] | 23 | METHOD | Quick Action | 12 | 100%
[72 empty] | 23 | METHOD | Quick Action | 13 | 100%
[72 empty] | 23 | METHOD | Quick Action | 14 | 100%
[72 empty] | 23 | METHOD | Quick Action | 15 | 100%
[72 empty] | 23 | METHOD | Quick Action | 16 | 100%
[72 empty] | 23 | METHOD | Quick Action | 17 | 100%
[72 empty] | 23 | METHOD | Quick Action | 18 | 100%
[72 empty] | 23 | METHOD | Quick Action | 19 | 100%
[72 empty] | 23 | METHOD | Quick Action | 20 | 100%
[72 empty] | 23 | METHOD | Quick Action | 21 | 100%
[72 empty] | 23 | METHOD | Quick Action | 22 | 100%
[72 empty] | 23 | METHOD | Quick Action | 23 | 100%
[72 empty] | 23 | METHOD | Quick Action | 24 | 100%
[72 empty] | 23 | METHOD | Quick Action | 25 | 100%
[72 empty] | 23 | METHOD | Quick Action | 26 | 100%
[72 empty] | 23 | METHOD | Quick Action | 27 | 100%
[72 empty] | 23 | METHOD | Quick Action | 28 | 100%
[72 empty] | 23 | METHOD | Quick Action | 29 | 100%
[72 empty] | 23 | METHOD | Quick Action | 30 | 100%
[72 empty] | 23 | METHOD | Quick Action | 31 | 100%
[72 empty] | 24 | METHOD | Quick Action | 1 | 0%
[72 empty] | 24 | METHOD | Quick Action | 2 | 0%
[72 empty] | 24 | METHOD | Quick Action | 3 | 100%
[72 empty] | 24 | METHOD | Quick Action | 4 | 100%
[72 empty] | 24 | METHOD | Quick Action | 5 | 100%
[72 empty] | 24 | METHOD | Quick Action | 6 | 100%
[72 empty] | 24 | METHOD | Quick Action | 7 | 100%
[72 empty] | 24 | METHOD | Quick Action | 8 | 100%
[72 empty] | 24 | METHOD | Quick Action | 9 | 100%
[72 empty] | 24 | METHOD | Quick Action | 10 | 100%
[72 empty] | 24 | METHOD | Quick Action | 11 | 100%
[72 empty] | 24 | METHOD | Quick Action | 12 | 100%
[72 empty] | 24 | METHOD | Quick Action | 13 | 100%
[72 empty] | 24 | METHOD | Quick Action | 14 | 100%
[72 empty] | 24 | METHOD | Quick Action | 15 | 100%
[72 empty] | 24 | METHOD | Quick Action | 16 | 100%
[72 empty] | 24 | METHOD | Quick Action | 17 | 100%
[72 empty] | 24 | METHOD | Quick Action | 18 | 100%
[72 empty] | 24 | METHOD | Quick Action | 19 | 100%
[72 empty] | 24 | METHOD | Quick Action | 20 | 100%
[72 empty] | 24 | METHOD | Quick Action | 21 | 100%
[72 empty] | 24 | METHOD | Quick Action | 22 | 100%
[72 empty] | 24 | METHOD | Quick Action | 23 | 100%
[72 empty] | 24 | METHOD | Quick Action | 24 | 100%
[72 empty] | 24 | METHOD | Quick Action | 25 | 100%
[72 empty] | 24 | METHOD | Quick Action | 26 | 100%
[72 empty] | 24 | METHOD | Quick Action | 27 | 100%
[72 empty] | 24 | METHOD | Quick Action | 28 | 100%
[72 empty] | 24 | METHOD | Quick Action | 29 | 100%
[72 empty] | 24 | METHOD | Quick Action | 30 | 100%
[72 empty] | 24 | METHOD | Quick Action | 31 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 1 | 0%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 2 | 0%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 3 | 0%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 4 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 5 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 6 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 7 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 8 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 9 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 10 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 11 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 12 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 13 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 14 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 15 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 16 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 17 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 18 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 19 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 20 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 21 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 22 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 23 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 24 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 25 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 26 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 27 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 28 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 29 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 30 | 100%
[72 empty] | 25 | ENVIRONMENT | Long Term / Development | 31 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 1 | 0%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 2 | 0%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 3 | 0%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 4 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 5 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 6 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 7 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 8 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 9 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 10 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 11 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 12 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 13 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 14 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 15 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 16 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 17 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 18 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 19 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 20 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 21 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 22 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 23 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 24 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 25 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 26 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 27 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 28 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 29 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 30 | 100%
[72 empty] | 26 | ENVIRONMENT | Long Term / Development | 31 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 1 | 0%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 2 | 0%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 3 | 0%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 4 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 5 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 6 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 7 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 8 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 9 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 10 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 11 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 12 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 13 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 14 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 15 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 16 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 17 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 18 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 19 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 20 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 21 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 22 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 23 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 24 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 25 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 26 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 27 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 28 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 29 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 30 | 100%
[72 empty] | 27 | ENVIRONMENT | Long Term / Development | 31 | 100%

## PIVOT
| 5 FACTOR | (Multiple Items)
| CATEGORY | (Multiple Items) |  |  |  | JUMLAH TOTAL
[6 empty] | CATEGORY | JUMLAH | COMPLETION RATE
PT2 | Row Labels | Count of NO |  |  |  | CLOSE | 19 | 70.37% | 29.63%
| CLOSE | 19 |  |  |  | OPEN | 1 | 29.63%
| ON PROGRESS | 7 |  |  |  | ON PROGRESS | 7
| OPEN | 1 |  |  |  | TOTAL | 27
| Grand Total | 27
| 5 FACTOR | (Multiple Items)
| CATEGORY | (Multiple Items)
JUMLAH OVERDUE
PT3 |  | Column Labels |  |  |  | JUMLAH | STATUS
|  | < 14 HARI | OVERDUE |  |  | 0 | > 14 Hari
| Count of NO | 1 | 7 |  |  | 1 | < 14 Hari
[6 empty] | 0 | < 7 Hari
[6 empty] | 0 | < 3 Hari
[6 empty] | 7 | Overdue
PT7 | 5 FACTOR | (Multiple Items)
| CATEGORY | (Multiple Items)
| Count of STATUS | Column Labels | [11 empty] | OPEN | CLOSED
| Row Labels | OPEN | ON PROGRESS | CLOSE |  |  |  | DEPARTMENT | TOTAL | OPEN | PROGRESS | UNCLOSED | CLOSE | COMPLETION RATE
| AGUS Y |  |  | 3 |  |  |  | AGUS Y | 3 | 0 | 0 | 0 | 3 | 0% | 100%
| AMIN |  |  | 2 |  |  |  | AMIN | 2 | 0 | 0 | 0 | 2 | 0% | 100%
| ANDREAS |  | 4 | 2 |  |  |  | ANDREAS | 6 | 0 | 4 | 4 | 2 | 66.67% | 33.33%
| GS |  |  | 1 |  |  |  | GS | 1 | 0 | 0 | 0 | 1 | 0% | 100%
| GS HO |  |  | 2 |  |  |  | GS HO | 2 | 0 | 0 | 0 | 2 | 0% | 100%
| HC | 1 | 1 |  |  |  |  | HC | 2 | 1 | 1 | 2 | 0 | 100% | 0%
| HO |  |  | 2 |  |  |  | HO | 2 | 0 | 0 | 0 | 2 | 0% | 100%
| OLOWAN |  |  | 1 |  |  |  | OLOWAN | 1 | 0 | 0 | 0 | 1 | 0% | 100%
| PLANT-LOG |  |  | 1 |  |  |  | PLANT-LOG | 1 | 0 | 0 | 0 | 1 | 0% | 100%
| SLD |  | 2 | 3 |  |  |  | SLD | 5 | 0 | 2 | 2 | 3 | 40% | 60%
| YOHANES |  |  | 2 |  |  |  | YOHANES | 2 | 0 | 0 | 0 | 2 | 0% | 100%
[8 empty] | #N/A |  |  |  | #VALUE! |  |  | #N/A
[8 empty] | #N/A |  |  |  | #VALUE! |  |  | #N/A
[8 empty] | #N/A |  |  |  | #VALUE! |  |  | #N/A
[8 empty] | #N/A |  |  |  | #VALUE! |  |  | #N/A
PT5 | 5 FACTOR | (Multiple Items)
| CATEGORY | (Multiple Items)
| Row Labels | COMPLETION RATE
| AGUS Y | 100%
| AMIN | 100%
| ANDREAS | 33.33%
| GS | 100%
| GS HO | 100%
| HC | 0%
| HO | 100%
| OLOWAN | 100%
| PLANT-LOG | 100%
| SLD | 60%
| YOHANES | 100%
| Sum of VALUE | Column Labels |  |  | DOZER READINESS
| Row Labels | PLAN | ACTUAL
| 1 | 16 | 15
| 2 | 16 | 13
| 3 | 16 | 14
| 4 | 16 | 11
| 5 | 16 | 16
| 6 | 16 | 14
| 7 | 16 | 16
| 8 | 16 | 15
| 9 | 16 | 13
| 10 | 16 | 14
| 11 | 16 | 11
| 12 | 16 | 16
| 13 | 16 | 14
| 14 | 16 | 16
| 15 | 16 | 15
| 16 | 16 | 13
| 17 | 16 | 14
| 18 | 16 | 11
| 19 | 16 | 16
| 20 | 16 | 14
| 21 | 16 | 16
| 22 | 16 | 15
| 23 | 16 | 13
| 24 | 16 | 14
| 25 | 16 | 11
| 26 | 16 | 16
| 27 | 16 | 14
| 28 | 16 | 16
| 29 | 16 | 12
| 30 | 16 | 11
| 31 | 16 | 15
| Sum of VALUE | Column Labels |  |  | PA DOZER
| Row Labels | PLAN | ACTUAL
| 1 | 90% | 87%
| 2 | 90% | 80%
| 3 | 90% | 83%
| 4 | 90% | 72%
| 5 | 90% | 100%
| 6 | 90% | 90%
| 7 | 90% | 98%
| 8 | 90% | 93%
| 9 | 90% | 87%
| 10 | 90% | 80%
| 11 | 90% | 83%
| 12 | 90% | 72%
| 13 | 90% | 100%
| 14 | 90% | 90%
| 15 | 90% | 98%
| 16 | 90% | 93%
| 17 | 90% | 87%
| 18 | 90% | 80%
| 19 | 90% | 83%
| 20 | 90% | 72%
| 21 | 90% | 100%
| 22 | 90% | 90%
| 23 | 90% | 98%
| 24 | 90% | 93%
| 25 | 90% | 87%
| 26 | 90% | 80%
| 27 | 90% | 83%
| 28 | 90% | 72%
| 29 | 90% | 100%
| 30 | 90% | 90%
| 31 | 90% | 98%
| Sum of VALUE | Column Labels |  |  | MTBF
| Row Labels | PLAN | ACTUAL
| 1 | 70 | 80
| 2 | 70 | 60
| 3 | 70 | 50
| 4 | 70 | 75
| 5 | 70 | 83
| 6 | 70 | 65
| 7 | 70 | 73
| 8 | 70 | 80
| 9 | 70 | 60
| 10 | 70 | 50
| 11 | 70 | 75
| 12 | 70 | 83
| 13 | 70 | 65
| 14 | 70 | 73
| 15 | 70 | 80
| 16 | 70 | 60
| 17 | 70 | 50
| 18 | 70 | 75
| 19 | 70 | 83
| 20 | 70 | 65
| 21 | 70 | 73
| 22 | 70 | 80
| 23 | 70 | 60
| 24 | 70 | 50
| 25 | 70 | 75
| 26 | 70 | 83
| 27 | 70 | 65
| 28 | 70 | 73
| 29 | 70 | 75
| 30 | 70 | 83
| 31 | 70 | 65
| Grand Total | 2170 | 2167
| Sum of VALUE | Column Labels
| Row Labels | PLAN | ACTUAL |  | MTTR
| 1 | 80 | 80
| 2 | 80 | 60
| 3 | 80 | 50
| 4 | 80 | 75
| 5 | 80 | 83
| 6 | 80 | 65
| 7 | 80 | 73
| 8 | 80 | 80
| 9 | 80 | 60
| 10 | 80 | 50
| 11 | 80 | 75
| 12 | 80 | 83
| 13 | 80 | 65
| 14 | 80 | 73
| 15 | 80 | 80
| 16 | 80 | 60
| 17 | 80 | 50
| 18 | 80 | 75
| 19 | 80 | 83
| 20 | 80 | 65
| 21 | 80 | 73
| 22 | 80 | 80
| 23 | 80 | 60
| 24 | 80 | 50
| 25 | 80 | 75
| 26 | 80 | 83
| 27 | 80 | 65
| 28 | 80 | 73
| 29 | 80 | 75
| 30 | 80 | 83
| 31 | 80 | 65
| Grand Total | 2480 | 2167
| Sum of VALUE | Column Labels
| Row Labels | DOZER READINESS | MTBF | PA ALL DOZER | MTTR
| 1 | 93.75% | 114.3% | 96.67% | 100%
| 2 | 81.25% | 85.71% | 88.89% | 75%
| 3 | 87.5% | 71.43% | 92.22% | 62.5%
| 4 | 68.75% | 107.1% | 80% | 93.75%
| 5 | 100% | 118.6% | 111.1% | 103.8%
| 6 | 87.5% | 92.86% | 100% | 81.25%
| 7 | 100% | 104.3% | 108.9% | 91.25%
| 8 | 93.75% | 114.3% | 103.3% | 100%
| 9 | 81.25% | 85.71% | 96.67% | 75%
| 10 | 87.5% | 71.43% | 88.89% | 62.5%
| 11 | 68.75% | 107.1% | 92.22% | 93.75%
| 12 | 100% | 118.6% | 80% | 103.8%
| 13 | 87.5% | 92.86% | 111.1% | 81.25%
| 14 | 100% | 104.3% | 100% | 91.25%
| 15 | 93.75% | 114.3% | 108.9% | 100%
| 16 | 81.25% | 85.71% | 103.3% | 75%
| 17 | 87.5% | 71.43% | 96.67% | 62.5%
| 18 | 68.75% | 107.1% | 88.89% | 93.75%
| 19 | 100% | 118.6% | 92.22% | 103.8%
| 20 | 87.5% | 92.86% | 80% | 81.25%
| 21 | 100% | 104.3% | 111.1% | 91.25%
| 22 | 93.75% | 114.3% | 100% | 100%
| 23 | 81.25% | 85.71% | 108.9% | 75%
| 24 | 87.5% | 71.43% | 103.3% | 62.5%
| 25 | 68.75% | 107.1% | 96.67% | 93.75%
| 26 | 100% | 118.6% | 88.89% | 103.8%
| 27 | 87.5% | 92.86% | 92.22% | 81.25%
| 28 | 100% | 104.3% | 80% | 91.25%
| 29 | 75% | 107.1% | 111.1% | 93.75%
| 30 | 68.75% | 118.6% | 100% | 103.8%
| 31 | 93.75% | 92.86% | 108.9% | 81.25%
| Grand Total | 2712% | 3096% | 3021% | 2709%
| Sum of VALUE | Column Labels
|  | DOZER READINESS |  | DAILY ACHIVEMENT
| Row Labels | ACTUAL | PLAN | ACTUAL | PLAN
| 1 | 15 | 16 | 0.025926 | 0.022222
| 2 | 13 | 16 | 0.059259 | 0.044444
| 3 | 14 | 16 | 0.1 | 0.096296
| 4 | 11 | 16 | 0.18519 | 0.14815
| 5 | 16 | 16 | 0.26296 | 0.21111
| 6 | 14 | 16 | 0.35556 | 0.28889
| 7 | 16 | 16 | 0.47037 | 0.38889
| 8 | 15 | 16 | 0.57037 | 0.48889
| 9 | 13 | 16 | 0.65556 | 0.58889
| 10 | 14 | 16 | 0.74074 | 0.68889
| 11 | 11 | 16 | 0.8 | 0.76667
| 12 | 16 | 16 | 0.85926 | 0.84444
| 13 | 14 | 16 | 0.91852 | 0.89259
| 14 | 16 | 16 | 0.97037 | 0.94074
| 15 | 15 | 16 | 1 | 0.97778
| 16 | 13 | 16 | 1 | 1
| 17 | 14 | 16 | 1 | 1
| 18 | 11 | 16 | 1 | 1
| 19 | 16 | 16 | 1 | 1
| 20 | 14 | 16 | 1 | 1
| 21 | 16 | 16 | 1 | 1
| 22 | 15 | 16 | 1 | 1
| 23 | 13 | 16 | 1 | 1
| 24 | 14 | 16 | 1 | 1
| 25 | 11 | 16 | 1 | 1
| 26 | 16 | 16 | 1 | 1
| 27 | 14 | 16 | 1 | 1
| 28 | 16 | 16 | 1 | 1
| 29 | 12 | 16 | 1 | 1
| 30 | 11 | 16 | 1 | 1
| 31 | 15 | 16 | 1 | 1
| Grand Total | 434 | 496 | 23.9741 | 23.3889
| ACH | Column Labels
| DAYS | ACTUAL | PLAN
| 1 | 2.593% | 2.222%
| 2 | 5.926% | 4.444%
| 3 | 10% | 9.63%
| 4 | 18.52% | 14.81%
| 5 | 26.3% | 21.11%
| 6 | 35.56% | 28.89%
| 7 | 47.04% | 38.89%
| 8 | 57.04% | 48.89%
| 9 | 65.56% | 58.89%
| 10 | 74.07% | 68.89%
| 11 | 80% | 76.67%
| 12 | 85.93% | 84.44%
| 13 | 91.85% | 89.26%
| 14 | 97.04% | 94.07%
| 15 | 100% | 97.78%
| 16 | 100% | 100%
| 17 | 100% | 100%
| 18 | 100% | 100%
| 19 | 100% | 100%
| 20 | 100% | 100%
| 21 | 100% | 100%
| 22 | 100% | 100%
| 23 | 100% | 100%
| 24 | 100% | 100%
| 25 | 100% | 100%
| 26 | 100% | 100%
| 27 | 100% | 100%
| 28 | 100% | 100%
| 29 | 100% | 100%
| 30 | 100% | 100%
| 31 | 100% | 100%
| DATE | DOZER READINESS | DAILY ACTUAL | DAILY PLAN
| 1 | 15 | 2.593% | 2.222%
| 2 | 15 | 5.926% | 4.444%
| 3 | 13 | 10% | 9.63%
| 4 | 13 | 18.52% | 14.81%
| 5 | 14 | 26.3% | 21.11%
| 6 | 14 | 35.56% | 28.89%
| 7 | 11 | 47.04% | 38.89%
| 8 | 11 | 57.04% | 48.89%
| 9 | 16 | 65.56% | 58.89%
| 10 | 16 | 74.07% | 68.89%
| 11 | 14 | 80% | 76.67%
| 12 | 14 | 85.93% | 84.44%
| 13 | 16 | 91.85% | 89.26%
| 14 | 16 | 97.04% | 94.07%
| 15 | 15 | 100% | 97.78%
| 16 | 15 | 100% | 100%
| 17 | 13 | 100% | 100%
| 18 | 13 | 100% | 100%
| 19 | 14 | 100% | 100%
| 20 | 14 | 100% | 100%
| 21 | 11 | 100% | 100%
| 22 | 11 | 100% | 100%
| 23 | 16 | 100% | 100%
| 24 | 16 | 100% | 100%
| 25 | 14 | 100% | 100%
| 26 | 14 | 100% | 100%
| 27 | 16 | 100% | 100%
| 28 | 16 | 100% | 100%
| 29 | 15 | 100% | 100%
| 30 | 15 | 100% | 100%
| 31 | 13 | 100% | 100%
| DATE | PA DOZER | DAILY ACTUAL | DAILY PLAN
| 1 | 87% | 2.593% | 2.222%
| 2 | 87% | 5.926% | 4.444%
| 3 | 80% | 10% | 9.63%
| 4 | 80% | 18.52% | 14.81%
| 5 | 83% | 26.3% | 21.11%
| 6 | 83% | 35.56% | 28.89%
| 7 | 72% | 47.04% | 38.89%
| 8 | 72% | 57.04% | 48.89%
| 9 | 100% | 65.56% | 58.89%
| 10 | 100% | 74.07% | 68.89%
| 11 | 90% | 80% | 76.67%
| 12 | 90% | 85.93% | 84.44%
| 13 | 98% | 91.85% | 89.26%
| 14 | 98% | 97.04% | 94.07%
| 15 | 93% | 100% | 97.78%
| 16 | 93% | 100% | 100%
| 17 | 87% | 100% | 100%
| 18 | 87% | 100% | 100%
| 19 | 80% | 100% | 100%
| 20 | 80% | 100% | 100%
| 21 | 83% | 100% | 100%
| 22 | 83% | 100% | 100%
| 23 | 72% | 100% | 100%
| 24 | 72% | 100% | 100%
| 25 | 100% | 100% | 100%
| 26 | 100% | 100% | 100%
| 27 | 90% | 100% | 100%
| 28 | 90% | 100% | 100%
| 29 | 98% | 100% | 100%
| 30 | 98% | 100% | 100%
| 31 | 93% | 100% | 100%
| DATE | MTBF (H) | DAILY ACTUAL | DAILY PLAN
| 1 | 80 | 2.593% | 2.222%
| 2 | 80 | 5.926% | 4.444%
| 3 | 60 | 10% | 9.63%
| 4 | 60 | 18.52% | 14.81%
| 5 | 50 | 26.3% | 21.11%
| 6 | 50 | 35.56% | 28.89%
| 7 | 75 | 47.04% | 38.89%
| 8 | 75 | 57.04% | 48.89%
| 9 | 83 | 65.56% | 58.89%
| 10 | 83 | 74.07% | 68.89%
| 11 | 65 | 80% | 76.67%
| 12 | 65 | 85.93% | 84.44%
| 13 | 73 | 91.85% | 89.26%
| 14 | 73 | 97.04% | 94.07%
| 15 | 80 | 100% | 97.78%
| 16 | 80 | 100% | 100%
| 17 | 60 | 100% | 100%
| 18 | 60 | 100% | 100%
| 19 | 50 | 100% | 100%
| 20 | 50 | 100% | 100%
| 21 | 75 | 100% | 100%
| 22 | 75 | 100% | 100%
| 23 | 83 | 100% | 100%
| 24 | 83 | 100% | 100%
| 25 | 65 | 100% | 100%
| 26 | 65 | 100% | 100%
| 27 | 73 | 100% | 100%
| 28 | 73 | 100% | 100%
| 29 | 80 | 100% | 100%
| 30 | 80 | 100% | 100%
| 31 | 60 | 100% | 100%
| DATE | MTTR (H) | DAILY ACTUAL | DAILY PLAN
| 1 | 80 | 2.593% | 2.222%
| 2 | 80 | 5.926% | 4.444%
| 3 | 60 | 10% | 9.63%
| 4 | 60 | 18.52% | 14.81%
| 5 | 50 | 26.3% | 21.11%
| 6 | 50 | 35.56% | 28.89%
| 7 | 75 | 47.04% | 38.89%
| 8 | 75 | 57.04% | 48.89%
| 9 | 83 | 65.56% | 58.89%
| 10 | 83 | 74.07% | 68.89%
| 11 | 65 | 80% | 76.67%
| 12 | 65 | 85.93% | 84.44%
| 13 | 73 | 91.85% | 89.26%
| 14 | 73 | 97.04% | 94.07%
| 15 | 80 | 100% | 97.78%
| 16 | 80 | 100% | 100%
| 17 | 60 | 100% | 100%
| 18 | 60 | 100% | 100%
| 19 | 50 | 100% | 100%
| 20 | 50 | 100% | 100%
| 21 | 75 | 100% | 100%
| 22 | 75 | 100% | 100%
| 23 | 83 | 100% | 100%
| 24 | 83 | 100% | 100%
| 25 | 65 | 100% | 100%
| 26 | 65 | 100% | 100%
| 27 | 73 | 100% | 100%
| 28 | 73 | 100% | 100%
| 29 | 80 | 100% | 100%
| 30 | 80 | 100% | 100%
| 31 | 60 | 100% | 100%
| DATE | DAILY ACTUAL | DAILY PLAN | MTTR (H) | Sum of DOZER_READINESS | Sum of PA_DOZER | Sum of MTBF
| 1 | 2.593% | 2.222% | 80 | 15 | 87% | 80
| 2 | 5.926% | 4.444% | 80 | 15 | 87% | 80
| 3 | 10% | 9.63% | 60 | 13 | 80% | 60
| 4 | 18.52% | 14.81% | 60 | 13 | 80% | 60
| 5 | 26.3% | 21.11% | 50 | 14 | 83% | 50
| 6 | 35.56% | 28.89% | 50 | 14 | 83% | 50
| 7 | 47.04% | 38.89% | 75 | 11 | 72% | 75
| 8 | 57.04% | 48.89% | 75 | 11 | 72% | 75
| 9 | 65.56% | 58.89% | 83 | 16 | 100% | 83
| 10 | 74.07% | 68.89% | 83 | 16 | 100% | 83
| 11 | 80% | 76.67% | 65 | 14 | 90% | 65
| 12 | 85.93% | 84.44% | 65 | 14 | 90% | 65
| 13 | 91.85% | 89.26% | 73 | 16 | 98% | 73
| 14 | 97.04% | 94.07% | 73 | 16 | 98% | 73
| 15 | 100% | 97.78% | 80 | 15 | 93% | 80
| 16 | 100% | 100% | 80 | 15 | 93% | 80
| 17 | 100% | 100% | 60 | 13 | 87% | 60
| 18 | 100% | 100% | 60 | 13 | 87% | 60
| 19 | 100% | 100% | 50 | 14 | 80% | 50
| 20 | 100% | 100% | 50 | 14 | 80% | 50
| 21 | 100% | 100% | 75 | 11 | 83% | 75
| 22 | 100% | 100% | 75 | 11 | 83% | 75
| 23 | 100% | 100% | 83 | 16 | 72% | 83
| 24 | 100% | 100% | 83 | 16 | 72% | 83
| 25 | 100% | 100% | 65 | 14 | 100% | 65
| 26 | 100% | 100% | 65 | 14 | 100% | 65
| 27 | 100% | 100% | 73 | 16 | 90% | 73
| 28 | 100% | 100% | 73 | 16 | 90% | 73
| 29 | 100% | 100% | 80 | 15 | 98% | 80
| 30 | 100% | 100% | 80 | 15 | 98% | 80
| 31 | 100% | 100% | 60 | 13 | 93% | 60
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## DASHBOARD
DASHBOARD IMPROVEMENT DOZER
ACHIVEMENT ACTION PLAN VS ACTUAL
ACHIVEMENT PARAMETER
27
1
7
70,37%
TOTAL ISSUE
OPEN
OVERDUE
COMPLETION RATE
DISTRIBUSI STATUS
19
CLOSED
7
PROGRESS
COMPLETION RATE
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
DOZER READINESS VS ACH
MTBF VS ACH
PA DOZER VS ACH
MTTR VS ACH
PLAN VS ACTUAL DOZER READINESS
PLAN VS ACTUAL MTBF
PLAN VS ACTUAL PA DOZER
PLAN VS ACTUAL MTTR